## Slide 1: Twinning Reform 2016-17 The Spoken word counts
8th Joint Training for RTAs with assignments in IPA and ENI regions
6 July 2018
Claus Lech

## Slide 2: Twinning is Institution Building
Nothing is possible without individuals.
Nothing is lasting without institutions.
Jean Monnet
(but "men" changed to "individuals")

## Slide 3: Short overview
1. The Team
2. A snapshot in statistics – and a reminder!
3. The Twinning reform focus incl. PAR
4. Some step by step advice
5. Advice on preparing the contract
6. Timetable
7. New versus old
8. Manual update and latest news

## Slide 4: 1. The Twinning Team
Christophe (1 FTE) |  | Francesca |  | Kaido | 
Albania |  | Algeria |  | Armenia | 
Belarus |  | the former Yugoslav Republic of Macedonia |  | Kosovo* | 
Bosnia & Herzegovina |  | Israel |  | Egypt | 
Tunisia |  | Palestine |  | Lebanon | 
Georgia |  | Azerbaijan |  | Jordan | 
Ukraine |  | Serbia |  | Morocco | 
Turkey |  | Moldova |  | Montenegro | 
Notes: * This designation is without prejudice to positions on status, and is in line with UNSCR 1244/1999 and the ICJ Opinion on the Kosovo declaration of independence.

## Slide 5: 1. The Twinning Team
Mandated Bodies: Christophe
Pipeline Coordination and bi-annual info to NCPs: Christophe
Harmonisation new Twinning Database, statistics: Kaido
Overall IBD coordination: Francesca
RTA Training coordination: Francesca
Twinning Functional Mailbox: Christophe
Maintenance and Updates of NCP-lists etc for webpage etc.: Kaido
Ex-IPA HQ coordination SC procedure Old Manual: Depending on Country
Focus Group and EU MS Coordination incl. IBD: Claus/Francesca
Horizontal Twinning Evaluation coordination: Francesca
Problem cases requiring litigation: Claus/Christophe
Coordination CFA/Legal Units/CoA, EUD/MS/PC triangle dialogues: Claus
Communication/Visibility issues and Twinning Newsletter: Stefania

## Slide 6: 2. Twinning circulated by Beneficiary country in IPA and ENI regions.

## Slide 7: 2. Twinning awarded to MSs in IPA and ENI region.

## Slide 8: 2a. Reminder - Twinning is not TA
Twinning is a JOINT undertaking – it is peer-to-peer cooperation – between professionals in Public administrations
Twinning requires Political committment from both the EU MS and the PC administration
Twinning places a high level adviser from an EU MS INSIDE the PC administration for the full period
Twinning selection not influenced by ”price”
Solid compensation base regulated in a Commission Decision
Twinning offers maximum flexibility at implementation stage
Twinning works under the PAR agenda
Twinning if no PC Administration capacity?

## Slide 9: 3. Twinning – reform focus
Preparing Twinning for the future by addressing
Simplification of processes
Speed (contracting and start) & Flexibility (implementation)
Common rules for Twinning for IPA/ENI
Alignment other EU developments (performance indicators/monitoring/evaluation and policies) incl C&V
Twinning always to work under the PAR agenda
A solid and simple Compensation model for all EU MS
Protecting the key concepts behind Twinning
One year down the line – lessons learned –> revision June 2018
Is simplification always ending in complexity?

## Slide 10: Twinning to be in line with PAR-principles Twinning aligned with PAR principles – a key to sustainability
We have so far assumed that
  Twinning always contributes to PAR efforts in the country
  Basically all support to acquis alignment improves capacity for implementation and enforcement
  Improving administrative capacity in one institution has a positive spill-over effect to other parts of administration
but that requires the application of same basic principles across all Twinning projects

## Slide 11: Align with NEAR developments - PAR Relationship with sectorial policies
PAR
Education
Employment
Agriculture
Environment
Transport and connectivity
Health
As seen in the past:
PAR
Education
Employment
Agriculture
Environment
Transport and connectivity
Health
As advocated now:

## Slide 12: New approach Areas where PAR and sectors connect
Sector policy planning
Sector strategy preparation
Monitoring and reporting on
implementation of policies
Policy /law making procedures
Human resources management
Transparency/access to information
Rationality of state administrative
structures
Administrative procedures
IT systems
Budgeting procedures
Capital investment planning
Accountability /internal control
Public procurement
PAR
Education
Employment
Agriculture
Environment
Transport and connectivity
Health
Customs
Notes: Public administration is internally: Institutions, public servants, systems (IT, etc.), procedures (for preapring policies, legislation, budgeting, assistance design)
External face of public administration: Accountability, service delivery

## Slide 13: Six core areas defined by Principles of Public Administration
Policy development and coordination
Public service and human resources management
Accountability
Service delivery
Public financial management

## Slide 14: Key Principles impacting twinning projects
Laws and policies are prepared in an inclusive and evidence-based process (Better Regulation)
Policy development and coordination
Notes: Twinning projects focus both on content and the quality of legislative/policy-making process
Twinning supports with impact assessments
Twinning helps to ensure inter-
inter-institutional coordination
Twinning helps to ensure
timely public consultations
Fast-track adoption of laws in
parliaments only exception

## Slide 15: Key Principles impacting twinning projects
The government ensures regular monitoring and reporting on implementation of policy objectives (incl. sector strategies) and publication of monitoring reports
Policy development and coordination
Notes: Twinning/IB projects should not do monitoring/reporting on behalf of beneficiaries, but should help to build capacity for monitoring and reporting (e.g. data collection, reporting on outcomes instead of activities, etc.)

## Slide 16: Key Principles impacting twinning projects
Professional, merit-based civil service with transparent salary structures and human resources management
Public service and human resources management
Notes: Twinning/IB projects should not promote salary top-up schemes and/or exclusion of certain groups/categories of civil servants from civil service.

## Slide 17: Key Principles impacting twinning projects
Rational organisation of state administration and clear accountability lines between institutions, including supervision and reporting between parent ministries and agencies
Accountability
Notes: Twinning/IB projects should avoid setting up new agencies that have unclear reporting lines to parent ministries or report directly to government/parliament. Accountability (supervision, reporting) should be addressed as part of project activities.

## Slide 18: Key Principles impacting twinning projects
One general law on administrative procedures and a limited number of sector laws with special procedures
Service delivery
Notes: Twinning/IB projects should not promote special administrative procedures, if a country has adopted a general Law on Administrative Procedures

## Slide 19: Key Principles impacting twinning projects
The budget is formulated with comprehensive spending appropriations, consistent with the medium-term budgetary framework. As part of this, capital investment projects are subject to appropriate investment analysis and prioritised according to their overall final costs and benefits
Public financial management
Notes: Twinning/IB projects should support with proper investment analysis and investment planning.

## Slide 20: Some practical advice
0. Liaise regularly with the EU Delegation PAR Task Manager
and the Partner Country leading Institution/person to know about ongoing horizontal PAR projects.
Ask for any studies and/or expert assessments that they could share and consider useful for your work.

## Slide 21: Practical advice provided to RTAs …
1. Get well acquainted with the overall PAR agenda and the administrative environment within which the institution and the staff you are working with operate.
Notes: Concretely:
Read the Principles of Public Administration (available on OECD/SIGMA website) to familiarise with the PAR policy framework
Read the SIGMA assessment reports (available on OECD/SIGMA website) to get an overall and detail view of the functioning of PA and the administrative environment you are working in
Read the country's PAR strategy and available implementation reports.
Get well acquainted with the procedural law/policy-making requirements in the country
Liaise with PAR experts (SIGMA and ongoing projects) to understand the main challenges in the administrative environment.

## Slide 22
2. Ensure that any legal texts, organisational structures, procedures and job profiles the Twinning project advocates are in line with the administrative culture of the country, the commitments made in the Stabilisation and Association Agreements or Association Agreements, and the Principles of Public Administration.
Practical advice provided to RTAs
Notes: Concretely:
Avoid promoting specific administrative procedures in a specific sector, if the country has adopted a modern Law on General Administrative Procedures; if necessary, ensure consistency between general and special administrative procedures
Avoid supporting creation of agencies unless clear accountability and reporting lines to parent institutions are ensured
Do not promote specific salary top-up schemes for specific groups of civil servants

## Slide 23: Practical advice provided to RTAs
3. Help the institutions to ensure an inclusive and evidence-based policy- and law-making process in line with the Better Regulation approach
Notes: Concretely:
Before supporting the beneficiaries with law/policy drafting, support them with preparation of problem analysis, of policy options, of fiscal and socio-economic impact assessments, estimation of costs of implementation, identification of indicators to assess the achievement of objectives
Support beneficiaries with conducting inter-ministerial consultations
Support beneficiaries with conducting public consultations at the right time of the process, allowing sufficient time for comments
Help to ensure that reports of stakeholder consultations are provided to decision-makers together with draft policy and legislative proposals
Advise and support preparation on reports on implementation of policies because this strengthens ownership

## Slide 24: 4. Twinning – Project Cycle – step by step
1. Project Preparation - key elements
Put realistic results and focus on the most important. Use the best expertise to assist you to define.
Define objectives and results not activities
Indicate key project milestones but don’t detail sequencing
Consider EUD and MS Embassy engagement in the communication/visibility planning
Carefully analyse and justify the need for study tours.
Notes: Use best expertise to assist on the Twinning Fiche description.

## Slide 25: 4. Twinning – Project Cycle – Step by Step
2. Publication, proposals and Selection of Partner
CA to Publish the call at e-call Prospect and send it to call EU MS NCPs as soon as you have the OK by the Twinning Inter-Service Group in EU HQ. React as quickly as possible to the ”opinion” given by EU HQ.
Focus your selection of partner on the one best fitting needs/wishes – meaning focus on the offered methodology, structure used by EU MS, the quality of RTA and the accessibility to expertise defined by the EU MS.
Do not focus on costs – they are to be a large extent regulated in the Commission Decision.

## Slide 26: 4. Twinning – Project Cycle – Step by Step
3. Contract
PC and MS and CA to agree a detailed contract preparation timetable - the selected partner has to provide all information for the contract asap.
Contract at the signature stage is ”sketchy” and only defined at budget heading level and the flat rate budgetlines (contingency/reserve 2,5% and flat indirect 6%) -> Process an addendum after the first Steering Committee
Since all contract cost details - for the first 6 months is only developed at the time when the initial rolling work-plan is agreed

## Slide 27: 4. Twinning – Project Cycle – Step by Step
4. Implementation
- The rolling work plan is the key document for all partners defining what, when, who, where for six-months rolling periods. Invest sufficient resources in developing it.
- A Steering Committee meeting every 3 months is composed of high-level representatives from the Partner Country and the EU MS(s) – (PLs) – steers the project and approve all work-plans. Do dedicate more time to prepare for these. At each SC carefully monitor remaining funds.
- For all Steering Committees all relevant stakeholders in the sector/sub-sector in which the project works, should be invited as observers for the Committee. Do analyse and involve the EUD when discussing who should be part (as observers).

## Slide 28: 4. Twinning – Project Cycle – Step by Step
- The Partner Country should check at Twinning Fiche stage and recheck well before the RTA arrival that adequate office space, meeting rooms etc are available.
- Partner country RTA Counterpart should be fully available and make sure that the RTA is assisted until RTA Assistants recruited
- All partners should engage fully in work-plan preparations as soon as the RTA has arrived – remember to ensure all related departments are on board
- Set aside sufficient time for discussing communication/visibility
- Involve all relevant departments/agencies/institutions in the work-programme planning – public reforms are rarely limited to only one entity (ex - customs -> revenue - taxes - police etc)

## Slide 29: 5. Commission Decision – defining the methodology for unit cost items and flat rates in the contract
Decision 1122 of 21.02.2017
Secures compliance of Twinning with FR Art 124 and defines the very existence of the Twinning manual
Methodology of Commission Decision now Annex B of Twinning Manual
As consequence:
  Unit costs defined at contracting stage (less supporting document requirements at expenditure verification stage) and definition of what the flat rates compensates
  One rate for all EU MS for experts (one fixed flat daily allowance at 350€) and compensation for RTA simplified)
Idea behind the decision
EU under Twinning compensates EU MS (we do not "buy" TA) since Twinning is peer-to-peer and
NB: Manual further limits use of non-public administration experts and if used there is still no compensation to EU MS for Twinning project support costs (TPSC) if used.

## Slide 30: 5. The financials – the short version
Commission Decision:
One flat daily allowance set at 350€ for all expert categories
Twinning Project Support Costs and setting the flat rate at 136%
Indirect cost fixed at 6%
Reserve funds fixed at 2.5%
Methodology for flat rates established
Methodology and timing for CA fixing unit costs described
When fixed evidence of "event" triggering the compensation, not of amount
NB: Initial work-plan: To accelerate the preparation of

## Slide 31: 5. The financials – the rules see Annex A7 of Twinning Manual
Reflects the Commission Decision:
Setting one flat daily allowance set at 350€ for all expert categories
Defines what in the contract should be covered by unit costs and flat rates and the timing and method for fixing these – if they cannot be defined – the costs continues to be "actually incurred cost" items with full documentation (procedure/process)
Setting flat rate for Twinning Project Support Costs (TPSC) at 136% and defines the cost related items covered and setting Indirect cost fixed at 6% and defines the cost related items covered
As a consequence:
Certain units costs and all flat rates fixed at contracting stage: Impact - when fixed only evidence that an "event" triggering the compensation took place, no control of actually incurred costs for these amounts

## Slide 32: 5. The Financials – the contract budget Defining the amounts under the budget headings until a rolling plan and the related budget is fixed after first SC
Unit costs and flat rates
  All unit costs defined as such in Commission Decision must be defined and flat rates in decision (136%, 6%) and Manual (reserves 2.5%) introduced
  (Recommendation: Reflect all such in an Annex to Annex A3)
RTA and RTA related costs:
  - Can be fixed with high level of precision (recommendation: 10-25% of DC)
Horisontal costs:
  - up to sums since cost items to some extent are not unit costs but will be actually incurred costs for Communication/Visibility plan (recommendation: 10-15% of DC)
Mandatory results:
  details of activity costs only known when first rolling work-plan is established and the related budget is ready (Recommendation: 60-80% of DC)
Notes: Pages 22-38 is a detailed review on cost items and could be skipped for certain audiences.

## Slide 33: 5. Budget historical data - and advice on defining amounts in the contract (which is now signed BEFORE the rolling work plan & related budget is finalised)
There are 3 budget headings:
Budget Heading 1: RTA and RTA related costs *guestimate 10-25% / DC
Budget Heading 2: Horisontal Cost items *guestimate 10-15% / DC
Budget Heading 3: Mandatory results *guestimate 60-80% / DC
* These percentages are a result of having exposed a representative sample of old Twinning contracts to the compensation levels and rules in the New Manual. These could be used to set the amounts at the contract stage since the rolling work plan and the related budget is not yet finalised). DC=Direct Costs.
Budget line for Indirect costs fixed at 6% of Σ headings 1-3 (DC)
Budget line for Reserves/Contingency fixed at 2,5% of Σ headings 1-3 (DC)
NB1: The cost item sub-headings under the budget headings in Annex A3 of the Twinning Manual is not exhaustive
NB2: Since Unit costs and flat rates are defined: recommendation to reflect these in an Annex to Annex A3 to the contract
Notes: When asked WHY we changes the system for compensating costs for developing Work-plan before Contract signature. This was clearly unacceptable to DG BUDGET who would only exceptionally accept to pay RTA/PC Counterpart training costs if appearing before contract signature. Instead we now compesate the PL (and component leaders and a support staff if relevant) in a capacity as Short Term experts to come to the country and develop the rolling work-plan AFTER the contract is signed only.

## Slide 34: 5. The financials – and contract advice
Get all information from EU MS for introducing correct identification and data for drafting the Contract Special Conditions
Annex A1: Include fiche and the proposal submitted by the EU MS, NB: only after the first SC the rolling work-plan can be added
Annex A2, Annex A4, Annex A5 and Annex A6: Standard
Annex A3: A very draft budget on level of headings only.
NB: only when rolling work-plan is agreed after first SCM the detailed budget can be included.
Annex A7: Don’t touch - regulating financial aspects
Annex A8: If applicable – if consortium agreement to include
Annex A9: Required CVs, declaration by RTA
Notes: * When reformatting the Manual the link has unfortunately been deleted

## Slide 35: 5. Financials - RTA salary compensation*
  Calculation of wage and non-wage compensation RTA described in detail in COM DEC / Annex B -> EU MS to submit details to CA – basis for calculation defined:
Commission Decision text
Wages
"While submitting their analytical accounting statements, Member States shall pay particular attention to specifying all elements taken into consideration.
In the case of wages, reference shall be made to the basic salary and to statutory benefits. The basic salary shall be determined in accordance with the pay grade held: functions performed by the civil servant are therefore irrelevant and solely the pay grade established on the basis of the official remuneration schemes for the public service at national or local level is considered.
The other statutory costs shall include all additional payments in form of statutory benefits linked to specific functions, responsibilities and conditions, as well as specific salary components that are not paid on a monthly basis, such as holiday allowances and additional month(s) payment at the end of the year. Since the diversity of national legislative conditions for remunerating personnel does not allow compiling an exhaustive list of eligible cost components,
Notes: * DG BUDGET required on having these details included. We are discussing the potential un-fair impact of one element with our legal unit.

## Slide 36: 5. RTA salary compensation
Member States shall be guided by the principle that costs which are in line with their usual policy on remuneration and in compliance with the national legislation can be included. Non-statutory, non-mandatory and discretionary premiums or bonuses shall not be included
Non-wage
  Similarly, the institution dispatching the RTA shall receive a reimbursement equalling the non-wage labour costs incurred for the RTA, including compulsory social security contributions such as those related to health, pension, unemployment), based on an analytical accounting statement of the last closed accounting year. The non-wage labour costs should take full account of statutory rights according to the civil service legislation of the given Member State in particular rights of civil servants working abroad, family allowances and insurances" (And further: In the case of non-wage labour costs, reference shall be made to the employer's social contributions such as insurance contributions, payments for healthcare, labour disability, unemployment and other statutory allowances")

## Slide 37: 5. RTA – Travel *
Travel: -> EU MS must inform the CA about private living arrangements of RTA and Contracting Authority to establish unit rate based on 3 offers covering all period of project (or accept to rely on 3 offers presented by EU MS*)
Commission Decision text:
If the RTA moves to the partner country without household effects or family, or both, travel costs can be compensated as a monthly travel allowance to cover return fares with one registered luggage. The amount of this monthly allowance shall be established based on the economically most favourable quote among those provided by three travel agencies before the signature of the Twinning contract. The quotes shall be endorsed by the authority signing the Twinning contract
If the RTA moves to the partner country with household effects or family, or both, travel costs can be compensated as a yearly travel allowance to cover return fares with one registered luggage for the RTA and each accompanying member of his or her family. The amount of this yearly allowance shall be established with the same method used for the monthly allowance.
Notes: It is to be noted that fixing travel allowance for the full life time of the project will all others conditions alike increase this unit cost. And to separate unit cost establishment from purchase

## Slide 38: 5. RTA Subsistence allowance
Per diem: -> EU MS to inform CA of Per diem level for RTA*
Commission Decision Text
While it can be expected that the RTA's salary covers expenses that continue to be borne in the place of origin, the Member State can pay the RTA a daily subsistence allowance to meet the extra costs of living in the partner country, such as lodging, extra security and additional health insurance.
The daily subsistence allowance for the RTA is capped at maximum 75% of the per diem rate for the partner country published by the Directorate-General for International Cooperation and Development (DG DEVCO) and applicable at the signature of the Twinning contract.
Considering that the subsistence allowance for the RTA covers costs that need to be met also during temporary absences such as holidays and business trips, Member States can pay it for the whole duration of the assignment of the RTA in the partner country.
Notes: Please note that a number of EU MS has expressed that the 75% compensation will lead to difficulties to find RTAs for certain countries. We however note that this compensation by all reference calculations made is still better than for any EU Official in EUDs

## Slide 39: 5. Other RTA related costs
-> EU MS to inform CA of other cost items i.e.:
Schooling costs
– capped at same level as used for EU officials and to be based on invoice = actually incurred costs
Removal costs*
– based on 3 offers = actually incurred costs
Training EU HQ
EU MS and PC Administration to flag need for costs for Brussels based RTA training
Notes: * We even tried with EEAS to see if we could find a solid reference for this in order to make it a unit cost - impossible

## Slide 40: 5. The Financials – RTA assistant
-> RTA is to select her own assistant(s ). As consequence the maximum amounts for these will be introduced in contract budget by the CA based on known competitive ceilings
Commission Decision text
"A RTA is normally supported by one, and exceptionally more, full time administrative or language assistant(s), or by an assistant who performs both the role of administrative and language assistant, whose monthly payment(s) shall be budgeted as monthly unit costs, based on the value of the contract(s) signed divided by months of contract duration, following a public procurement procedure and established on a case-by-case basis taking into consideration conditions prevailing in the partner country and indications provided by the local EU Delegation"

## Slide 41: 5. The Financials – Horisontal cost items
-> Partners to agree after EU MS to indication of intensity and engagement of EU MS PL and Component Leaders in
Work-planning – Initial WP now AFTER contract signature
Steering Committees & Communication/visibility activities
-> Exceptional items - CA and EU MS based on detailed needs analysis regarding potential exceptional items related to
infrastructure and meetings facilities and
extra extraordinarily needs of project (heavy translations of acquis, etc)
And subsequently agree on exceptional "up to amounts" to cover such cost items to be reimbursed based on actually incurred cost
-> Limitations to specific cost items the PAO/NIPAC and the EUD and the CA subsequently are always free to include certain well-justified (historically/budget limitations/budget efficiency) limitations into the project fiche (as examples only: max. number of study tours/conferences/minimum visibility)

## Slide 42: 5. The Financials – Horisontal cost items
-> EU MS and CA to agree to a fixed maximum amount for Communication and Visibility (max 3% of Twinning Budget) to be included in the contract budget until the Communication and Visibility Plan has been agreed and co-signed by the EUD
Small-scale Communication and Visibility programme including
Opening/closure
Thematic/milestone events
Minimum: Use of Social Media, Link to EUD webpage
Large-scale Communication and Visibility programme might include
  Development of expensive AV material (films, animations etc)
  Internet/ TV intensive Advertising campaigns
  Full integration into SBS communication plan
Notes: If the project is by EUD is considered a communication platform for delivering key political messages

## Slide 43: 5. The Financials – STE – Flat Daily
Definition
  Member States shall be compensated with a flat daily allowance for the absence from duty of officials or assimilated agents who act as short-term Twinning experts, which means experts being dispatched for less than 29 consecutive calendar days in the partner country. NB: No LTEs or alike. But many RTAs in one Twinning fully possible.
  The flat daily allowance to be paid to Member States to compensate the absence from duty of officials or assimilated agents acting as short-term Twinning experts is 350€/day.
-> Recommendation: The CA could introduce the unit cost in a separate Annex to Annex A3 without defining the detailed number of Units – since only established when the rolling work-plan is ready

## Slide 44: 5. The Financials – STE – Travel
Each time an official or assimilated agent is dispatched to the partner country to act as a short-term expert, travel costs should be compensated on the basis of a travel allowance established based on the economically most favourable quote among those provided by three travel agencies before the signature of the Twinning contract. The quotes shall be endorsed in advance by the authority signing the Twinning contract.
-> Recommendation: The CA to establish unit costs and agree this with the EU MS for all "possibly used" travel routes – we recommend to add as Annex to Annex A3*
Notes: If a travel route later shows not to have been defined the travel will all be based on actually incurred costs requiring the traveller to document the travel including the costs for this

## Slide 45: 5. The Financials – PC staff DSA
Officials or agents of a recipient administration can receive a subsistence allowance when on mission to a Member State. The maximum amount of this allowance corresponds to the per diem rate for the Member State concerned published by DG DEVCO and applicable at the signature of the Twinning contract.
-> Partners to inform CA of activities involving such cost items outside the PC*
Notes: See earlier remark regarding possible limitations set in the project fiche – one should also not forget that EU MS related costs are part of the flat rates – for management costs.

## Slide 46: 5. The Financials – TPSC – ex-TMC Twinning Project Support Costs
Commission Decision defining what cost items are covered by this:
a) costs related to time spent by officials or assimilated agents in the Member State in order to prepare and follow-up their missions in the partner country;
b) costs related to time spent by the Member State(s) project leader(s) in order to coordinate project implementation from his/her home administration without being seconded from his/her post;
c) costs related to time spent and costs incurred for the delivery of activities during study visits of partner country's officials or agents to a Member State;
d) costs related to time devoted to the logistical arrangements necessary for the organisation of activities in the partner country.

## Slide 47: 5. The Financials – TPSC – ex-TMC and defines how the TPSC is calculated
Compensated on the basis of a flat rate of 136% of all flat daily allowances paid for activities delivered in the partner country by short-time experts.
-> CA could introduce the unit cost in an Annex to Annex A3 but the detailed number of Units can only be established when
EU MS has informed about the days of the EU MS PL (and component leaders and one support staff if at all applicable – depends a lot on project complexity*) to take part in preparing the rolling work plan
EU MS has informed about the days of the EU MS PL(s) participation in SCs
EU MS has informed about the days of the EU MS PL(s) participation in Communication / Visibility activities if agreed by EUD
Notes: * Since we live in a modern world we should not encourage travel when we can equally use Video-conferencing, but at least one travel to the PC by the PL MUST be envisaged – also as part of confidence building.

## Slide 48: 5. The Financials – Indirect costs - and what this fixed percentage is to cover
Costs covered
  time devoted to support the drafting of interim and final reports;
  other costs such as training provided to officials, office space and equipment, human resources management, general management and administrative costs of the Member State grantee linked, among other things, to accounting or book-keeping or invoicing
  Limited to 6% (sinced some costs compensated under TPSC)
  -> CA can introduce when figures for Budget Headings 1-3 are calculated (6% of these)

## Slide 49: 5. The Financials – Reserves and what reserves are to be used for
Under the new Twinning Manual there are no longer any unit cost revisions – units costs are fixed at contracting stage.
The 2,5% reserve can only be used for actions/activities to be justified and agreed between the parties and EUD (when the project end is approaching the end) for sustaining the results* of the project. No further definition/limitation is given.
Notes: In old manual only costs related to achieving the mandatory costs were allowed

## Slide 50: 5. The Financials and how to handle contracting / budget challenges*
Since contract will be signed before rolling work plan and related costs is defined we strongly recommend to process an addendum reflecting the rolling work plan (in Annex A1) and related cost items (in Annex A3) immediately after the first SC (Steering committee)
After each SC an updated rolling work plan and the related cost items is signed by the EU MS and PC PLs and addressed to the CA and these updates replaces the existing rolling work-plan and budget
It is for the PLs to closely monitor that the 25% rule on changes between budget headings is complied with and timely request an addendum if needed
Since Twinning is under the grant chapter of FR the budget can never be increased*
A "side letter" is in the new Twinning Manual a term reserved for the "between SC" modifications: It is the responsibility of the PLs to timely notify such urgent modifications of work plan/STE changes etc. The ex-operative side letter is now simply the "Rolling work-plan (which includes the budget)"
The Financial section of the SC reports: record the consumed amounts vs budget
Notes: Since DG BUDGET did not accept to cover costs for contract preparations by the parties – and rolling work plan consequently only defined later
This is seemingly in contrast to Delegation agreements under PAGODA2

## Slide 51: 5. The financials - Other remarks to remember
PLs can opt for only submitting an extensive narrative report bi-annually. If so only a narrative summary of max 3 pages can be required by the CA for each SC
CA's should not add extra controls (monthly reports, additional documentary proofs related to cost items) or in other ways weaken the flexibility or increase red tape, but rather increase their monitoring efforts by project visits & active participation in the SCs
CA's cannot refuse to use the methodology used for establishing unit costs/flat rates.
CA's should always without hesitation flag to the EUD should they consider any implementation aspect being influenced by "irregular" practices.
Partners should not be afraid of agreeing on change of RTA and/or RTA counterpart consider a replacement in case "it simply does not work". Remember that we compensate EU MS – an RTA hence should have a job to come back to if and that the New Twinning Manual allows the EU MS PL to temporarily replace RTA
Irregular "motives" should always be brought to the attention of the Twinning coordinator and the HOC in the EUD.

## Slide 52: 6. Timetable
Activity | Actors | Timeline
Update Analysis (Strategy-Sector-Programme design) | Beneficiary, EUD, PAO | Preparation Phase (PP)
Drafting of the « Twinning fiche » | Beneficiary, EUD, PAO, private experts | PP – time depends on nature and complexity
Final fiche sent to HQs (Brussels) for Assessment before launch | From CA/EUD to DG NEAR Unit C3, Line DGs, CoTE | Only when sufficient quality
Opinion on the fiche | DG NEAR Unit C3 to EUD/CA | 2 weeks
Publication of the fiche | EUD - EuropeAid website | Asap after possible revisions
Circulation of the "Twinning fiche" | Contracting Authorithy to MS NCPs | Same day / close to Publication

## Slide 53: From programming to activity start
6. Timetable |  | 
Proposals | Member States | 8 weeks
Selection meeting | PC by consensus | 2 weeks
Notification of result | Contracting Authorithy | 2 weeks
Preparation of the contract file, filling the templates listed in 3.1.1. | Contracting Authorithy | In max 12 weeks – below in "clear blue" is ONLY advice on how the 12 weeks could be planned
-Requests the CV of the BC PL, RTA counterpart, names and function of Component Leader counterpart) | CA | Asap / in Week 1
- Organise VC with MS PL to clarify: | CA | Asap / In Week 2
the accountancy statement on the compensation of costs related to the RTA |  | 
RTA situation (alone or with family) |  | 

## Slide 54: 6. Timetable
Activity | Actors | Timeline
travel itineraries of the PL, RTA and Short Term experts (who requests 3 offers) |  | 
indicate the plans for participation of the PL(s), Component Leaders and staff in the initial work plan |  | 
indicate the plans for participation of the PLs for communication and visibility activities |  | 
Clarifications related to a general management body (if indicated in the proposal) |  | 
entity issuing payment requests (if different from MS lead entity signing the contract ) |  | 
All data from the MS PL to CA | MS PL | Around week 4
Draft Contract from CA to MS PL | CA | Around week 6

## Slide 55: 6. Timetable
Activity | Actors | Timeline
Contract originals signed by MS PL sent to CA | MS PL | Around week 8
Signature of the original contracts by the CA , initialised Annex A1 and A3 by the BC PL | CA | Around week 10
Contract is signed and now the RTA is seconded and starting the implementation of the project | CA and MS | Max 12 weeks – after the notification of result
Drafting of initial work plan | RTA/MS PL(s)/Component Leaders/staff/ Partner country PL | In 4/6 weeks
First steering committee meeting | RTA/MS PL(s)/Partner country PL, RTA and Component Leaders | 2 weeks
Start of activities | RTA | 4 weeks

## Slide 56: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Update of needs analysis | Beneficiary, EUD, PAO (i.e IPA unit in Line ministries) | Programming phase (PP) | Beneficiary, EUD, PAO (i.e IPA unit in Line ministries) | Prepraration phase (PP)
Drafting of the « Twinning fiche » | Beneficiary, EUD, PAO, private experts | PP - Depends on nature and complexity | Beneficiary, EUD, PAO, private experts | PP - Depends on nature and complexity
Final fiche sent to HQs (Brussels) for Assessment | From EUD to DG NEAR Unit C3, Line DGs, CoTE | Only when sufficient quality | From EUD to DG NEAR Unit C3, Line DGs, CoTE for ENI | After ex-ante approval by CFCD/ EUD
Opinion on the fiche | DG NEAR Unit C3 to EUD | 2 weeks | n/a for IPA, DG NEAR Unit C3 to EUD for ENI | n/a for IPA, 2 weeks for ENI
Publication of the fiche | EUD - EuropeAid website | Asap after possible revisions | Standard TW -DG NEAR Unit C3 for IPA TWL published by EUD for IPA EUD for ENI | Asap after possible revisions following comments by DG NEAR

## Slide 57: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Circulation of the "Twinning fiche" | Contracting Authority to MS NCPs | Same day after Publication | Standard TW -DG NEAR Unit C3, TWL circulated by EUD for IPA Contracting Authority to MS NCPs for ENI | 
Proposals | Member States | TW 8 weeks TWL 6 weeks | Member States | TW 8 weeks TWL 6 weeks
Evaluation of written proposals All participants shall sign Declaration of impartiality (template available annex C18) | BC by consensus of EUD | 2 weeks | BC representatives (3-4 persons, members of the selection panel); EUD/ CFCD observers Declaration signed (PRAG template used) | before the selection meeting

## Slide 58: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Selection meeting 45 min for presentation of MS proposal; 30 min for Q&A | Organised at CA | 2 weeks | Organised at EUD, Chaired by HoC; 30 min for presentation of MS proposal; 30 min for Q&A | 2 weeks after the deadline for submission of proposals
Selection report | BC by consensus | Immediately after the selection meeting | BC representatives (3-4 persons, members of the selection panel); EUD/ CFCD observers; | Decision taken Immediately after the selection meeting; Selection report submitted to EUD in 2 weeks
Notification of result | Contracting Authority | 2 weeks | Contracting Authority | 3 weeks after the selection meeting
Preparation of the contract file, filling the templates listed in 3.1.1. No preparatory period= no preparatory costs before the signature of the contract | Contracting Authority | In max 12 weeks | BC Partners (commented by CFCD, EUD) | In max 4 months after the notification of the results the final draft should be sent to STC, otherwise the preparatory costs are not eligible

## Slide 59: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Secondment of the RTA – Starting the implementation of the project | CA and MS | Max 12 weeks – after the notification of result | MS | Max 1 month after the notification letter for the signature of the contract
Drafting of initial work plan | RTA/MS PLs/CLs/staff | 4/6 weeks |  | 
First steering Committee | RTA/MSPLs | 2 weeks |  | 4 months after the notification of the Contract signature
Start of activities | RTA | 4 weeks | RTA | Coincides with the arrival of the RTA

## Slide 60: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Secondment of the RTA – Starting the implementation of the project | CA and MS | Max 12 weeks – after the notification of result | MS, CA | Max 1 month after the notification letter for the signature of the contract
Drafting of initial work plan | RTA/MS PLs/CLs/staff | 4/6 weeks |  | RTA and MS PL negotiation of the contract : 4 months IPA and 5 months ENI.
First steering Committee | RTA/MS PLs | 2 weeks |  | 4 months after the notification of the Contract signature
Start of activities | RTA | 4 weeks | RTA | Coincides with the arrival of the RTA

## Slide 61: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 | Twinning Manual 2012, revision 2013-14
FINANCIALS | FINANCIALS
One flat daily allowance set at 350€ for all expert categories Recently retired experts (less than three years) before the call for proposal could be engaged in line with the specific requirements | Different experts fees 250/350/450 €for the STEs from MB; Civil servants receive max 250€ Recently retired experts (less than two years) before the call for proposal could be engaged n line with specific requirements Art.5.4.5
Twinning Project Support Costs and setting the flat rate at 136% | Twinning Management costs 150%
Daily subsistence allowance for RTA = 75% of the per-diem for the BC | Daily subsistence allowance for RTA = 50% of the per-diem for the BC
Communication costs 3 % of the Twinning Budget | Max 5000 €for project to 1.000.000€ Max 10000 EUR for project above 1.000.000 €
Three Budget Headings 1. RTA and RTA related costs 2. Horisontal Cost items 3. Mandatory results | Not precise instructions exist
Two budget-lines Budget line Indirect costs fixed at 6% of Σ headings 1-3 (DC) Budget line Reserves (sustainability) fixed at 2,5% of Σ headings 1-3 (DC) | n/a Contingency 2.5 %
Training RTA counterpart and BC PL: Can participate in HQ training. Potential un-clarity under | BC Pl OR RTA counterpart could attend RTA training in Brussels, together with the RTA

## Slide 62: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 | Twinning Manual 2012, revision 2013-14
FINANCIALS | FINANCIALS
- Number of RTA assignments (from months to maximum duration of projects etc) (4.1.6.7) max two consecutive assignments | Max four assignments art. 2.2.2(at least 12 months, max 36 months in one BC)
- Replacement of RTA assistants (from redo to use ranking) (4.1.6.10) | 
- EU MS component leaders designation (from "if relevant" to "obliged") | Not obligatory under the old Twinning manual; EUD always advises the Ms Partner to identify MS./BC Component Leaders in the drafting stage of the Contract
- Curricula to be inserted in the proposal: PL, RTA and CL (2.2) not any more STEs CVs) | PL, RTA, STEs, CL
BA staff available to support the RTA until the RTA assistant can be selected | Similar approach, but not obligatory in line with the TM
Initial work plan (6 months rolling plan for activities): prepared in 4-6 weeks following signature of the contract and arrival of the RTA including Communication and Visibility plan. Work plan to define how much time will be devoted to each activity of the project including STE CVs updates prepared by RTA and RTA counterpart, agreed and signed by two PLs discussed by SCs accepted by all contracting parties (max 14 days after SC) to accelerate the preparation EU MS PL's and/or Component Leaders and/or one support staff | For IPA: OSL 1 prepared together with the Draft Twinning contract, but not subject of approval by the STC; OSL 1 signed together with the twinning contract by the two PLs. Subsequent OSL prepared every three months, approved by the STC ( covering each time period of 6 months ( OSL1 (1-6m; OSL2 4-9 m;OSL3 14m) For ENI:: full contract and workplan prepared before the signature of the contract.

## Slide 63: 7. New Manual vs old Manual
New Twinning Manual, 1st July 2017 | Twinning Manual 2012, revision 2013-14
FINANCIALS | FINANCIALS
Reports – from detailed report every 3 months to possibility to only submit the extensive narrative report part every 6 months* and report to possibly include elements of wider reform context. (5.5.2.2) * In such case the rolling work plan update will still be discussed and so will the financial report and budget update every 3 months. | IQR submitted every three months/approved and discussed at the STC meetings
Bi-annual narrative report (extensive narrative report) | n/a
Costs for the private sector input, max 5000 €per component | 10000€per activity
Supply of equipment (exceptionally and dully justified) max 5000 € per project | 5000 €per project
Changes to the Twinning Contract: Addendum for significant changes and reallocation beyond 25% of the budget headings; Rolling work plan SL | Changes to the Twinning Contract: Addendum for significant changes and reallocations beyond 25% of the ttl budget; OSL SL

## Slide 64: 8. Manual update and news
Corrections/clarifications
Nobody is perfect and we have fund cross-reference mistakes etc. a correction/clarification note was issued just before Christmas last year.
Some extra clarifications and revisions are internally in process now – for instance regarding annex C1, Special Conditions, text harmonisation/clarification
Expansion of Twinning and links to TAIEX
Decision "en principe" by DG DEVCO
PCs and EU always to analyse possible synergies at programming stage
Smaller news from the Twinning Team
General evaluation kicked off - to be finalised end 2018
Database being developed to be a significantly better tool for all
Twinning Review Missions – changes on WHO can exercise this

## Slide 65: For Twinning - always use
https://ec.europa.eu/neighbourhood-enlargement/tenders/twinning_en
And also keep us updated when changes
https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/twinning-manual-revision-2017-final-updated-09-08.pdf
Since there might be smaller corrections introduced

## Slide 66: Further information on PAR
Principles of Public Administration:
http://www.sigmaweb.org/publications/principles-public-administration.htm
OECD/SIGMA baseline measurements and monitoring reports:
http://www.sigmaweb.org/publications/public-governance-monitoring-reports.htm
EU Better Regulation agenda:
http://ec.europa.eu/smart-regulation/better_regulation/key_docs_en.htm
EU Better Regulation Guidelines:
http://ec.europa.eu/smart-regulation/guidelines/toc_guide_en.htm

## Slide 67: THANK YOU
A BIG THANK YOU FOR YOUR ENGAGEMENT IN MAKING TWINNING A SUCCESS