Development and Cooperation EuropeAid

Evaluation of the European Union’s Cooperation

with the occupied Palestinian territory and support to the Palestinian people 2008 – 2013

Final Report

Volume 2

May 2014

___________

Evaluation carried out on behalf of

the European Commission

Development and Cooperation EuropeAid

Development and Cooperation EuropeAid

Consortium composed by

Development Researcher’s Network, ECDPM, ECORYS, PARTICIP

Leader of the Consortium: DRN

Contact Person: Marco Palmini

m.palmini@drn-network.com

Contract No 2012/307554 Version 1

This evaluation was commissioned by the Evaluation Unit of the Directorate General for Development and Cooperation – EuropeAid (European Commission)

The opinions expressed in this document represent the authors’ points of view

which are not necessarily shared by the European Commission or by the authorities of the concerned countries

Evaluation Team

Team Leader:	Joe Saba

Deputy Team Leader: Paolo Scalia

Social Expert: Nick Krafft

Water and Sanitation Expert:	 Jean-Claude Ceuppens

National Expert: Omar Shaban

Research Assistant: Silvia Cifarelli

Quality Advisor: Jean Bossuyt

The evaluation is being managed by the Evaluation Unit of DG DEVCO.

The authors accept sole responsibility for this report, drawn up on behalf of the Commission of the European Communities. The report does not necessarily reflect the views of the Commission.

TABLE OF CONTENTS

Annex 1: Terms of References	4

Annex 2: Bibliography	31

AnneX 3: List of People INTERVIEWED	41

Annex 4: EVALUATION METHODOLOGY	54

Annex 5: DATA evaluation GRID	64

ANNEX 6: NATIONAL CONTEXT	76

Annex 7: Inventory of devco and echo interventions	105

aNNEX 8: Others Donors’ Cooperation	124

ANNEX 9: LIST OF DEVCO INTERVENTIONS IN PALESTINE	126

ANNEX 10: LIST OF ECHO INTERVENTIONS IN PALESTINE	164

Annex 11: Comparative analysis of projects “Result-Oriented Monitoring”	173

Annex 12: Conclusions and Recommendations matrix	181

# Annex 1: Terms of References

# Annex 2: Bibliography

Document on General Development Cooperation Policy

- Barcelona Declaration 1995

- Oslo II (1995) Israeli-Palestinian Interim Agreement on the West Bank and the Gaza Strip, Washington, D.C., 28 September 1995

- Council of the European Union Regulation No 1257/96, Concerning Humanitarian Aid, 20 June 1996

- United Nations, 55/2 “Resolution adopted by the General Assembly United Nations Millennium Declaration”, 2000

- Paris Declarations on Aid Effectiveness, 2005

- Accra Agenda for Action, 2008

EU Documents

EU/ Food security thematic programme

- European Commission Food security thematic programme Thematic Strategy Paper and  MultiAnnual Indicative Programme 2007-2010, 4 May 2007

- European Commission, Annual Action Programme covered by the programming document “Thematic Strategy Paper and Multiannual Indicative Programme 2007-2010” for the Development Cooperation Instrument in favour of Food Security for 2009

- European Commission Food security thematic programme" Thematic Strategy Paper and  MultiAnnual Indicative Programme 2011-2013, 21 December 2010

ENP Policy

- European Commission COM (2003) 393 final, Paving the way for a New Neighborhood Instrument, 1 July 2003

- European Commission SEC(2005) 1521, Implementing and promoting the European Neighborhood Policy -22 November 2005

- European Commission, European Neighborhood& Partnership Instrument - Cross-Border Cooperation - Strategy Paper 2007-2013 - Indicative Programme 2007-2010 - November 2006

- European Commission COM(2007) 774 final, A Strong European Neighborhood Policy, 05 December 2007

- European Commission ENPI Regional Strategy Paper (2007-2013) and Regional Indicative Programme (2007-2010)

- European Commission COM(2010) 207, Taking stock of the European Neighborhood Policy, 12 May 2010

- EEAS COM(2011)200 final, A partnership for democracy and shared prosperity with Southern Mediterranean, 8 March 2011

- EEAS COM(2011)303 final, A new response to a changing Neighborhood, 25 May 2011

EU/PA Background documents

- Council of the European Union, Euro-Mediterranean Interim Association Agreement on Trade and Cooperation between the European Community and the Palestine Liberation Organization (PLO) - Brussels, 24 February 1997

- Council of the European Union Conclusions on the Middle East Peace Process, 8 December 2009

- Council of the European Union Conclusions the Middle East Peace Process, 10 December 2012

- European Commission SEC(2004)565, ENP Country Report Palestinian Authority of the West Bank and Gaza Strip, 12 May 2004

- European Commission COM(2005)458 final, EU-Palestinian cooperation beyond disengagement - towards a two-state solution, 5 October 2005

- European Commission, EU/Palestinian Authority Action Plan 2005

- ECHO, Humanitarian Implementation Plan (HIP), Occupied Palestinian Territory, 07 December 2012

- European Commission, EU/Palestinian Authority Action Plan 2013

- EEAS, Note on Denomination of Palestine, April 2013

- EU Local Strategy on Development Cooperation, 26 October 2011

- European Commission; Note of Mr Landaburu to Commissioner Ferrero-Waldner ; 17 December 2012

- European Commission; Order for Service for the oPT and the PA 2008;

- European Commission; Order for Service for the oPT and the PA 2009 - I tranche;

- European Commission; Order for Service for the oPT and the PA 2009 - II tranche; European Commission; Order for Service for the oPT and the PA 2010 - I tranche

- European Commission; Order for Service for the oPT and the PA 2010 - II tranche

- European Commission; Order for Service for the oPT and the PA 2010 - II tranche - annex

- European Commission; Order for Service for the oPT and the PA 2011 - I tranche

- European Commission; Order for Service for the oPT and the PA 2011 - II tranche

- European Commission; Order for Service for the oPT and the PA 2012 - I tranche

- European Commission; Order for Service for the oPT and the PA 2012 - II tranche

EU/PA Annual Programmes

- European Commission, Annual Action Programme, Implementing Decision and Action Fiches (Part I,II,III), 2008

- European Commission, Annual Action Programme, Implementing Decision and Action Fiches (Part I,II,III), 2009

- European Commission, Annual Action Programme, Implementing Decision and Action Fiches (Part I,II,III), 2010

- European Commission, Annual Action Programme, Implementing Decision and Action Fiches (Part I,II,III, IV), 2011

- European Commission, Annual Action Programme, Implementing Decision and Action Fiches (Part I,II), 2012

EU/PA Progress Reports

- European Commission SEC(2008) 400Implementation of the European Neighborhood Policy in 2007’Progress Report the occupied Palestinian territory, 3 April 2008

- European Commission SEC(2009) 519/2 Implementation of the European Neighborhood Policy in 2008’Progress Report the occupied Palestinian territory, 23 April 2009

- European Commission SEC(2010) 515 Implementation of the European Neighborhood Policy in 2009’Progress Report the occupied Palestinian territory, 12 May 2010

- European Commission SEC(2011) 644 Implementation of the European Neighborhood Policy in 2010’ Country Report the occupied Palestinian territory, 25 May 2011

- European Commission SWD(2012)120 final Implementation of the European Neighborhood Policy in 2011’ Progress Report the occupied Palestinian territory, 15 May 2012

- European Commission SWD(2013) 82 final Implementation of the European Neighborhood Policy in 2012’ Progress Report the occupied Palestinian territory, 20 March 2013

EU Reports and other documents

- European Commission, Our Neighbours: Panorama of Regional Programmes and Projects in the Mediterranean Countries, 02 July 2005

- European Commission,ENP Economic Review of EU Neighbour Countries - occasional papers 40, August 2008

- European Commission, Damage Assessment and Needs Identification in the Gaza Strip, Submitted by Eunida, march 2009

- European Commission, Sector Strategy Fiche – Security Updated, October 2010

- European Commission, Mapping Study of Civil Society Organisations in the occupied Palestinian territory - Final report, submitted by Soges,  18 April 2011

- European Commission, Press release, Palestinian people and local business at the heart of the Commission's new assistance package, 22 August 2011

- European Commission, EU support to the private sector, and trade in the oPT

- European Union press release EU and Germany provide EUR 40M to build new Waste Water Treatment Plant in Nablus (press release) 8 September 2013

- EU parliament - Delegation for relations with the Palestinian Legislative Council 9th Interparliamentary - December 2009

- EU parliament- Delegation for relations with the Palestinian Legislative Council Working group visit to OPT - April 11

- EU parliament- Delegation for relations with the Palestinian Legislative Council Working group visit to OPT-November 2011

- EU parliament- Delegation for relations with the Palestinian Legislative Council 9th Interparliamentary Decemebr 2010

- EU parliament- Delegation for relations with the Palestinian Legislative Council Working group visit to OPT-November 2012

- EU parliament- Delegation for relations with the Palestinian Legislative Council Working group visit to OPT-May 2013

- EuropeAid, External Assistance Management Report (EAMR), delegation West Bank and Gaza Strip 2012

- European Commission Single Support Framework (SSF) European Union Representative Office in Jerusalem (EUREP Office) 2014/2015 (progress draft October 2013)

- European Commission Local Strategy on Development Cooperation Occupied Palestinian Territories (oPt) (June 2013)

- European Commission PEGASE programmes of Direct Financial Support to the recurrent costs of the Palestinian Authority, August 2013

- European Commission Note to the attention of Mr Patrick Child, director EEAS; Mr Marcu Cornaro, Directror DEVCO/A, Shortage ofoperation himan resources in EUREP, February 2011

- European Commission , New Vision Management Consulting Report Of Evaluation of the EU EIDHR-CBSS Program, February 2011Final

- European Commission Country Human Rights Strategy and Priorities, Date of approval by HOMs: 1/6/2011, update 13/12/2012

- European Commission UNRWA - EU communications and visibility plan 2013

- European Commission Delegations’ Information and Communication Annual Report (2012) & forward planning (2013)

- European Court of Auditors, EU direct financial support to the PA, 2013

Palestinian authority Documents

- Palestinian National Authority, Annual Progress Report on Palestinian Reform (2004-2005), December 2005

- Palestinian National Authority, Palestinian Reform and Development Plan 2008-2010, 2008

- Palestinian National Authority, Palestine-Ending the Occupation, Establishing the State, August 2009

- Palestinian National Authority Ministry of Finance, Palestinian Economic Recovery -  Strategy in Transition, 7 June 2009

- Palestinian National Authority, National Development Plan 2011-2013: Establishing the State, Building our Future, April 2011

- Palestinian National Authority Ministry of National Economy, Governmental Documents Summary of Project Priorities 2013-2015, 13 February 2013

- Palestinian National Authority Ministry of National Economy, Private Sector Development & Trade Sector Working Group Meeting-PPT, 13 February 2013

- Palestinian National Authority Ministry of National Economy, Private Sector Development-Projects matrix, 13 February 2013

- Palestinian National Authority Ministry of National Economy, PSD Objectives-Projects power point

- Palestinian National Authority Ministry of Planning and Administrative Development, Governance Strategy Group - GSG and SWG Co-Chairs Meeting – Minutes, 22 October 2012

- Palestinian National Authority Ministry of Planning and Administrative Development, The National Strategy to Achieve the MDGs by 2015, June 2012

- Palestinian Water Authority, Palestinian Water Sector: Status Summary Report

- Palestinian Water Authority, Background Information and Water Resource Management Strategy, Ramallah, West Bank, 2004

- Palestinian Water Authority, National Water Strategy for Palestine
Toward Building a Palestinian State from Water Perspective, December 2012

- Palestinian Water Authority, Update and plans for the years 2010-2015 
Development and Reform – PPT, March 2013

- PCBS Economic Surveys and Roy 1999

- Governance Strategy Group, Bi-monthly report, April 2011

- Governance Strategy Group, Bi-monthly report, April 2012

- Governance Strategy Group, Bi-monthly report, June 2012

- Governance Strategy Group, Bi-monthly report, September 2012

- Governance Strategy Group, Bi-monthly report, November 2012

AHLC Documents

AHLC Reports

- AHLC-Palestinian National Authority Reforming Donor Coordination in the West Bank and Gaza, 14 December 2005

- AHLC-Palestinian National Authority, Building Palestine Achievements and Challenges-Report of the Palestinian National Authority to the AHLC, 13 April 2010

- AHLC-Palestinian National Authority Building Palestine Achievements and Challenges-Report of the Palestinian National Authority to the AHLC, 21 September 2010

- AHLC-Palestinian National Authority, Building Palestine Achievements and Challenges-Report of the Palestinian National Authority to the AHLC, 18 September 2011

- AHLC-Palestinian National Authority, Equitable Development: Moving Forward Despite the Occupation-The Palestinian National Authority’s Position Paper to the AHLC, 21 March 2012

- AHLC-Palestinian National Authority, Moving Beyond the Status Quo: Safeguarding the two - State Solution-The Palestinian National Authority’s Position Report to the AHLC, 23 September 2012

- AHLC-PNA - Ministry of Planning and Administrative Development, Building Palestine an update on PRDP implementation, 8 June 2009

- AHLC-World Bank, Palestinian economy and prospects for its recovery: economic Monitoring Report to the Ad Hoc Liaison Committee - Number 1, December 2005

- AHLC-World Bank, Two Years after London: Restarting Palestinian Economic Recovery Economic Monitoring Report to the Ad Hoc Liaison Committee, 24 September 2007

- AHLC-World Bank, Palestinian economic prospects: aid, access and reform-Economic Monitoring Report to the Ad Hoc Liaison Committee, 22 September 2008

- AHLC-World Bank, Implementing the Palestinian Reform and Development
Agenda Economic Monitoring Report to the Ad Hoc Liaison Committee, 2 May 2008

- AHLC-World Bank, A Palestinian State in Two Years: Institutions for Economic Revival, September 22, 2009

- AHLC-World Bank, Palestinian Economic Prospects: Gaza Recovery and West Bank Revival Economic Monitoring Report to the Ad Hoc Liaison Committee, 8 June 2009

- AHLC-World Bank, The Underpinnings of the Future Palestinian State:
Sustainable Growth and Institutions-Economic Monitoring Report to the Ad Hoc Liaison Committee, 21 September 2010

- AHLC-World Bank, Towards a Palestinian State: Reforms for Fiscal Strengthening -Economic Monitoring Report to the Ad Hoc Liaison Committee, 13 April 2010

- AHLC-World Bank, Building the Palestinian State: Sustaining Growth, Institutions, and Service Delivery - Economic Monitoring Report to the Ad Hoc Liaison Committee, 13 April 2011

- AHLC-World Bank, Sustaining achievements in Palestinian Institution-Building and economic growth-economic monitoring report to the Ad Hoc Liaison Committee, 28 September 2011

- AHLC-World Bank, Fiscal Crisis, Economic Prospects-The Imperative for Economic Cohesion in the Palestinian Territories-Economic Monitoring Report to the Ad Hoc Liaison Committee, 23  September 2012

- AHLC-World Bank, Stagnation or Revival? Palestinian Economic Prospects-Economic Monitoring Report to the Ad Hoc Liaison Committee, 21 March 2012

- AHLC – IMF, Macroeconomic Development and Outlook in the West Bank and Gaza, 14December 2005

- AHLC – IMF, Macroeconomic and Fiscal Developments in the West Bank and Gaza, 24 September 2007

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, First Review of Progress, 2 May 2008

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, Second Review of Progress, 22 September 2008

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, Third Review of Progress, 25 February 2009

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, Fourth Review of Progress, 22 September 2009

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, Fifth Review of Progress, 13 April 2010

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, Sixth Review of Progress, 21 September 2010

- AHLC – IMF, Macroeconomic and Fiscal Framework for the West Bank and Gaza, Seventh Review of Progress, 13 April 2011

- AHLC – IMF, Recent experience and prospects of the economy of the west bank and Gaza staff report prepared for the meeting of the Ad Hoc Liaison committee, 18 September 2011

- AHLC – IMF, Recent experience and prospects of the economy of the west bank and Gaza staff report prepared for the meeting of the Ad Hoc Liaison committee, 21 March 2012

- AHLC – IMF, Recent experience and prospects of the economy of the west bank and Gaza staff report prepared for the meeting of the Ad Hoc Liaison committee, 23 September 2012

- AHLC-UN, Humanitarian Situation and Humanitarian Access
Background Paper for the Ad-Hoc Liaison Committee, 24 September 2007

- AHLC-UN, UN Report Ad Hoc Liaison Committee Meeting New York, 22 September 2008

- AHLC-UN, Report of the Resident and Humanitarian Coordinator
Ad Hoc Liaison Committee Meeting, 8 June 2009

- AHLC-UN, Progress and challenges effective support to state-building in the occupied Palestinian territory, 13 April 2010

- AHLC-UN, Enabling Palestinian State-Building foundations for peace, 21 September 2010

- AHLC-UN, Palestinian State-Building at stake: preserving the two-state solution, 28 September 2010

- AHLC-UN, Palestinian State-Building a decisive period, 13 April 2011

- AHLC-UN, Palestinian State-Building: an achievement at risk, 18 September 2011

- AHLC – Government of Israel, Supporting Palestinian Capacity Building: Israel’s Efforts inSupporting the Palestinian Economy, Civil Affairs and Security Reforms, June 2009

- AHLC – Government of Israel, Measures Taken by Israel in Support of Developing the Palestinian Economy, the Socio-Economic Structure, and the Security Reforms, 13 April 2010

- AHLC – Office of the Quartet Representative - Report for the Meeting of the Ad Hoc Liaison Committee On OQR Action in Support of Palestinian Authority State-Building, 13 April 2011

- AHLC – Office of the Quartet Representative, Report for the Meeting of the Ad Hoc Liaison Committee Summary of OQR Development Agenda to Support
Palestinian Economic Sustainability and Institution-Building, 21 March 2012

- AHLC – Office of the Quartet Representative, Report for the Meeting of the Ad Hoc Liaison Committee, 19 March 2013

AHLC Statements

- AHLC – Benita Ferrero Waldner, Opening Statement of Benita Ferrero Waldner, Commissioner for External Relations and European Neighborhood Policy, 2 May 2008

- AHLC- Salam Fayyad, Statement by Dr. Salam Fayyad Prime Minister of the Palestinian National Authority, 22 September

- AHLC - Jonas Gahr Støre, Opening Address by Foreign Minister Jonas Gahr Støre, Chair of the Ad-hoc Liaison Committee, 22 September 2009

- AHLC - Jonas Gahr Støre, Opening Address by Foreign Minister Jonas Gahr Støre, 13 April 2011

- AHLC - Jonas Gahr Støre, Opening Address by Foreign Minister Jonas Gahr Støre, 21 March 2012

- AHLC - Catherine Ashton, Remarks by EU High Representative Catherine Ashton
after the donor coordination group for the Palestine Territories, 13 April 2011

AHLC Meeting Minutes

- AHLC Meeting Minutes 2007 sept

- AHLC Meeting Minutes 2008 May

- AHLC Meeting Minutes 2009 Sept

- AHLC Meeting Minutes 2010 April

- AHLC Meeting Minutes 2010 Sept

- AHLC Meeting Minutes 2011 April

- AHLC Meeting Minutes 2011 Sept

- AHLC Meeting Minutes 2012 March

- AHLC Meeting Minutes 2012 Sept

- AHLC Meeting Minutes 2013 March

UNRWA

- UNRWA,  UNRWA Medium Term Strategy 2010 – 2015, 2010

- UNRWA  MEDIUM TERM STRATEGY OUTLINE 2013; June 2013

- UNRWA Discussion Paper The EU and UNRWA in Strategic Partnership: Outlines of UNRWA’s Regional Role; 18 oct 2010

- UNRWA THE MANDATE OF UNRWA AT SIXTY; 10 May 2010

- UNRWA 2011 Harmonised UNRWA-Donor Report; 2011

- UNRWA 2012 Harmonised UNRWA-Donor Report; 2012

- UNRWA HE Efficiency Report Final ; April 2013

- UNRWA 2012 UNRWA Education Reform Report  - Final; April 2013

- UNRWA 2012 UNRWA Education Reform Report ; April 2013

- UNRWA About UNRWA; 2013

- UNRWA org chart 2013; 2013

- UNRWA Annual Report UNGA; 2008

- UNRWA Annual Report UNGA; 2009

- UNRWA Annual Report UNGA; 2010

- UNRWA Annual Report UNGA; 2011

- UNRWA Annual Report UNGA; 2012

- UNRWA UNRWA Management Response to OD Evaluation ; 29 February 2012

- UNRWA Outline of Protection Initiatives FINAL;

- UNRWA Protection Policy 2012; June 2012

- UNRWA Protection Standards Tool - English 071010; February 2010

- UNRWA Filed implementation plan Gaza Fiel Office GFO 2010-11;

- UNRWA Filed implementation plan Jordan Field Office JFO 2010-11;

- UNRWA Filed implementation plan Lebanon Field Office LFO 2010-11;

- UNRWA Filed implementation plan Syria Field Office SFO 2010-11;

- UNRWA Filed implementation plan West Bank Field Office WBFO 2010-11;

- UNRWA Filed implementation plan Gaza Fiel Office GFO 2012-13;

- UNRWA Headquarters Implementation Plan 2012-13;

- UNRWA Headquarters Implementation Plan Education 2010-11;

- UNRWA Headquarters Implementation Plan Health 2010-11;

- UNRWA Headquarters Implementation Plan Relief 2010-11;

- UNRWA Filed implementation plan Jordan Field Office JFO 2012-13;

- UNRWA Filed implementation plan Lebanon Field Office LFO 2012-13;

- UNRWA Filed implementation plan Syria Field Office SFO 2012-13;

- UNRWA Filed implementation plan West Bank Field Office WBFO 2012-13;

- UNRWA Explanatory Note Key privileges and immunities of UNRWA and related responsibilities and standard operating procedures of UNRWA and the Palestinian Authority

- UNRWA in the Near East and Lebanon, Exchange of notes constituting an over-all agreement (with annexed specific arrangement). Beirut, 26 November 1954

- UNRWA Report on UNRWA’s resource mobilization strategy 2012-2015 final 2012 findings/ April 2013

- UNRWA medium term strategy (mts) blueprint, November 2013

- UNRWA Joint Declaration  between the European Commission and UNRWA on European Union support to UNRWA in 2011-2013

- UNRWA Harmonised UNRWA-Donor Report 2011

- EC Note for the Attention of Mr. Christian Berger, Director, EEAS IV A, Subject UNRWA Development and upcoming Advisory Commision June 2012, March 2012

- Family Health Team data 2013

- 2011 TIMSS Results

Other Studies and Publications

- Al-Haq Defending Human Rights, Elisabeth Koek, Water Discriminatory Access and ‘Water-Apartheid’ in the OPT March 2013

- Al-Haq Submission to the EU on its 2013 ENP Progress Report on Israel, 14 October 2013

- AIDA - Failing to Make the Grade-may 2012

- Amnesty International, Troubled Waters – Palestinians Denied fair Access to Water. Israel-Occupied Palestinian Territories, London: Amnesty International, 2009.

- ARIJ The Applied research Institute, Status of The Environment in the occupied Palestinian Territory, A Human Rights – Based approach, (ARIJ), 2011.

- A-Shabaka, Palestinian Civil Society: What went wrong? April 2013

- CEC Central Elections Commission – Strategic Plan - Palestine 2014-2016

- CEPR Council for European Palestinian Relations– Memo- Israeli Water Exploitation in the Occupied West Bank – 2012

- CEPR Council for European Palestinian Relations – Memo -European Union Policy Towards the Middle East Peace Process – 2012

- CEPR - Memo: The Impact of the Israeli Blockade on the Environmental Situation in Gaza strip - Dr. Amal Sarsour  - 2013

- CESR -Mair, Lucky, Anjali Kamat and Julian Liu: Thirsting for Justice: Israeli Violations of the Human Right to Water in the Occupied Palestinian Territories. In A Report to the 30thSession of the United Nations Committee Economic, Social and Cultural Rights, New York, 2003

- CIDSE - The EU's Aid to the OPT-CIDSE-Dec 2008

- CIDSE - The EU’s aid to the occupied Palestinian territory How to improve coherence and effectiveness in line with international law? Nov 2008

- Chaillot Papers, Esra Bulut Aymat, European Involvement in the Arab-Israeli Conflict- Dec 2008

- CMWU Coastal Municipalities for Water Utility, Annual Report on Water Status in the Gaza Strip - Summary about Water and Wastewater Situation in Gaza Strip, 2012

- COWI, Independent Review of the Local Aid Coordination Secretariat in the Palestinian Territory, 23th November 2012

- Doing Business, Doing Business in the Arab World, 2011

- Economic and Social Council UN, Trends and progress in international development cooperation Report of the Secretary-General, 23 May 2008

- EGMONT, Palestinian Unity Government: EU Should Find Ways to Cooperate-Security Policy Brief-May 2011

- European Commission - Görlach, B., Möller-Gulland, J., Bar-On, H. and Atrash, Analysis for European Neighborhood Policy (ENP) Countries and the Russian Federation of social and economic benefits of enhanced environmental protection – Occupied Palestinian territory Country Report, 2011

- FAO, WFP, UNRWA, PCBS - Socio-Economic and Food Security Survey West Bank and Gaza Strip, occupied Palestinian territory 2011, May 2012

- Gianniou, Maria,The European Union's involvement in the Israeli-Palestinian conflict: an active paradigm of European foreign policy? Paris III Sorbonne Nouvelle European Consortium for Political Research, September 2006

- Gvirtzman Haim - The Begin-Sadat Center for Strategic Studies, Israel,The Israeli-Palestinian Water Conflict: An Israeli Perspective, Mideast Security and Policy Studies No. 94,January 2012

- Heinrich Boll Foundation, Assaf et al. (2004) Water as a Human Right: The understanding of water in Arab countries of the Middle East – A four countries analysis, Ramallah, Palestine

- IMF, Staff Report: Recent Experience and Prospects of the Economy of the West Bank and Gaza. March 19, 2013

- Laurence Bernard Journaliste Le monde diplomatique Protestations sans conviction contre l’occupation Faillite de l’Union européenne en Palestine, Nov 2013

- Lunat, Ziyaad (2010): Charting the Rapids: The Water and Sanitation Sector under Occupation, in Geographies of Aid in Palestine International Conference, Birzeit University, Ramallah.

- Messerschmid, Clemens, What price cooperation? Hydro-hegemony in shared Israeli/Palestinian groundwater resources. Conference paper, Amman, 2007

- Messerschmid, Clemens, Bitter Water – Reality and Illusions in Water Policy for Gaza, in Gaza-Palestine – Out of the Margins International Conference, Birzeit University, Ramallah, 2010

- Norwegian Government, International donors call for Palestinian Authority observer status in the WTO, Press release, April 2011

- OCHA, 2012e Five Years of Blockade: The Humanitarian Situation in the Gaza Strip, June 2012.

- ODI, Cash Transfers Pal Briefing

- ODI, Cash Transfers Pal ExecSum

- ODI, Cash Transfers Pal Full Report

- ODI, Cash Transfers Synthesis Briefing

- ODI, Cash Transfers Synthesis Full Report

- OECD, 2011 Report on International Engagement in Fragile States:
Can’t we do better? , 2011

- OHCHR EC Area C and Palestinian State Building Final Report July 2011

- Scarpa, David, Hydropolitics in recent Israeli-Palestinian relations, Water and Soil Environmental Research Unit, Palestinian National Authority, 2004

- The Carter Centre, The Carter Center Electoral Study Mission Urges Parties to Pursue Political Reconciliation, 21 October 2012

- Trading Away Peace: How Europe helps sustain illegal Israeli settlements, October 2012

- VISSER, YOCHANAN Israel How water became a weapon in Arab-Israeli conflict By - 03/2013

- Water for Life, Water, Sanitation and Hygiene Monitoring Program (WaSH MP) – The dilemma of development under occupation : the obstacles to achieving the MDG and water rights in the occupied Palestinian territory - WASH Monitoring program - Palestinian Hydrology Group (PHG), 2006

- World Bank, Developing the Occupied Territories” 1993,vol.1

- World Bank, Report No. 47657-GZ-West Bank and Gaza – Assessment of restrictions on Palestinian water sector development - Sector Note - April 2009

- World Bank, Development Report 2009

- World Bank, Reforming Prudently Under Pressure:  Health Financing Reform and the Rationalization of Public Sector Health Expenditures. August 2009.

- World Bank, West Bank and Gaza coping with conflict? Poverty and inclusion in the West Bank and Gaza, 29 July 2011

- World Bank, Coping with Conflict: Inclusion in the West Bank and Gaza, October 2011

- World Bank, World Bank: Concerted action needed by all parties for the PA to meet state-building goals, Press release, 2010

- World Bank, Palestinian Institutions Performing; Sustainable Growth Still Absent, 7 April 2011

- World Bank, International donors call for Palestinian Authority observer status in the WTO, Press release, 13 April 2011

- World Bank, Checkpoints and Barriers: Searching for Livelihoods in the West Bank and Gaza Gender Dimensions of Economic Collapse February 2010

- World Bank, Interim Strategy Note for the West bank and Gaza, 2012-2014, 13 March 2012

- University of Warwick, Stillborn State, The European Union’s Role in the Palestinian Territory after the Oslo Accords: building-Dimitris Bouris

- 1st Governance Report to the GSG Co-Chairs March - April 2011

- 7th Governance Report to the GSG Co-Chairs March - April 2012

- 8th Governance Report to the GSG Co-Chairs May – June 2012

- 9th Governance Report to the GSG Co-Chairs July - September 2012

- 10th Governance Report to the GSG Co-Chairs October - November 2012

- Corruption Report 2011 Absence of Accountability

Evaluations

- European Commission - HTSPE, Interim Evaluation of the PEGASE - Autumn 2009

- European Commission - Business and Strategies Europe, External Evaluation of PEGASE 2008-2011 For West Bank and Gaza, 2012

- European Commission - Soges, Evaluation of the EU Partnership for Peace Program, April 2010

- European Commission - Associates in Building Capacity (ABC) Consulting, Evaluation of the EU Program to support the delivery of community services in East Jerusalem, 2012

- European Commission – IBF - Evaluation Non-state actors program in the oPT 2007-2011 final report - July 2013

- European Commission - Channel research, Evaluation of DG ECHO’s Interventions in the occupied Palestinian Territory and Lebanon, March 2012

- European Commission – ADE, Thematic Evaluation of European Commission Support to Conflict Prevention and Peace-building, Final Report, October 2011

- WFP, Operation Evaluation - oPT - PRRO 2007-2009

- DFID – TripleLine Facility for New Market Development (FNMD) to Strengthen the Private Sector in the Occupied Palestinian Territories

- UNRWA – Transtec Mid-term evaluation 7 January 2013

- UNRWA – Transtec Evaluation of UNRWAs Organizational Development 24 October 2011

- European Commission Impact Evaluation of the PEGASE DFS “Private Sector Reconstruction in Gaza (PSRG) Programme”  Final Report - September 2013

- Ministry of Foreign Affairs of Japan, Mitsubishi Research Institute, Inc. Evaluation of Assistance to the Palestinian Territories, February 2012

Websites

Amnesty International www.amnesty.org

CEPRCouncil for European Palestinian Relationswww.thecepr.org

CMWU Costal Municipalities Water Utility Official Website www.cmwu.ps/en/index.php

ECHO http://ec.europa.eu/echo/aid/stories/middle_east23_en.htm

ENPI Reference documentshttp://ec.europa.eu/world/enp/documents_en.htm

EU Delegation in OPThttp://eeas.europa.eu/delegations/westbank/index_en.htm

EC - External ActionsOPThttp://eeas.europa.eu/occupied_palestinian_territory/index_en.htm

EUROPEAIDhttp://ec.europa.eu/europeaid/where/neighbourhood/country-cooperation/occupied_palestinian_territory/occupied-palestinian-territory_en.htm

ENPI Southhttp://www.enpi-info.eu/indexmed.php

FSTPhttp://ec.europa.eu/europeaid/how/finance/dci/food_en.htm

Local Development Forumhttp://www.lacs.ps/DocumentsSearch.aspx

OCHA Office for the Coordination of Humanitarian Affairswww.ochaopt.org

Reports of the Joint Evaluation Unit of the EChttp://ec.europa.eu/europeaid/how/evaluation/evaluation_reports/index_en.htm

Strategic Foresighthttp://www.strategicforesight.com/middleeast_water_security.htm

The applied research Institutehttp://www.arij.org/

UNRWAhttp://www.unrwa.org/

WHO/UNICEF (2010) http://www.unicef.org/statistics/index_24302.html

# AnneX 3: List of People INTERVIEWED

LIST OF PEOPLE MET FOR INCEPTION PHASE

| Name | Position |
| --- | --- |
| Brussels / Palestine March 2013: Inception Mission |  |
| Dr. Mohamed Shtayia, | Director of PECDR |
| Dr. Samir Abdulla, | Director of MAS institute for economic research and policies |
| Dr. Mohamed Mustafa, | Head of board and director of Palestinian investment fund, PIF |
| Dr. Nabil Qesis, | Ministry of finance. |
| Mr. Samir Huleila, | Director PADICO |
| Mr. Nabil Kassis | Former Minister of Finance of Palestine |
| Mr. Christian Berger | EEAS Director |
| Dr. Mohammed Shtayyeh | Minister Palestinian Economic Council for Development and Reconstruction (PECDAR) and PLO |
| Dr. Mohammed Mustafa | Chief Executive Officer of the Palestine Investment Fund (PIF) |
| Dr. Firas Raad | OQR, Head of Mission and seconded by the World Bank |

list of people met for desk phase

| Name | Position |  |  | Key topics |
| --- | --- | --- | --- | --- |
| Washington October 2013 |  |  |  |  |
| Nabila Assaf, |  | Manager, Private Sector Development, MENA, World Bank, and previously resident in Jerusalem for private sector development and donor coordination. (Washington 01.10.2013) | Private Sector, Donor Coordination |  |
| William Corcoran |  | CEO and Paul Butler, Director Palestine, resident Jerusalem, ANERA (Washington 06.10.2013) | Modalities for implementation of projects in West Bank, Jerusalem and especially Gaza |  |
| Gaith al-Omari |  | Executive Director American Task Force on Palestine, former member of PA negotiations unit (Washington 08.10.2013) | Effectiveness of EU Cooperation in advancing two-State solution and partnership with US |  |
| Mariam Sherman, |  | Outgoing Country Director for Palestine, World Bank (Washington 08.10.2013) | Coordination, partnerships, sector strategies, overall economic situation, progress in two-State solution. |  |
| Geoffrey Aronson, |  | Conflicts Forum (Washington 08.10.2013) | Aid Effectiveness in Palestine |  |
| Mohammad Shtayyeh, |  | Minister, Negotiating team and President PECDAR (Washington 11.10.2013) | Aid Effectiveness in pursuit of political goals |  |
| Salam Fayyad, |  | former Prime Minister Palestine. (Washington 17.10.2013) | Overall PA-EU relationship 2008-2013 |  |
| Steen Jorgensen, |  | Director, Human Development, MENA, World Bank and incoming Country Director, Palestine (Washington 17.10.2013 | Human Development and Social Protection Programs for Palestine |  |
| Omar Mehyar, |  | Palestine Desk, Islamic Development Bank,. (by telephone 10.11.2013) | Palestine program and cooperation with regional actors |  |
| El Mansour Feten, |  | Director, Trust Funds, Islamic Development Bank, (by telephone 10.11.2013) | Palestine program and cooperation with regional actors |  |
| Jihad alWazir, |  | Governor Palestine Monetary Authority (October 2013) | Economic Sector |  |
| John Nasir, |  | Lead Private Sector Development Specialist Country Economist for World Bank in West Bank and Gaza | Private Sector Development |  |
| Bruxelles November 2013: Desk Phase |  |  |  |  |
| Laura Fallovita Annemie Cump |  | DEVCO, F2 | - Strategy preparation (Joint Committees, Action Plan, Local Strategy) - Programming - Interventions follow-up - Interactions with EEAS - Actors coordination - Review of key documents - Discussion of assumptions and external factors Discussion on scope of evaluation |  |
| Matthias Bruchard |  | UNRWA | - Overview of UNRWA activities in the 5 geographical fields - Main goals and 4 key strategic sectors - Planning (HIP and FIPs) - Organizational Development - Medium-term Strategy - Issues and challenges - Goals - Relevance to EU goals Partnership with EU |  |
| Christian Berger |  | EEAS | - Overview of Cooperation from 1995-present - Impact of Lisbon Treaty changes on cooperation - Relationship of EEAS to DEVCO in programming - Overall Action Plan relationships with PA - Constraints to Implementation and overall EU objectives - Issues of trade agreements, certificates of origin and guidelines Prospects going forward |  |
| Christian Leffler |  | EEAS | - External Action for Palestine – history - Overview of period 2006-2008 - Overview of early political dialogue – Action Plan 2005 and reporting - Mandates following Lisbon Treaty - Fragile State assessment - Setting up of PEGASE - Benchmarks for PEGASE Issue of EU trade agreements |  |
| Karolina Hansson |  | DEVCO | - Human Rights in DEVCO - EIDHR instrument - Policies for HR - Political dialogue for HR - Platforms with Civil Society Resources and capacities for follow-up of HR issues |  |
| Emer Costello |  | EU Parliament and Legislative Council for Palestine | - Political follow-up of situation in Palestine - EU political role: actual and potential - Political priorities - Human Rights issues - Elections in Palestine Coordination Council and EEAS |  |
| Christian Garrigues |  | EU Parliament and Legislative Council for Palestine | - EU political role: actual and potential - Political priorities - Human Rights issues - Elections in Palestine Coordination Council and EEAS |  |
| Brigitte Herremans |  | Broederlijk Delen | - Civil Society and EU cooperation - Assumptions for EU cooperation - Analysis of obstacles to achieving goals - Respect of humanitarian law and EU engagement - Policy making: tangible and intangible factors - Gaza - Area C - Need for engagement and socialization with Israel - Role and challenges for Civil Society - Relevance and effectiveness of aid - Civil Society contacts in Palestine Civil Society and EU policies |  |
| Pavel Bouda |  | Cabinet Commissioner Fule | - Coordination EU services - Lisbon Treaty and collegiality - Political perspective of EU for Palestine and Middle East - Stable equilibrium - Political circumstances and exit strategy - Dialogue with Israel - Leverage with PA and Israel - Guidelines - Application of Humanitarian Laws - Instruments for making cooperation more effective - Role of High Representative Scope and importance of the Evaluation |  |
| Raffaella Iodice |  | DEVCO | - Context for cooperation with Palestine and evolution of the situation - Paradigm shift in cooperation - Coordination DEVCO – EEAS - Quartet and AHLC - Outcomes of cooperation efforts - Privileged channel of communication with PA - Instruments of cooperation - Limitation of cooperation efforts with PA (example of Judiciary) - Accountability - Coordination with Member States - Coordination with Gulf States and Islamic Bank Benchmarks for cooperation |  |
| Deborah Casalin |  | CIDSE | - Civil Society action for EU policies - EU Peace process support - Relations with Israel - Association Agreement - Guidelines and labelling - December 2012 Council Conclusions and agreements not to recognize, aid or assist violations to international law - Challenges of different political perspectives of MS |  |
| Isabelle Martins |  | EU Advocacy Intern OXFAM | - Positive outcomes of EU cooperation - Dichotomy of political track and development track - Civil Society action for EU policies - Demolition of EU projects: lack of coordinated policies and mechanisms - Investments in Area C - Guidelines for a) funding, b) labeling and c) business - Call from MS to HR for EU guidelines - Different approaches of MS to middle east politics and how this affects cooperation efforts - Difficulties to enforce existing legislation |  |

Annex 4: List of Stakeholders for field mission

| INSTITUTION | NAME |  | SURNAME | FUNCTION |
| --- | --- | --- | --- | --- |
| EUREP |  |  |  |  |
| EUREP | OLGA | BAUS GIBERT |  | Head of Social Affairs, Human Rights and Civil Society |
| EEAS | Christian | Berger |  | Director North Africa, Middle East, Arabian Peninsula, Iran and Iraq |
| EUREP | Anna Maria | Bonnici |  | Co-Desk oPT Middle East Division MEPP Israel |
| EUREP | Sophie | Collette |  | Programme Manager OPS2 - Water and Sanitation |
| EUREP | JOSEP | DESQUENS |  | Project manager Direct Financial Support |
| EUREP | Paolo | Curradi |  | Head of Section OPS2- Infrastructure,Water, Energy, Environment and Agriculture |
| EC | Esmèe | De Jong |  | Head of office |
| EUREP | MARIEM | EL HAROUCHI |  | Project Manager Direct Financial Support |
| EuropeAid | Michael | Docherty |  | Team Leader Geographical Coordination Neighborhood South |
| EUREP | Bozkurt | Eralp |  | Head of Finance, Contracts and Audit Section |
| EUREP | Guillaume | Fine |  | Head of Section OPS2- Infrastructure,Water, Energy, Environment, Agriculture and UNRWA |
| EUREP | JOHN | GATT-RUTTER |  | HoM |
| EUREP | DAVID | GEER |  | Deputy EUD |
| EUREP | JUDITH | JOHANNES |  | Education, Health and Cultural Officer |
| EUREP | GERT | KEMPMAN |  | Head of mission |
| EEAS | Christian | Leffler |  | Managing Director Americas |
| EUREP | Michael | Mansur |  | Task manager |
| EUREP | Bernard | Philippe |  | Political Officer |
| EUREP | SERGIO | PICCOLO |  | Head of Cooperation |
| EUREP | CAROLE | RIGAUD |  | Economic and financial cooperation |
| EUREP | Abdel Karim | Yakobi |  | Programme Manager OPS2 - Water and Sanitation |
| EUREP | ANTONIA | ZEFEIRI |  | press and information manager |
| Donors Member States |  |  |  |  |
| Cooperazione Italiana alla sviluppo (Italy) | EMANUELA | BENINI |  | Deputy Director |
| French Consulate General in Jerusalem | SEBASTIEN | BIDAUD |  | Consul adjoint |
| Germany GIZ | Volker | Bode |  | Deputy Country Director |
| Germany GIZ | Barbara | Wolf |  | Head of German Representative Office |
| Germany GIZ | Elke | Bullesbach |  | First secretary |
| French Consulate General in Jerusalem | JULIEN | BUISSART |  | Economic and commercial counselor |
| France AFD | HERVE | CONAN |  | DIRECTEUR |
| Belgian Cooperation (CTB) | Willy | Demeyer |  | Resident Representative |
| KfW | Thomas | Eisenbach |  | Director – KfW Development Bank |
| French Consulate General in Jerusalem | AUGUSTIN | FAVEREAU |  | Head of cooperation |
| Belgian Consulate | Alfred | Fickers |  | Consul – Cooperation |
| UK/DFID | JONATHAN | HARGREAVES |  | Head, DFID Jerusalem Palestinian |
| France AFD | Bruno | Juvet |  | Head of Cooperation |
| France AFD | Camille | KERDANET |  | Project Officer – Water and Sanitation Sector AFD Jerusalem Office |
| Spain AECID | Eva Suarez | leonardo |  | Senior Programme Manager Civil Society and Peace building |
| French Consulate General in Jerusalem | HEVRE | MAGRO |  | Consul general de France à Jerusalem |
| Slovak Republic- National Council | IVAN | MIKLOS |  | Member of Parliament |
| ITALY/COOPERAZIONE ITALIANA ALLO SVILUPPO | Vincenzo | Rocalbuto |  | Head |
| Germany GIZ | Rudolf | Rogg |  | Country director |
| German Cooperation (GIZ) | Dirk | Schaefer |  | Head of Programme – Water and Solid Waste Management Programme |
| Sweden/Consulate general | JOHANNA | Strömquist |  | Head of Political section |
| Spain AECID | Jesus | Tome |  | Senior Programme Manager griculture and economic development |
| Sweden/Consulate general | Frederik | westerholm |  | Consul |
| Other Donors |  |  |  |  |
| Switzerland/Cooperation office in Gaza | SEGOLENE |  | ADAM |  |
| USA/ Department of state | STEVEN |  | BITNER | Deputy economic chief |
| USA/ Department of state | JEFFREY |  | ZAISER | Chief Economic section |
| Switzerland | VERONIQUE |  | HULMANN | Director of cooperation |
| USA/MIDDLE EAST POLICY COUNCIL | THOMAS R. |  | MATTAIR | Executive director |
| USA/AMERICAN TASK FORCE PALESTINE | GAITH AL- |  | OMARI | Executive director |
| Palestinian Authority |  |  |  |  |
| MIN OF NAT. ECONOMY | HASAN |  | ABDEL | MINISTERS’ ADVISOR |
| MIN OF SOCIAL AFFAIRS | DAUOD |  | AL-DEEK | ASSISTANT DEPUTY MINISTER |
| MIN OF AGR. | WALEED |  | ASSAF | MINISTER OF AGRICULTURE |
| AL-HAQ | SHAWAN |  | JABARIN | Director of Al-Haq |
| JUDICIAL | THURAYA |  | JUDI AL WAZIR | head of PPMU |
| MIN OF AGR. | ABDULLAH Q. |  | LAHLOUH | DEP MINISTER |
| PALESTINE INVESTMENT FUND | MOHAMMAD |  | MUSTAFA | Chairman and CEO |
| STATE OF PALESTINE | MOHAMMAD |  | MUSTAFA | Deputy Prime minister for economic Affairs |
| CEC | Carole |  | Rigaud, | SSF, political dialogueù |
| PALESTINIAN ECONOMIC COUNCIL FOR DEV | MOHAMMED |  | SHATAYYEH | Minister |
| MIN OF NAT ECO | MANAL F. |  | SHKOKANI | Chemical Engineer |
| MIN OF NAT ECO | ZIAD |  | TOAME | Director general- Industry, Trade, Consumer Services |
| Palestinian Civil Society (see also below tables of list of NGOs) |  |  |  |  |
| MAS-PALESTINE ECONOMIC POLICY RESEARCH INSTITUTE | SAMIR |  | ABDULLAH | Director General |
| ANERA | PAUL |  | BUTLER | Country director, WB & Gaza strip |
| PALESTINIAN MEDICAL RELIEF SOCIETY | MUSTAFA |  | BARGHOUTHI | MD.M.Sc. President |
| BHC LLC | AHMED |  | DAWOOD | Iraq attorney and managing partner |
| OQR | HENDRIK |  | DENKER | Infrastructure adviser |
| FUTURE FOR PALESTINE | SALAM |  | FAYYAD | Chairman |
| PADICO HOLDING | SAMIR O. |  | HULILEH | Chief executive officer |
| HUSSEINI & HUSSEINI | HIBA I. |  | HUSSEINI | Attorney and counselors at law |
| PADICO | Munib |  | Masri, | Chairman, |
| OQR | FERAS |  | MILHELM | Rule of law adviser |
| OQR | NASSIM |  | NOUR | Private sector development adviser |
| PALESTINIAN NGO NETWORK | DUA’A |  | QURIE | Executive Director |
| ARIJ | RAED E. ABED |  | RABBO | Public Relation Director |
| ARIJ | Jad |  | Isaac | Director General |
| ARIJ | Jane |  | Hilal | Head of Water and Environment Department |
| PASSIA | MAHDI F. ABDUL |  | HADI | Chairman |
| PNGO | Hiba Husseini |  | Al-Mustaqbal | Head |
| OQR | BADER |  | ROCK | Legal and policy adviser |
| AMAN | AZMI |  | SHUAIBI | Anti corruption Commissioner |
| PALTRADE | HANAN |  | TAHA-RAYYAN | Chief executive officer |
| OQR | TIM |  | WILLIAMS | Movement and access adviser |
| PALESTINIAN FED. OF INDUSTRIES | ODEH AL- |  | ZAGHMOURI | Secretary General |
| Multilateral Cooperation |  |  |  |  |
| CENTRE DE MARSEILLE POUR L’INTEGRATION EN MEDITERRANEE | MATS |  | KARLSSON | Directeur |
| FAO | NADEJDA |  | DAGASH | Agriculture Sector Coordinator |
| FAO | CYRIL |  | FERRAND | Head of office |
| IMF | UDO |  | KOCK | Resident representative for West bank and Gaza |
| ISLAMIC DEV. BANK | BASHIR OMAR MOHAMMED |  | FADLALLA | Director Islamic solidarity Fund For Development |
| UNDP | WALID |  | HASNA | Head of Engineering and Infrastructure |
| UNDP | RIMA ABUMIDDAIN |  | BARGHOTHI | Team leader - Environment and natural resources 5UNDP/PAPP |
| UNICEF | BILAS |  | DONGOL | Chief, WASH |
| UNICEF | KUMIKO |  | IMAI | Chief Social Policy, Occupied Palestinian Territory |
| UNICEF | MOHANLAL |  | PEIRIS | WASH Specialist |
| UNICEF | CAROL |  | AWAD | Officer, WASH |
| UNRWA | Michelle |  | Labeeu | macro-economic support, PEGASE, |
| UNRWA | MEG |  | AUDETTE | Field Programme Support Officer |
| UNRWA | Esther kuish- |  | Laroche | Chief Donor Relations division |
| UNRWA | Anna Trolle- |  | Lindgren | Senior External Relations and projects officers donor relations division |
| UNRWA | Salvatore |  | Lombardo | Director |
| UNRWA | Scott |  | Anderson | Deputy Director of UNRWA operations - Gaza |
| UNRWA | Virginia Villar |  | Arribas | Liason Officer |
| UNRWA | Matthias H.T. |  | Burchard | Director UNRWA |
| UNRWA | David |  | Hutton | Deputy Director of URWA Operations (Programme) |
| UNRWA | Felipe |  | Sanchez | Director of URWA Operations West Bank |
| WB | MARIAM |  | SHERMAN | Country Director West Bank and Gaza |
| WB | DINA |  | ABU-GHAIDA | Senior economist Human Development DPT Middle east and North africa |
| WB | PIERRE |  | MASALLI | Senior Public Administration |
| WB | JOHN |  | NASIR | Economic adviser |
| WB | OHRAN |  | NIKSIC | Senior Country Economist |
| WB | NABILA |  | ASSAF | Manager, private sector |
| WB | NUR NASSER |  | EDDIN | Economist |
| WB | STEEN |  | JORGANSEN | Country DIrector West Bank and Gaza |
| WB | John |  | Nash | Senior Country Economist |
| WB | Yasser |  | el Gammal | Social Protection Sector Manager |
| WB | Ernesto, |  | Cuadra | Lead Education Specialist |
| WB | Enis, |  | Baris | Manager, Health Sector |
| WB | Ranjana |  | Mukherjee, | Country Coordinator |
| WHO | MAHMOUD |  | DAHER | Acting head of Office |
| Others |  |  |  |  |
| Water Resources Directorate | Ekrima | Abadi |  | Director |
| AL-JAZEERA-NETWORK | JAMAL | ABDULLAH |  | Researcher |
| IRD (INGO) | Ihab | Barghothi |  | Country Director |
| QUATAR/Quatar charity | JUDEH | JAMAL |  | Acting country Director- Palestine office |
| USA/The MEGA COMPANY | CHANG S. | OH |  | Managing director |
| USA/DLA PIPER | GEORGE R. | SALEM |  | Strategic advisor to DLA Piper |
| USA/The MEGA COMPANY | SALAH | TURKMANI |  | Owner of MEGA COMPANY |

list of ngos met during the field visit

International NGOs

| Name of INGO | Contact Name | Email | Phone | Sector |
| --- | --- | --- | --- | --- |
| Action Against Hunger (ACF) | Eric Fort - Head of Mission | efort@pt.acfspain.org | 02-5835739 | Humanitarian |
| American Friends Service Committee (Quakers) (AFSC) | Patricia Sellick - Regional Director for the Middle East | psellick@afsc.org | +972 (0) 2 6288070 | Society, Youth, Peace and Development |
| CARE International (CARE) | David White - Country Director | info@carewbg.org | +972 2 583 4069 ¦+972 2 295 4949 | Relief Agency |
| Catholic Relief Service (CRS) | Matthew McGarry - Country Representative | Matthew.mcgarry@crs.org | +972.2.656.9240/1 | International Humanitarian Agency |
| CHF International (CHF) | Lana Abu Hijleh - Country Director | labuhijleh@chf-pal.org | +972.(0)2.2429522 | Development and Humanitarian Aid Organization |
| Handicap International (HI) | David Ligneau - Head of Mission | dligneau@hi-me.org | +972 (0)2 626 169 | Independent International Aid Organization working in situations of poverty and exclusion, conflict and disaster |
| -Heinrich Boell Foundation- Ramallah office. (HBF) | Rene Wildangel | Rene.Wildangel@ps.boell.org | +972 2 296 11 | Equality and civil society, democracy, health, environment |
| Islamic Relief (IR) | Muneeb Abu Ghazaleh - Country Director | muneeb@irpal.ps | 02 297 4643 ¦082837889 | A UK-registered charity which works internationally in emergency relief, development projects |
| Japan International Volunteer Center (JVC) | Naomi Fukuda – Representative, Jerusalem office | kaneko@ngo-jvc.net | 02 628 7167 | Peace, Community development, Emergency Relief |
| Medecins du Monde - France (MDM France) | Fahmi Masri- Admin | Genco.palestine@medecinsdumonde.net | 02 6261830 ¦02 6261832 | Healthcare |
| Mercy Corps (MC) | tu Willcuts - Mission Director | swillcuts@field.mercycorps.org | 02 628 4563 | An International Development Organization that helps people around the world survive and thrive after conflict, crisis and natural disaster |
| Norwegian Refugee Council (NRC) | Neil Jebb - Country Director | neil.jebb@nrc.no |  | Humanitarian non-governmental organization which provides assistance, protection and durable solutions to refugees and internally displaced persons worldwide |
| Oxfam Great Britain (Oxfam GB) | Tim Holmes - Country Director | THolmes@oxfam.org.uk jerusalem@oxfam.org.uk | +972 2 6566234/5 | Aid and Development Charity |
| Oxfam Italia (OIT) | Peter Laban - Associate Country Director | jerusalem@oxfamitalia.org | +972(0) 2 6727805 | Aid and Development |
| Save the Children - International (SCI) | Alex Schein - Country Director | alex.schein@savethechildren.org | Jerusalem office: 02-583 8593 / 4 ¦Ramallah office: 02-2973631 | Independent organization for children |
| The Swedish Cooperative Centre (SCC) | Mohammed Khaled | Mohammed.Khaled@utangranser.se | 02 2413950 ¦00970597840480 | Poverty, Development, Cooperation |
| United Nations Association International Service (UNAIS) | KhaledHusseini - Country Director | k.husseini@unais.org | 02-5823941 info@unais.org | Women, Disabled people, Children and Young people |
| War Child Holland (WCH) | Javier Pérez Salmerón - Israel-OPT Representative | Javier.Salmeron@warchild.nl | 025853952 | Children and Young people |

NGOs Ramallah

| NGOs | Contact Name | Phone | Email | Sector |
| --- | --- | --- | --- | --- |
| Al-Haq Institute | Sha'wan Jabareen | 02-2956421 | haq@alhaq.org admin@alhaq.org | International Human Rights and the Rule of Law |
| Arab agronomists association | Saad dagher | 02-2413051/2 | info@aaa-arc.org | Agriculture |
| Arab Center for Agricultural Development (ACAD)/ Ramallah | Mr Samir Barghouthi | 02-2409650 | acad@palnet.com | Agriculture |
| Arab Women Union Society | O’houd Yaeesh | 09-2389104 | ohoudyq@yahoo.com | Women |
| BADIL Resource Center for Palestinian Residency & Refugee Rights | Ingrid jaradat gassner | 02-2777086 | info@badil.org | Democracy and Human Rights/ Refugees |
| Baladna cultural center al-bireh | Farid Morah | 02-2958435 | info@baldna.org | Culture |
| Bisan Center for Research and Development | Naim Abu Teir | 02-2407837/8/9 | bisanrd@palnet.com www.bisan.org | Research and Environment |
| Care for Children with Special Needs Society | Sarab Malhas | 09-2386097 | info@ccsns.org | Children |
| Democracy & Workers’ Rights Center | Hasan barghouthi | 02-2952608 | info@dwrc.org | Democracy and Human Rights |
| Freedom Forum Palestine | Ashraf Okkeh | 0599-785 803 | ashrafokeh@yahoo.com | Thought and Research; Freedom and Youth |
| Health Work Committees‫ ‬(HWC)‬ | Shadah Odeh | 02-2407518; 02-2427517 ; 02-2957047 | uhwc@palnet.com | Health Services through a developmental community (Women and Children) |
| Khalil Sakakini Cultural Center | Faten Farrahat | 02-2987374/5 | sakakini@sakakini.org | Culture |
| Land Research Center | Jamal Talab | 02-2217239 | LRC@palnet.com www.lrcj.org | Research and Environment |
| MA’AN Development Center | Sami Khader | 02-2954451; 02-2986698 ; 02-2986796 | maanc@palnet.com www.maan-ctr.org | Society and Development Sector |
| MUSAWA - The Palestinian Center for the Independence of Judiciary and the Legal Profession | Ibrahim al-barghouthi | 02-2424870 | musawa@musawa.ps | Law |
| Palestinian Agricultural Relief Committees | Mr.khalil shiha | 02-2962840 | monjed@pal-arc.org | Agriculture |
| Palestinian Business women’s’ Association ASALA | Reem Aboshi | 02-2400532 ; 02-2402433 | asala@palnet.com | Women Empowerment/ Microcredit |
| Palestinian Hydrology Group for water and environmental resources development (PHG) | Abdel-RahmanTamimi | +9702 2966315-6 ; 0599-204690 | a.tamimi@phg.org info@phg.org | Water and Environmental Resources Development |
| Palestinian Medical Relief Society (PMRS) | Heider abu ghoash | 02-2969970 | pmrs@pmrs.ps | Health |
| Palestinian Youth Union | Moharam Barghouthi | 2981313 | Pyu2002@hotmail.com | Youth |
| Ramallah Center for Human Rights Studies | Iyad Barghouthi | 2413001 | rchrs@rchrs.org Ramallah.center@gmail.com | Democracy and Human Rights |
| Sawa- All the Women Together Today and Tomorrow | Uhaila Shomar | 5324122 | Info@sawa.ps | Women |
| Tamer Institute for Community Education | Renad Qubbaj | 02-2986121/2 | tamer@palnet.com | Education |
| Union of Health Care Committees- UHCC | Aqil Fares | 09-2372432 | uhcc@palnet.com | Health |
| Welfare Assocation | Haitham Hammouri | (+970-2) 241-5130 | hammouri@jwelfare.og | Development and Humanitarian Assistance |
| Youth Development Association | Talal Abukishek | 2976662 | info@youth.ps | Youth |

NGOs Jerusalem

| Name of NGO | Contact Name | Phone | Email | Sector |
| --- | --- | --- | --- | --- |
| Al-Maqdese for Society Developing (MSD) | Moua’azZa’tari | 02-6285918 0547-520249 | info@al-maqdese.org | Law and Democracy |
| Al-Nayzak Extracurricular Education & Scientific Innovation | Aref Al-Husseini | 02-6285387 | info@alnayzak.org | Instructional and advisory Educational activities for Children; Modern technologies and creative thinking programs |
| Arab Thought Forum (ATF) | Dr.Mu'enKanaan | 02-6289126/64774 | nfo@multaqa.org | Research, seminars on society, Development, Politics, Library |
| Dalia Association | Dr.Sa’idaMousa | 02-2989121/0599734357 | info@dalia.ps | International aid; Diaspora and other resources; sustainable development agenda |
| Grassroots Al-Quds | Mona Hassan | 02-9665655 | info@grassrootjerusalem.org | Legal Issues |
| Husseini Foundation | Abdel-Qader Husseini | 054-561 9370 | abdalqaderhusseini@gmail.com | Education |
| International Peace and Cooperation Centre (IPCC) | Adeeb Salem | 0546-880 358 | asaleem.ipcc@gmail.com | Applied research centre and Community development. |
| Jerusalem center for social & economic rights | Ziad Hammouri | 0545-949 242 | info@jcser.org | Society and Economy |
| Jerusalem Center for Social & Economic Rights (JCSER) | Ziad Al-Hammoury | 02-6271776/5446 | info@jcser.org | Legal aid & research on social & economic rights in Jerusalem |
| Jerusalem Chamber of Commerce | Azzam Abu-Sood | 0505-695 808 | azzamco127@hotmail.com | Commerce |
| Palestinian Academic Society for the Study of International Affairs - PASSIA | Dr. Mahdi F. Abdul Hadi | 02-6264426 6286566 | passia@passia.org | Seminars, research & meetings on the Palestine Question, civil society empowerment training program |
| Ru’ya (Palestinian Vision) | Rami NaserEddin | 02-6285080 | info@palvision.ps | Youth leadership in communities; voluntarism; networking |
| Sabeel - Ecumenical Liberation Theology Center | Dr.NaimAteek | 02-5327136 | sabeel@sabeel.org | Advocacy; local & international conferences; community building & empowerment; special tours |
| The Civic Coalition for Defending the Palestinians' Rights in Jerusalem | ZakariyaOdeh | 02-2343929 6287677 | info@civiccoalition-jerusalem.org | Human Rights |
| The East Jerusalem Hospitals Network (EJHN) | Dr.Tawfiq Nasser | 02-6279911/902 | info@avh.org | Health and Rehabilitation |
| Union of Parents’ Committees in East Jerusalem Schools | Eng. Abdul KarimLafi | 0522-809881 | almaqdision@bezeqint.net | Education |
| Women's Center for Legal Aid &Counseling (WCLAC) | Maha Abu DayyehShamas | 02-6281497- 6282449 | wclac@palnet.com | Women and Legal Issues |

# Annex 4: EVALUATION METHODOLOGY

The progress of the work was closely followed by a Reference Group (RG) composed of members of the Commission’s Directorate-General (DG) Development and Cooperation - EuropeAid Office (DEVCO), of the European External Action Service (EEAS), of the EU Delegation in Palestine, and chaired by the Evaluation Unit of DG DEVCO-EuropeAid.

In accordance with the guidelines issued by the Evaluation Unit, the methodology developed for this evaluation aimed to define and answer a set of Evaluation Questions in order to draw out conclusions based on sound analysis and useful corresponding recommendations. To this end, the evaluation was conducted in three main phases: desk phase, field phase and synthesis phase. This section briefly presents the overall evaluation process, the information on which the findings are based (data collection), and the main challenges and limits faced by the evaluation.

    - Evaluation Process

The evaluation has been carried out from March 2013 to April 2014, see workplan on next page. The evaluation was structured in three main phases: i) a desk phase; ii) a field phase; and iii) a synthesis phase. Figure 1 provides an overview of the three main phases, specifying for each of them the activities carried out, the deliverables produced and the meetings organised with the Reference Group (RG) and with the European Union Delegation (EUD) in Ecuador. Further details are provided in the paragraphs that follow.

Figure 1: Key Steps of the Palestine Country Level Evaluation

Workplan of the evaluation March 2013- April 2014

DESK PHASE

Inception stage

During the inception phase, the Team Leader has conducted a preliminary exploratory mission in March 2013 in Palestine. Throughout the inception phase, more than 10 representatives of EUREPstaff, national authorities and other donors have been interviewed. The objective of the preparatory mission was to introduce to the reference group representatives and other partners the evaluation process, the methodological approach, set a first contact with EUREP and identify through a participatory approach the fundamental issues to be addressed during the evaluation.

Following the preliminary analysis of the Commission’s strategy and policy documents, the team elaborated the intervention logic which represents the hierarchy of objectives and expected effects Evaluation of the Commission of the European Union’s co-operation with Palestine as expressed in the main strategy documents over the years. As such, it represents the backbone for the evaluation, and outlines the set of objectives against which the EC intervention will be assessed.

The intervention logic was designed on six levels as follows:

Level 1 - the starting point: EU Political agenda and Palestinian priorities

Level 2 - Interventions areas and cooperation tools

Level 3 - Cooperation interventions

Levels 4, 5 and 6 – Benefits of the cooperation effort as follows: .

- Outcomes (level 4) or immediate benefits relating to the interventions (benefits of DFS, sustainable changes induced in focal and non-focal sectors and benefits to refugees derived from support through UNRWA);

- Intermediate impacts (level 5) or longer-term sustainable changes, derived from intervention outcomes. Intermediate impacts contribute to the final goal of cooperation efforts (see summary list in box).

- Final Impact (level 6): the “2-state solution, including an independent, economically viable and democratic Palestinian state”. Level 6 matches with the EU political objectives described in level 1.

The interventions logic is presented in two different versions: 1) for monetary activities 2) for non monetary activities.

Figure 2: Intervention Logic - Cooperation interventions EU – Palestine, spending activities

Source total amounts are EC  committed amount, data retrieved from DWH and CRIS and DRN own elaboration

Figure 20: Intervention Logic – Cooperation EU-Palestine - Political dialogue and non-spending activities

Source: Doc A) EU-PA ENP Action Plan of 2005 and 2013; Doc B) PA Ending the Occupation Establishing the State August 2009, PA National Development Plan 2011-2013, PA Palestinian Reform and Development Plan 2008-2011; Doc C) UN Reports to AHLC 2008- 2012 Doc D) Measures Taken by Israel in Support of Developing the Palestinian Economy, the Socio-Economic Structure, and the Security Reforms Report of the Government of Israel to the AHLC,  April 2010; Doc E) Reports for AHLC on OQR Action in Support of PA - April 2011, March 2012, March 2013; Doc F) UNRWA: EU Discussion Paper 18 Oct 2010,  The Mandate of UNRWA at Sixty Lance Bartholomeusz; Doc G) WB Interim Strategy Note for the WB&GS 2012-2014 Report No: 66781-GZ, March 13, 2012; Doc H) Foreign Affairs Council Conclusions (Conclusion of 8 December 2009 on MEPP, Conclusion on MEPP of 14 May and 10 December 2012) and Communications (COM2010(207), COM2011(303))

The intervention logic demonstrates the need to focus evaluation efforts on different levels of the causes–effects progression:

- Links between interventions and political objectives driving the cooperation efforts, with attention to the first segments of the cooperation logic (relationships between political goals, beneficiary needs and the cooperation interventions);

- Relationships between interventions and goals, exploring the higher level of the results sequence (contribution of cooperation efforts to outcomes, intermediate impacts and political goals relating to the two-states solution);

- Analysis of the central part of the sequence, assessing processes, resources, capacities and partnerships in terms of achieving the cooperation goals (how effectively interventions are translated into benefits and the ultimate goals of the cooperation efforts).

Figure 4: Evaluation Questions and Intervention Logic

To address these levels the evaluation team designed four thematic clusters, embracing nine main Evaluation Questions focusing on critical aspects of the EC Palestine cooperation:

| Cluster | Evaluation Question: main focus |
| --- | --- |
| A - POLITICAL COHERENCE | - Political coherence in relations with Palestine |
|  | - Political coherence in relations with key players |
| B - EU RESPONSIVENESS | - EC processes, resources and capacities |
|  | - Cooperation instruments |
| C - STRATEGIC ALLIANCES | - Partnerships |
| D - DELIVERY OF THE COOPERATION EFFORT | - Governance |
|  | - Social sector |
|  | - Private sector and trade |
|  | - Water and sanitation |

Desk Stage

The desk study has consisted of a review of available documentary sources by the Evaluation team (see Bibliography, annex 2). It also builds on the inception visit to Palestine and exchanges with EU Representation staff (March 2013), as well as on interviews with a broad range of stakeholders (see List of People Interviewed in annex 3).

Five main categories of information have been collected and analyzed for the desk study:

- Background and context information on the country, the region and the Cooperation policy of the Commission. This information is necessary first for an understanding of the main issues addressed, or that should have been addressed, by the Commission’s support, and second for an overview of the country’s situation in relation to these issues, so as to form a first idea of the possible contribution of the Commission’s contribution to the observed trends. This work was started during the Inception Phase and then complemented during the Desk Study stage with information under each specific Evaluation Question.

- EU cooperation with Palestine including a systematic review of strategic and programming documents, alignment with the PA’s policies, an inventory of Commission’s funding, etc. This started during the inception phase and has continued throughout the desk study.

- Information on the interventions selected for in-depth analysis. A set of 19 interventions was identified and selected for further analysis during the desk and field work. This sample of cooperation interventions has supported the identification of lessons and provide elements of the answers relating to each of the Judgment Criteria, particularly for the last cluster (relating to delivery) of Evaluation Questions. The available documentation on these interventions has been screened at the level of the relevant Judgment Criteria. Due to the particular nature of this evaluation the case study analysis hasn’t been carried out following the standard procedures. The interventions selected have been reviewed only for particular sectors (governance, human rights, social protection, water and sanitation) but in-depth analysis at project level has not been developed.

- Information on ROM reports. A set of 10 ROM has been identified (see Annex 11) and selected for analysis during the desk and field phases and the information is to be used to support preliminary findings for each of the Evaluation Questions.

- Inventory. The DEVCO Inventory has been reviewed on the basis of documents collected for the UNRWA and PEGASE mechanisms and an additional inventory for ECHO interventions has been analyzed.

The process of data gathering and analysis is structured in two steps (see figure 1):

- Identification, collection and processing of information relevant to all Judgment Criteria and Indicators.

- Analysis and synthesis of the information at the level of Judgment Criteria and Indicators. For each Judgment Criterion the team has structured the information in order to provide the basis for:

- Preliminary elements of the answers and findings (what has been observed at this stage);

- Formulation of hypotheses for field work (what is presumed on the basis of the preliminary findings);

- Identification of information gaps (what could not be observed at this stage).

The desk study has been also characterised by several team meetings carried out in Rome and Bruxelles throughout the whole period. These meetings allowed to develop internal discussions on key points of the evaluation and focus on particular issues linked to the specific political nature of this evaluation.

Figure 5: Evaluation of Cooperation with Palestine, Desk Phase: approach to information processing

Field Phase

The work carried out during the field phase aimed to gather additional information that allowed to: i) confirm (or eventually disproof) preliminary findings; ii) validate (or otherwise) the hypotheses; and iii) fill remaining information gaps.

With a view to ensure the comprehensive coverage of the evaluation questions and issues to be investigated, each team member focused on certain EQs / interventions as detailed in the table below.

| Question | Joe Saba | Nick Krafft | Paolo Scalia | Jean-Claude Ceuppens | Omar Shaban | Jean Bossuyt |
| --- | --- | --- | --- | --- | --- | --- |
| EQ1 Political Coherence in relations with Palestine | x |  |  |  |  |  |
| EQ2 Political Coherence of EU External Action with Key Players | x |  |  |  |  |  |
| EQ3 EC Processes, Resources and Capacities |  |  | x |  |  |  |
| EQ4 Cooperation Instruments |  |  | x |  |  |  |
| EQ5 Strategic Alliances |  |  | x |  | x | x |
| EQ6 Governance: democratic and accountable Palestinian Institutions |  |  | x |  |  |  |
| EQ7 Social Sector |  | x |  |  |  |  |
| EQ8 Private Sector and Trade | x |  |  |  |  |  |
| EQ9 Water and Sanitation |  |  |  | x |  |  |

The table below describes the five key steps of the field phase:

|  | Key Activities |
| --- | --- |
| Preparatory Work | - Finalisation of the list of sources of information (incl. list of key informants, key databases, etc.) that will help fill the information gaps identified during the desk phase. - Each team member prepares a final programme for the mission. - Key staff of the Delegations are contacted to provide feedback on the draft list of interviews; - Preparation of interviews - Key informants (in first place PA officers) are contacted. - Preparation of logistical aspects of field work - Preparatory meeting (evaluation team) |
| Briefing with EU Delegation in Palestine | - Round-table discussion with key staff in Delegation. |
| Data Collection | - Collection of any missing reports, programme documents etc. - Final confirmation of key organisations and relevant staff to meet. - Interviews with relevant EU Representation officials addressing key sectors of cooperation. - Interviews with officials addressing overall coordination of donor aid. - Interviews with EU MS, UN, IFIs and other donors. - Other relevant national stakeholders such as NSAs, or relevant Civil Society organisations engaged in areas relevant to the Evaluation. - Interviews with local stakeholders (incl. implementing partners and beneficiaries). - Use of specific data collection tools (group discussions or other). |
| Debriefing | - Elaboration and presentation of preliminary findings to EU Representation |
| Debriefing with RG | - Elaboration and presentation of preliminary findings to Reference Group |

The field phase was carried out in four different moments as outlined in the text and table below:

|  |  | Dates | Consultants |
| --- | --- | --- | --- |
| 1 | First Mission to Palestine | 2-13 December 2013 | Joe Saba, Nicholas Krafft, Omar Shaban |
| 2 | Second Mission to Palestine / Jordan | 14-26 January 2014 | Paolo Scalia, Jean-Claude Ceuppens |
| 3 | Interviews in Bruxelles | 4-6 November 2013 / January 2014 | Joe Saba, Jean Bossuyt |
| 4 | Interviews in Washington | November/ December 2013 | Joe Saba, Nicholas Krafft |

- Mission to Palestine in December 2013: a two-weeks mission was organised with two team members (Team Leader and the Social Expert); due to health problems the deputy team leader was not able to take part to this mission, therefore a second mission was scheduled in January. During this visit key stakeholders have been interviewed in particular staff members of EUREP, EEAS, Members States (MS) Cooperation Offices and Consulates, Other Donors (USA, Switzerland) and PA representatives. During this first visit a focus group was organised by the national expert to PASSIA (Palestinian Academic Society for the Study of International Affairs) and a discussion on civil society view of the EU cooperation with Pas has been carried out;

- Mission Palestine/Jordan in January 2014: a second two-weeks mission was organised for the Deputy Team Leader and the Water and Sanitation Expert. During this visit  a second round of interviews has been carried out with EUREP to better focus on Instruments and Technical Cooperation issues and UNRWA for the refugees issues. Other interviews with specialised staff in Water and Sanitation have been carried out in particular with PA Ministries, MS Cooperation Agencies and UN (FAO, UNDP, UNICEF).

- Interviews in Bruxelles in November 2013: Ahead of the second mission additional interviews have been carried out in Bruxelles with EEAS and DEVCO for the collection of additional information for EQs 3 and 4 and with key NGOs for issues mostly related with civil society.

- Interviews in Washington in December 2013: Thanks to the professional network of two team members interviews in Washington with key staff members of WB and Islamic Development Bank  has been carried out.

During the field visit the below data collection tools have been applied:

| Interviews | Direct interviews were organized at four different levels: - Policy and strategic level: with national counterparts as well as EUD officials involved in policy definition. - Implementing bodies: interviews with the various Ministries, public institutions, and non-state actor organisations, including social partners and specialized agencies in charge of implementation. The managers of the EU Representation will also be interviewed. - Beneficiary institutions: these interviews will be limited to the above-mentioned sample of programmes. - Other donors and Civil Society: interviews with key external actors (business sector, trade unions, academic world, think tanks etc.) who are not directly involved in the EC cooperation but who could provide valuable information. EU Member States’ and other donors’ officials have been interviewed to complete the analytical policy framework of the main sectors of EC support. |
| --- | --- |
| Group meetings/Focus groups | Group interviews with a limited number of people from the same category (i.e. EU Representation staff, project staff) have been organized. Interviews aimed at: - appreciating perceptions of the results and relevance of the EU cooperation strategy overall or by sector, and the efficiency of the implementation mechanisms; - understanding the internal and external mechanisms of coordination and communication; and - validating, reviewing, and completing the findings and hypotheses of the desk phase. More specifically a focus groups with civil society representatives has been organised to the premises of PASSIA. |
| Additional Documentary review | In addition to the interviews the Evaluation team has collected additional documentation that was not possible to be collected previously. Sources included the EU Representation, managers of the programmes, beneficiary institutions and organisations, other donors, EU Member States, and other Civil Society organisations and academic centres. |

Synthesis Phase

During the Synthesis Phase the team brought together the results of the desk phase and field phase, including comments made by the RG during the debriefing held in Brussles on the 4th of February 2014, in the drafting of the final report. During the synthesis phase, all information collected was analysed and cross-checked with a view to provide evidence-based answers to the evaluation questions, sound conclusions and useful recommendations. See Annex 5 Data Evaluation Grid for a full overview of data collection tools used for each JC and EQ.

The analysis was structured according to the three-tiered logic from Indicator, to Judgement Criteria (JC), to Evaluation Question (EQ). As a result, activities carried out during this phase can be grouped in the following five subsequent steps:

- Informing the indicators: sharing of information between the team members, updating, comparing, confirming and cross-checking the information gathered through the different sources;

- Identifying the limits of the analysis: data quality and unavoidable information gaps;

- Validating, integrating or amending the judgement criteria;

- Providing answers to the evaluation questions based on the combination of the answers at the level of the JCs;

- Drafting of conclusions and recommendations

- Quality control of the whole report

# Annex 5: DATA evaluation GRID

| EQ | Judgment Criteria | Indicators | Source of information |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Documentary review | Interviews |  |  |  |  |  | Focus Groups | ROM analysis | Inventory analysis | Site visit |
|  |  |  |  | EU Staff in Bruxelles | WB staff in Washington | EUREP | PA | NGO | Other Donors |  |  |  |  |
| EQ 1 POLITICAL COHERENCE IN RELATIONS WITH PALESTINE; To what extent and how has the EU developed and implemented a coherent political strategy to underpin its relations with the Palestinian Authority and foster its core objectives (i.e., the two-state solution and the establishment of an independent, democratic and viable Palestinian state? | JC1. The EU has elaborated and implemented a clear and coherent external action strategy towards the PA that has the effective support of Member States; | - Strategy in place; - Clear, comprehensive and coherent definition of strategy; - MS support to strategy; | x | x | x | x | x |  | x |  | x | x |  |
|  | JC2. Appropriate, efficient and result-oriented political dialogue mechanisms are in place between the EU, the PA and other stakeholders; Inception report version: “Appropriate, efficient and result-oriented political dialogue mechanisms are in place between the EU and the PA” Justification of change: Words “and other stakeholders” have been added to open to a broader analysis of the political dialogue based on results. | - Dialogue mechanisms in place; - Benchmarks and targets agreed; - Follow up of results by political dialogue; | x | x | x | x | x |  | x |  | x | x |  |
|  | JC3. The EU has developed adequate responses to address the divergence of the West Bank and Gaza Strip including economic and governance divergence; Inception report version: “The EU has developed appropriate response to address the inter Palestinian conflict” Justification of change: The change improves JC focus on political differences of Palestinian society, and how these affect governance and economic issues, aspects relevant to cooperation efforts’ analysis. | - Evidence of progress toward reconciliation as a result of EU cooperation efforts; | x | x | x | x | x |  | x |  | x | x |  |
|  | JC4.The EU external action towards the PA –including the use of its leverage as global player and major donor- contribute to attainment of the EU’s political and cooperation objectives | - Evidence of use of leverage to engage Palestine, Israel, Member States and other stakeholders toward the achievement of political goals; | x | x | x | x | x |  | x |  | x | x |  |
| EQ 2 POLITICAL COHERENCE OF EU EXTERNAL ACTION WITH KEY PLAYERS; To what extent and how has the EU developed and implemented a coherent external action strategy to push for peace and a two-state solution in its relations with key political players including Israel, regional actors and its partners in the Quartet? | JC1.The EU has adequately used available tools and instruments to constructively engage with Israel towards achieving peace and contributing to the establishment of an independent and viable Palestinian state. Inception report version: “The EU has adequately used available tools and instruments to influence Israeli approaches towards achieving peace and contributing to the establishment of an independent and viable Palestinian state” Justification of change: “Constructive engagement” describes better the scope of EU dialogue with Israel and sets a better frame for evaluation work. | - Increased access to Area C, - Availability of permits for EU delegation, humanitarian workers and EU Parliamentarians for movement within West bank/Jerusalem and to/from Gaza; - Progress on trade matters ( King Hussein bridge, e.g.,) - Regularity of VAT remission from Israel to PA | x | x | x | x | x |  | x |  | x | x |  |
|  | JC2. The EU has engaged strategically with Regional Donors with a view to fostering the peace process and contributing to the establishment of an independent and viable Palestinian State; | - Evidence of efforts to engage regional Donors; | x | x | x | x | x |  | x |  | x | x |  |
|  | JC3. The EU has optimally and coherently used its leverage and available windows of opportunity within the framework of the Quartet to push for peace and for the establishment of a viable and independent Palestinian state | - Examples of pro-active action within the Quarter framework to foster EU goals; | x | x | x | x | x |  | x |  | x | x |  |
| EQ3. EU PROCESSES, RESOURCES AND CAPACITIES; To what extent do EC processes, resources and capacities support political and cooperation goals in Palestine’s complex and volatile environment? | JC1. Capacities are established to define cooperation strategies coherent with political objectives and are responsive to conflict and the external context; | - Strategies clear and benchmarked and in line with political objectives; - Sectoral strategies developed; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC2.Coordination with donors, development agencies and key stakeholders fosters design and implementation of an effective cooperation program | - Coordination mechanisms in place; - Action fiches evidence coordination and complementarities; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC3.Capacities are established for programming and design of effective cooperation efforts, in line with strategies and political goals; | - Quality of design of interventions; - Quality control mechanisms in place; - Project assessment and prioritization mechanisms in place; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC4. Capacities are appropriate to implement, follow up and evaluate interventions in line with strategies and political goals, and are adapted to the volatile context of Palestine | - External evaluation of efficiency criterion (including monitoring reports); - Timeliness of interventions; - Portfolios of Programme Officers in EUREP: number of contracts and value (million €) per person; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC5.Learning mechanisms are in place supporting new strategies and cooperation interventions | - Tools, programs and interventions which did benefit of external assessment; - Mechanisms in place to follow up implementation of evaluations’ recommendations; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC6. Effective communication and visibility strategies and mechanisms supports EU cooperation | - Visibility and communication strategy in place; - Communication strategy is designed to support contributions to goals; | x | x |  | x | x |  | x |  | x | x |  |
| EQ4 - COOPERATION INSTRUMENTS; Are the different cooperation instruments adapted, suitably flexible and effective for contributing to political and cooperation goals? | JC1. Direct financial support (PEGASE) is effectively supporting political goals | - External assessment of PEGASE; - Evidence of outcomes contributing to viable Palestinian State; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC2.The EU uses its various instruments in a strategic and complementary way to optimize impact; The analysis is covering: i) Development Projects, ii) Support to East Jerusalem, iii) Support to Area C, iv) Thematic programs, v) Regional Programs | - Action Fiches supporting complementarities; - External assessment of complementary use of instruments; | x | x |  | x | x |  | x |  | x | x |  |
|  | JC3.Support to refugees through UNRWA is strategically supporting the achievement of EU goals for the Palestinian people | - External assessment of outcomes of UNRWA efforts; - Evidence of contributions to EU goal as a result of UNRWA support; | x | x |  | x | x |  | x |  | x | x |  |
| EQ 5 - STRATEGIC ALLIANCES; To what extent and how has the EU engaged in strategic alliances with key actors in-country with a view to enhancing the relevance, outreach and impact of its own political and cooperation efforts? | JC1. The EU engages in dialogue with relevant Palestinian civil society organizations and provides support that fosters their empowerment and viability as domestic change agents | - Example of engagement in dialogue; - External assessment of work with civil society; - Civil society perception of support provided by EU (qualitative analysis tools); | x | x | x | x | x |  | x |  | x | x |  |
|  | JC2. The EU has developed an effective strategic framework to engage (politically) with UNRWA, including appropriate institutional arrangements | - Evidence of political engagements with UNRWA; - Institutional arrangements in place; | x | x | x | x | x |  | x |  | x | x |  |
|  | JC 3. The EU has developed and effectively implemented a strategic alliance with IFIs, inter alia through dialogue, joint action, task division on the basis of comparative advantage and a pooling of expertise and financial resources | - Agreements with IFIs to share tasks; - Evidence of joint actions with IFIs; - Examples of blending mechanisms applied to cooperation with Palestine | x | x | x | x | x |  | x |  | x | x |  |
| EQ6 GOVERNANCE; How effectively does the EC cooperation contribute to the EU goal of building transparent, democratic and accountable Palestinian institutions, respecting the rights of citizens? | JC1.Clear goals and strategies are set for democracy, justice, human rights and rule of law | - Strategy statements relevant to goals; - Clear benchmarks set for good governance; | x | x | x | x | x | x | x |  | x | x |  |
|  | JC2. Cooperation interventions respond to needs and demands of the Palestinian people | - External evaluations assess positively relevance to needs; - Beneficiaries confirm through interviews perception of relevance of EC cooperation to their needs (qualitative analysis); | x | x | x | x | x | x | x |  | x | x |  |
|  | JC3. Cooperation efforts contribute to institutional capacity-building for governance, accountability and credibility of key institutions | - Evidence of capacity building across cooperation interventions; - Positive assessment of capacity building components by external evaluations; | x | x | x | x | x | x | x |  | x | x |  |
|  | JC4. EU–Palestine Cooperation effectively supports goals of good governance, democracy, respect for human rights and rule of law contributing to a viable and democratic Palestinian State | - Interventions supporting governance are positively assessed (SDG, monitoring reports, external evaluations) - Evidence of positive results of cooperation efforts in favor of good governance; - Support to political dialogue on Good Governance issues, SDSG and thematic working groups or regular exchange of information at regional and national level | x | x | x | x | x | x | x |  | x | x |  |
| EQ 7 SOCIAL SUPPORT; Is EC support to the social sector (education, health, social protection and food security) fostering a socially viable State, while improving the social conditions of the Palestinian people? | JC1.Cleary goals and strategies set for education, health, social protection and food security | - Social sector strategy is well defined and in line with goals; - Results, targets and benchmarks defined and followed up; | x | x | x | x | x | x | x | x | x | x |  |
|  | JC2. Cooperation interventions respond to needs and demands of Palestinian people | - External evaluations assess positively relevance to needs; - Stakeholders (PA and Civil Society) confirms through interviews perception of relevance of EC cooperation to their needs (qualitative analysis); | x | x | x | x | x | x | x | x | x | x |  |
|  | JC3. Cooperation efforts contribute to institutional capacity-building and good governance in sector institutions | - Evidence of Institutional Strengthening result from EU Cooperation; | x | x | x | x | x | x | x | x | x | x |  |
|  | JC4. EU – Palestine Cooperation effectively supports goals of a socially viable and sustainable Palestinian State Inception Report: EU – Palestine Cooperation effectively supports goals of a socially viable Palestinian State; Justification of change: The analysis of sustainability of social sector support and its contributions to the goal of a “sustainable” State strengthen the definition of the JC and allow for a better focus of the assessment; | - Interventions supporting social sector are positively assessed (subcommittee, monitoring reports, external evaluations) - Evidence of positive results of cooperation efforts in favor of social sector; - Support to political dialogue on social sector issues, thematic working groups or regular exchange of information at regional and national level | x | x | x | x | x | x | x | x | x | x |  |
| EQ 8 PRIVATE SECTOR AND TRADE; Are the EC’s interventions for private sector development and trade effectively promoting the goal of an economically viable Palestinian State? | JC1. Clear goals and strategies set for private sector development and trade | - PSD strategy is well defined and in line with goals; - Results, targets and benchmarks defined and followed up; | x | x |  | x | x | x | x |  | x | x |  |
|  | JC2. Cooperation interventions respond to needs and demands of project partners and targeted beneficiaries Inception Report: “Cooperation interventions respond to needs and demands of Palestinian People;” Justification of change: Rewording, with specification of partners and beneficiaries, allows for a more precise focus of the analysis of relevance; | - External evaluations assess positively relevance to needs; - Stakeholders (Private Sector) confirms through interviews perception of relevance of EC cooperation to their needs (qualitative analysis); | x | x |  | x | x | x | x |  | x | x |  |
|  | JC3. Cooperation efforts contribute to institutional capacity building and good governance | - Evidence of Institutional Strengthening result from EU Cooperation; | x | x |  | x | x | x | x |  | x | x |  |
|  | JC4. EU – Palestine Cooperation effectively supports private sector development, contributing to an economically viable Palestinian State | - Interventions supporting PSD are positively assessed (subcommittee, monitoring reports, external evaluations) - Evidence of positive results of cooperation efforts in favor of PSD; - Support to political dialogue on PSD issues, thematic working groups or regular exchange of information at regional and national level | x | x |  | x | x | x | x |  | x | x |  |
| EQ 9. WATER, SANITATION AND LAND To what extent have the EC’s interventions on water and sanitation delivered social and economic benefits (contributing to poverty reduction), supported national institutional capacity (contributing to state-building) and cross border cooperation (contributing to governance challenges)? | JC1.Clear goals and strategies set for the water and sanitation sector | - Key constraints for access to water and sanitation identified; - Strategy, goals and plan of action defined and coherent to sector priorities | x |  |  | x | x |  | x |  | x | x | x |
|  | JC2. Cooperation interventions respond to needs and demands of the Palestinian people | - Budget allocated to develop access to safe drinking water and increase the wastewater treatment; - Beneficiaries confirms through interviews perception of relevance of EC cooperation to their needs (qualitative analysis); | x |  |  | x | x |  | x |  | x | x | x |
|  | JC3. Cooperation efforts contribute to institutional capacity-building and good governance | - Enhancement of sector Authorities (PWA) capacity to manage and mitigate the effects of water shortage and environmental issues; - Support and enforcement of the regulatory framework and national capacities; - Budget allocated to support and develop sector capacities; | x |  |  | x | x |  | x |  | x | x | x |
|  | JC4. Support to water and sanitation contributes to improved socio-economic conditions and sustainable use of water resources, supporting the goal of an economically viable and sustainable Palestinian State | - Number and quality of regional coordination programmes on water; - Support to political dialogue on W&S issues, thematic working groups or regular exchange of information at regional and national level; - Resources involved in developing complementarities and synergies | x |  |  | x | x |  | x |  | x | x | x |

# ANNEX 6: NATIONAL CONTEXT

Political and historical overview

Figure 1: Map of Palestine

Historical overview. In accordance with the Gaza-Jericho Agreement of 1994 which followed the 1993 Oslo Accords between Israel and the Palestinian Liberation Organisation (PLO)the Palestinian Authority (PA) was established as an interim administrative body to prepare for final status agreement and an end of the Israeli-Palestinian conflict.. The agreements defined the PA mandate and authority in terms of internal Palestinian security and certain civil affairs. At the end of the initial five year interim period, further negotiations were to have led to Palestinian elections and final status agreements. In essence, the PA’s task was to guarantee Israel’s security and foster development in defined areas of the occupied Palestinian territories. In return, Israel would permit a gradual expansion of PA governance. In the event, elections were not held in 1998, settlements expanded and security diminished. Following the outbreak of the second Intifada in 2000 and Israeli military action in 2002, joint patrols between Israeli and Palestinian Security Forces (a fundamental pillar of the Oslo framework) ended. Israel extended and reasserted its military presence in the West Bank (WB), assuming overall security control and establishing military checkpoints in Area A, see Figure 1.

In 2005, Israel withdrew its military and Israeli settlers from the Gaza Strip (GS). In January 2006, Palestinian elections resulted in Hamas naming Ismail Hamiyeh PA Prime Minister. In reaction, Israel, the United States, Canada and the EU then froze diplomatic relations and funding to the PA, conditioning resumption on Hamas agreement to three conditions: recognition of Israel, renunciation of violence; and, abiding by all existing agreements between the PLO and Israel. Pending satisfaction of these demands, Israel withheld the customs clearance revenues it collected for the PA, which was heavily reliant on this income to meet recurrent expenditures. Direct international aid to Palestine dropped significantly. In addition, Palestine’s main bankers, fearing actions under US law sanctioning Hamas as a terrorist organization, ceased operating PA accounts and began to call in their loans to the PA. The boycott of the PA aggravated the already severe economic crisis in Palestine.

A unity government was formed between Fatah and Hamas in early 2007, but conflict continued in the GS and on June 14, 2007, Hamas took control of the GS, ousting Fatah. One day later PA President and Fatah Chairman Mahmoud Abbas named a Caretaker Government for the PA led by Prime Minister Salam Fayyad. The international community embraced the new PA cabinet and pledged more than US$7.5 billion in aid. The funds were to support the PA objectives of sustaining gains and progress with institutional development aiming at statehood. By late 2011, a consensus emerged in the international community that the PA had reached its institutional goals. However, Hamas has remained in de facto control of the GS, although the PA continues to assert its authority and pay its employees there through the PA budget. And despite the PA’s executive institutional progress, elections were postponed, the Palestinian Legislative Council became paralyzed and judicial institutions stalled in advancing most administrative reforms.

In November 2008, hostilities between Hamas and Israel broke out. Israel undertook Operation Cast Lead, invading the GS with considerable loss of life and property. The PA in the WB took no military action. For the GS, the brief war brought considerable loss of life, further economic decline and isolation imposed by an Israeli military blockade and a boycott by international donors. However, by 2009, Hamas authorities had succeeded in sustaining tunnel traffic with Egyptian Sinai which helped boost an economic revival, though no credible data exists on the volume or kind of trade.

In 2011, Fatah and Hamas agreed to form a unity government and hold elections. However that agreement was not implemented and no elections, other than some local elections in 2012, have been held since 2006. In the interim, laws have been issued by PA Presidential decree.

On November 29, 2012, in a 138-9 vote, with 41 abstentions, the UN General Assembly voted to upgrade Palestine to a “non-member observer state.” Israel responded by withholding customs revenue due the PA, severely aggravating an already dire fiscal situation.

Political context. Despite the explicit intent of the Oslo Accords, twenty years of substantial international assistance, institutional gains and the 2012 UN recognition, Palestine still lacks the fundamental attributes of a state. It does not have a monopoly of the use of force for security in its territory, even in the relatively small West Bank Area A. Indeed, since at least 1998, in the WB, the PA’s span of control and governance has continually diminished as Israeli settlements, subject entirely to Israeli law and governance, have expanded. Hence, its territory and span of control have been at all times uncertain. It does not have full authority to mobilize, allocate or manage resources between the WB and GS or externally; and it lacks jurisdiction over natural resources, airspace and the sea.

The PA therefore has limited authority but broad responsibility for administering two non- adjacent land areas. This task has been difficult from the outset of the Oslo process in 1993 and has become more so since the 2007 divergence of governance between the WB and the GS. However, perhaps the PA’s single greatest constraint has been the system of Israeli limitations on Palestinian freedom of movement and access to resources and markets.  Beginning in 1992, Israel imposed on all of Palestine a complex and unpredictable regime of permits and closures determined by a set of non-transparent military orders as would be applied under full military occupation. The impacts of the permit and closure regime have been continuing, cumulative and pervasive, affecting virtually every aspect of Palestinian political, economic and social life. The regime’s opaque and ever-changing system limits the PA’s ability to deliver basic services to its constituents. The system inhibits the unification, coherence and coordination of Palestinian legal and administrative systems and service delivery and creates the de facto application of two sets of laws in one territory: permissive, encouraging, accountable and protecting for Israelis and settlers; restricting, opaque and discriminating for all others.

Economic background

Over the past twenty years, while the PA has been successful in developing the institutions to manage an independent state, the economic foundations remain much weaker. Prolonged occupation and the permit and closure regime have arrested economic development and locked in structural distortions, and restricted Palestine’s ability to access the resources necessary to maintain macroeconomic and fiscal stability, provide basic services and grow a productive private sector.

In the post Oslo period, industry, agriculture, tourism, transport, retail sales services and some related services contributions to GDP and employment have declined or stagnated at best, while donor funded sectors such as public administration, education, health and social services have grown (through budget support and development projects). Hence, the donor contributions and public sector employment have been the major drivers of growth.

Thus, the outlook for the economic situation in Palestine reflects the uncertainties in the political situation. Since 2000, the economy has been volatile. GDP fell to US$3.6M in 2002 and then recovered slightly in 2003 and 2005. With the continuing restrictions on the movement of goods and people, the loss of international aid, GDP fell again in 2006 after the election of Hamas. Real GDP in 2007 was US$3.9M, 14% lower than its peak in 1999. The situation since 2007 has remained relatively stable with an average GDP growth rate equal to 7% but with some negative trends during the last year, see Figure 2. As current projections indicate, much of the real economic potential for growth has been exhausted. The economy by 2013 is moribund with a projected real GDP growth declined to 5%, far below recent growth rates, with a continuing downward trend in subsequent years and supported almost exclusively by high levels of external aid. The continuation of these circumstances undermines the functionality and legitimacy of the institutions built over the past twenty years.

Figure 2: GDP Growth Rate 1999-2012 - Palestine Source: PCBS and World Bank Staff for Economic Monitoring for AHLC September 2102 and March 2103

Trade. The legal reference for trade policy in Palestine is the 1994 Protocol of Economic Relations (Paris Protocol or PP). This placed Palestine in a quasi-customs union with Israel and effectively left Israel in control of Palestine’s external economic relations. With few exceptions, the PP extended Israeli tariffs, tax rates and in most cases technical standards to Palestine. In theory, the PP could have led to deep integration of the two economies. However, the PP was never fully implemented as envisioned. Indeed, after the Oslo Accords, while goods from Israel entered Palestine freely, exports from the Palestinian territories were constrained in a variety of ways: security restrictions which are the facto non-tariff barriers (such as quality, health and safety standards) imposed on the movement of Palestinians goods and restrictions on the importation of dual use goods. These and other measures have all had the effect of increasing uncertainty and the cost of trade and reducing the competitiveness of Palestinian exports both within Palestine and Israel and to the rest of the world.

Israel remains the main destination for Palestine’s exports and source of imports. Though there has been a small increase in the share of exports to the rest of the world, particularly the Arab countries, Israel dominates Palestinian trade and will likely continue to do so for the foreseeable future. According to PCBS figures, Israel has been consistently accounting for around 85-90% of Palestinian exports and 65-75 % of imports since 2008.

Figure 3: Import-Exports and trade balace of Palestine 2000-2013, USD Millions Source: PCBS and DRN elaboration

Palestine’s export performance has always been weak but it particularly suffered during the Second Intifada. Between 2000 and 2002, exports of goods and services declined by nearly 45 % in real terms (see Figure 6), falling from 18% to 12.5% of GDP. Since then they have recovered slightly, rising in 2008 to the equivalent to 16 % of GDP and remaining stable. The poor export performance, combined with the need to import almost all consumption goods have resulted in Palestine consistently running large trade deficits. The bulk of the decline occurred in Gaza, where the closures have shut off exports and where there is only a limited domestic market. The high cost of doing business in Palestine and the Israeli restrictions on movement combine to lower the competitiveness of Palestinian businesses. Consequently, only 7 % of manufacturing enterprises in the 2009 Economic Survey reported exporting and exports were only 11 % of total sales.

Private Sector. The Palestinian private sector is overwhelmingly dominated by small family owned and managed enterprises. According to the 2007 PCBS enterprise census, the average size of employment in the West Bank establishments was 3 for all enterprises and 4.5 for manufacturing. There were only 57 establishments with more than 100 workers in the entire Palestine and only 26 in the manufacturing sector. Internal trade dominates accounting for more than 40 % of employment, while service activities account for 30 % and industrial activities 22 % of employment. Palestine is specialised in labor intensive manufacturing with a very low competitive performance, due to the labor costs relatively higher compared to other countries specialized in same goods and a labor force scarcely trained and specialised.

The lack of land and security remain major impediments to the development of the Palestinian private sector. PA is making a concerted effort to improve the business environment. It has made notable progress, especially in establishing security and stability. However, there remains much to be done as evidenced by Palestine slipping from 133 in the 2010 to 135 in 2011 in the overall Doing Business rankings.

Socio - cultural background

Social Development: Education, Health, Social Protection, Food Security, and Payment of Social Sector Salaries. This section provides a brief overview of the performance of the social sectors, which have, over past years, received huge support from the EU and donor community.  By far the largest proportion of PEGASE funds are directed at payment of PA salaries and support for social protection.  The bulk of PA employees are in the education and health sectors.  Hence by providing PEGASE support, the EU is invested in education, health and social protection. – the EU directly pays the salaries of about one third of all teachers and health workers.

Figure 4: Unemployment in the West Bank and Gaza compared to selected countries Source : West Bank and Gaza coping with conflict? Poverty and inclusion in the West Bank and Gaza - WB report No. 61293 – July 29 2011

Socio-economic situation. Unemployment in the Palestinian Territories continues to be alarmingly high compared to that of other countries.  The overall unemployment rate reached 22.9% in 2012.  The unemployment rate in Gaza continues to be amongst the highest in the world at around 32.2%.

Table 1: Labour Force Statistics (at the end of 2012) - % WB&GS; WB; GS. Unemployment Rate; 22.0; 18.3; 32.2. Labour Force Participation; 43.9; 46.1; 40.0. Under employment; 5.7; 5.0; 7.1. Youth Unemployment (Ages15-29); 35.1; 27.9; 48.9. Youth Labour Force Participation; 38.0; 40.3; 34.2. Source: PCBS Labour Force Survey from World Bank, Fiscal Challenges and Long Term Economic Costs: Economic Monitoring Report to AHLC, March 19, 2013

Youth unemployment reached a frightening 48.9% in Gaza (see table 1). Labor force participation is also low. These figures indicate that Palestinian youth is discouraged from joining the labor force because of lack of opportunities.  To illustrate: prior to the year 2000 when the second Intifada broke out, a large portion of Palestinian youth was employed in Israel as the latter’s share in Palestinian Territory employment was around 21%.  Since the outbreak of the second Intifada, Israel’s share in employment has declined to 12%.  The high youth unemployment and low labor force participation are both predictors of social discontent.

The gap between the overall participation rate of males (69.5%) and females (18.7%) is large.

Looking ahead, the risk for high unemployment remains significant. Private investment is unlikely to increase significantly given the on-going Israeli constraints on trade, movement and access, and investment in Area C – these restrictions remain the biggest constraint facing Palestinian private sector growth. Unless the situation changes, the private sector will not be able to generate sufficient job opportunities to absorb the increasing number of job seekers. The public sector has been the employer of last resort but its ability to generate more jobs is limited given the PA’s financial stress and the already excessive size of the sector.

Poverty. In 2009, a little over a fifth of the Palestinian population lived in poverty. The principal poverty narrative is the prevailing and widening poverty divide across the regions of Gaza and the West Bank despite an overall 4 percent point reduction in poverty since 2004.  Poverty in the West Bank has been steadily declining, while in Gaza it has yet to return to its 2004 level. (Figure 5 below). At 33.7%, poverty incidence in Gaza is twice as high as that in the West Bank. The stark regional divergence is driven by the severe economic shock that began in 2006. Gaza experienced a dramatic 20-percentage point poverty increase in 2007, with one in two living below the poverty line.

Analysis by the World Bank shows that while there are many drivers of poverty, education level and employment status are clear and enduring correlates of poverty status demonstrating that the closure policy which restricts growth in the private sector is not surprisingly a key factor.

Figure 5. Poverty Incidence across West bank and Gaza (as percentage of population)

General Overview of Human Development Status. Despite the gloomy picture on unemployment and poverty (and mental health), there are some remarkable bright spots.  Unlike in many other countries, poverty in the West Bank and Gaza is not correlated with poor human development outcomes.  The Palestinian territories outperform other countries with similar GNI per capita as well as its neighbors in terms of life expectancy and literacy rates, which are much higher than countries with similar per capita incomes such as India, Egypt, Nigeria, Cameroon and Ghana (Figure 6). In fact, Palestinian measures are on par with its richer neighbors in the region, Turkey and Jordan, which have seven and three times the per capita income of the West Bank and Gaza.

Even more striking is the remarkable performance of the Palestinian Territory on measures of early childhood development. Countries with similar per capita GNIs perform far worse in terms of measures of stunting and wasting (Figure 7). India, Pakistan and Nigeria have stunting rates more than three and a half times that of the West Bank and Gaza. The comparison is even starker in wasting incidence, with rates more than seven times higher than in the Palestinian territories. Again, the performance of the West Bank and Gaza on these measures of long term investments in human capital dimensions is in line with middle income countries rather than countries with similar per capita incomes.

| Figure 6: Life expectancy and literacy in the West Bank and Gaza compared to selected countries | Figure 7: Stunting and wasting in the WB&GS |
| --- | --- |
| Source: West Bank and Gaza coping with conflict? Poverty and inclusion in the West Bank and Gaza - WB report No. 61293 – July 29 2011 |  |

In short, within its limited ambit of influence in sectors such as education, health and social protection, the Palestinian Authority has implemented policies that ensure service delivery, which bodes well for the formation of a future Palestinian state.  Rather than being linked to human development outcomes, poverty and unemployment are much more closely linked to labor market outcomes, themselves a product of the mobility of labor and goods and the consequent lack of dynamism of the private sector.  This relatively strong performance in the area of human development carries forward to WBG’s achievements with the Millennium Development Goals. These achievements are high in those areas where the PA has significant ability to influence outcomes (achieving universal primary education, promoting gender equality and empowering women, improving maternal health, and combating HIV/AIDs). It is doing less well on eradicating extreme poverty and ensuring environmental sustainability (over which it has only limited influence).  It is not clear why it has performed poorly in the area of reducing child mortality.

Figure 8: Incidence of stunting in Palestinian territories and around the world

Figure 9: Incidence of wasting in Palestinian territories and Around the World Sources: World Health Organization, Global database on Child Growth and Malnutrition; Size of bubbles proportional to total population.

Education. In West Bank and Gaza, school enrolment has always been high with an average of 90% enrolment for the school age population, see figure 10. Access to primary education is near universal. The secondary gross enrolment rate is on the order of 20% percentage points higher than the rate in the average middle-income country. Also, as a result of a surge in enrolments in the last decade, enrolment rates in tertiary education are well above the average for the Middle East and North Africa Region. But access does not provide the full story. Students must learn. In this regard, the WB and Gaza’s performance on international student assessments has been mixed. WB and Gaza participated in the 2003, 2007 and 2011 international comparative student assessment Trends in International and Science Study (TimSS) which is designed to help countries all improve student learning in mathematics and science. WB and Gaza scores dropped between 2003 and 2007 but increased in 2011. Around 50 countries participated in both studies. After weak performance in 2007, performance ranked reasonably well compared to other countries. Performance was much poorer in Gaza relative to West Bank; Gaza performance is also getting weaker. .

Figure 10: Enrollment ratios by age group, 1995-2011 Sources: Palestinian Central Bureau of statistics

Figure 11: TIMSS results, Mathematics, Gaza and West Bank, 2003, 2007 and 2011

Figure 12: TIMSS results, Science, Gaza and West Bank, 2003, 2007 and 2011

Figure 13: Difference in TIMSS Scores – West Bank Compared to Gaza, Mathematics and Science, 2003, 2007 and 2011 Source: TIMSS and MOE, Department of Assessment and Evaluation, Ramallah

Table 2 compares performance in Gaza between UNRWA-run schools, those run by Government (PA/Hamas), and private schools. As can be seen, performance is consistently best in private schools, then in UNRWA-operated schools, and weakest in Government-operated schools.

Table 2: School performance in UNRWA schools, PA schools, and Private schools

| Area | UNRWA |  |  |  | PA |  |  |  | Private |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Arabic |  | Math. |  | Arabic |  | Math. |  | Arabic |  | Math. |  |
|  | Pass % | Mean 50 | Pass % | Mean 50 | Pass % | Mean 50 | Pass % | Mean 50 | Pass % | Mean 50 | Pass % | Mean 50 |
| 1st Semester 2010-2011 | 72.9 | 33.1 | 65.9 | 29.3 | 59.8 | 28.0 | 53.2 | 25.6 | 87.8 | 38.9 | 84.5 | 34.5 |
| 2nd Semester 2010-2011 | 76.0 | 33.7 | 83.4 | 34.6 | 67.1 | 30.4 | 75.0 | 32.3 |  |  |  |  |
| 1st Semester 2011-2012 | 71.1 | 30.5 | 71.0 | 31.5 | 56.6 | 25.8 | 57.9 | 27.4 | 90.5 | 36.7 | 89.5 | 37.9 |
| 2nd semester 2011-2012 | 76.7 | 32.5 | 80.5 | 33.8 | 67.4 | 29.2 | 71.5 | 31.1 | 95.7 | 41.1 | 96.8 | 41.6 |
| 1st Semester 2012-2013 | 71.0 | 30.7 | 69.7 | 31.0 | 62.0 | 27.5 | 63.0 | 28.6 | 90.5 | 38.2 | 90.5 | 38.0 |
| 2nd semester 2012-2013 | 79.8 | 34.9 | 76.0 | 32.9 | 73.0 | 32.1 | 68.7 | 30.3 | 94.6 | 41.5 | 92.7 | 39.2 |

In short, as the March 2013 UNICEF report notes, Gaza has a number of strengths in its education system: high enrolment, gender equality, widespread availability of textbooks, high proportion of qualified teachers, and reasonable assessment of student learning. Many of these activities are or have been supported by the EU and/or other donors. The main weakness is related to low and unequal educational achievements. Moreover its performance is falling relative to the West Bank.

UNICEF concludes that low education achievement is the product of multiple factors.  Environmental (or non-school) factors include the effects of border closure, socio-psychological effects of military conflicts, high unemployment and slow economic growth etc.  A compounding effect may be the content and quality of what is taught. For example, despite the large number of unemployed youth, employers report that it is difficult to hire qualified job applicants – there is a mismatch between skills of the unemployed, many with university degrees, and those skills demanded by the labor market.  Recent focus groups clearly identified the lack of relevant skills as well as the low level of competencies and experience of graduates to be among the most important constraints to employment for youth in the Territory.

In the same vein, the Technical and Vocational Education and Training (TVET) institutions are criticized for producing graduates, year after year, with little regard to the labor market signals.   According to the private sector, the education system does not well prepare students for the demands of the modern work-place. Most topics are taught using traditional methods of lectures, memorization, and examinations with less emphasis on critical thinking, problem solving, and hands on learning experiences. Though the TVET institutions have in recent years embraced more rigorous and professionally oriented curricula, the same World Bank report notes that the system does not begin to reach its potential. This is an area in which the EU has sunk considerable resources and may require a re-look.

Health. Despite high unemployment, high poverty, and chronic conflict, child nutrition indicators in Palestine are extraordinarily high. These results are consistent with other indicators of child health and nutrition. Almost all children are immunized against diphtheria, pertussis, tetanus, measles and tuberculosis. Vaccination rates exceed those of the average middle-income country.  There is near universal coverage of pre-natal care. And life expectancy at 73 is good compared to an average is 70 for all countries of the Middle East.

| Figure 14: Tangible improvements to health in Gaza and the West Bank (1999-2009) | Figure 15: Health expenditure trend line in the Palestinian territory for the years 2000-2010 |
| --- | --- |
| Source: Palestinian Bureau of Statistics and Ministry of Health. National Health Accounts 2009, 2010, Main Findings. Published Feb 2012 |  |

Good as they may be, it is important to note that these health outcomes paint only a partial picture of health outcomes in terms of coverage and scope.  Maternal mortality remains unacceptably high. Infant mortality in Gaza is almost double that of the West Bank. And an infant born to the poorest quintile in Gaza is twice as likely to die as in infant born into the richest quintile in Gaza.  Despite the reductions in child mortality, MDG 4 will not be reached. Indeed, Palestine had the smallest reduction in child mortality rates compared to all Arab countries. The assessment of most working in the sector is that outcomes in the sector have been disappointing and not commensurate with the funding going into the sector. Indeed, there has been an explosion of costs that would indicate scope for improving efficiency in the sector. Expenditures have risen by 150% over the past ten years (see table 15).

As noted in a report prepared by ICAI:  DFID’s Support for Palestine Refugees through UNRWA dated September 2013, the cost of health care delivered by the PA is considerably higher than that provided by UNRWA.  UNRWA performs better suggesting that the PA/Hamas has great scope to introduce efficiency reforms.

A number of issues have been identified in the sector. Several stem, at least in part, from the conflict conditions and closure policy which have, at times, restricted access to medical supplies.  These include:

- A fragmented institutional framework with effectively two ministries of health, one in the West Bank and one in Gaza. This is described in more detail in the main text;

- Unpredictable health financing and donor dependence. Also, a massive increase in recurrent health spending on salaries (doubling between 2000 and 2005). In later years, this was of course financed in large part by the EU through DFS under PEGASE.

- Each doctor sees, on average, 104 patients a day, which, without implementation of proposed reforms, will increase to 138 by 2021.

- a huge increase in treatment referrals outside the PA health system. According to data given to the mission, the PA had unpaid bills at the end of 2012 on referrals of some $180 million out of a yearly health budget of around half a billion dollars. And since 1994, the total bill for referrals has been close to $2 billion – a massive sum. This problem became even more acute when the PA cut off funds to the health system in Gaza following the election of Hamas (short of medical supplies, many more patients were sent of Gaza for treatment elsewhere);

- Inadequate financial protection from illness with about 40% of total health expenditures coming in the form of out-of-pocket household expenditures,

- Ministry of health capacity constraints and fiscal pressures so that there are often long delay in the payment of salaries,

- An increasing burden of chronic disease such as cardiovascular disease, hypertension, diabetics, etc., and finally

- A huge increase in mental health issues related to the conflict, which results in domestic violence, clinical depression and loss of productivity.  The last survey by PCBS on violence in Palestinian society (December 2011) showed an increase in all types of violence, with worrying rates of domestic violence by husbands – 29.9% in the West Bank compared to 51.1% in Gaza.

An important issue not mentioned in the World Bank report relates to that of data and monitoring of progress and results. This is well illustrated by a review mission for the USAID Health Sector Reform and Development Flagship Project (Mid-Term Evaluation). The review mission noted that “the evaluation team experienced extraordinary difficulties with developing an accurate view of the accomplishments and challenges of this large and complex project, largely because of the “public relations-oriented” reporting style and lack of substance in the written material”. Others repeated this comment in the sector:  weak reporting of results and the difficulty of obtaining hard data to assess results and efficiency of the health system.

Hospitals and health centers suffer from a shortage of specialized doctor, lack of new technologies, and outdated equipment.  Interviews noted too that there is high fragmentation in the donor community with little coordination among the donor community in the health sector;  donor interventions and policies are often not aligned with national priorities. A substantial issue that continues to be pushed off with little real effort to come to resolution is that of the reform of a national health insurance law.

Figure 16: Social Assistance as a share of total household consumption expenditures: West bank and Gaza,2004-2009 Sources:The World Bank. Targeting Assesment of the Cash Transfer Program in West Bank and Gaza. June 25, 2012.

Vulnerabilities and Social Protection. Following the election of a Hamas-led government in Gaza in 2006, the international community temporarily cut off aid to the PA, while Israel instituted a complete embargo of the Gaza strip. Public sector employees went without salaries for months and many fell into poverty. When international assistance for budget support was reinstated, poverty among public sector employees also fell. With increased aid, came increased social assistance to the poor (see figure 16). By 2009, international assistance coverage had doubled, with a staggering 71% of all Gazans becoming beneficiaries of at least one form of social assistance or another.

EU support to the social assistance sector is considerable:  support to the budget of the PA through DFS, and capacity building to the Ministry of Social Affairs.  It is implemented through a number of programs including the cash transfer program, other support, food assistance and support through UNRWA.  Interestingly, while there are a multitude of social assistance programs run by the PA, international organizations, UNRWA and NGO’s, there are relatively low rates of overlaps where households receive assistance from multiple PA sources.  Generally, this assistance, in conjunction with the World Bank, has been extremely well targeted and implemented.   These are programs for which the EU should take considerable credit.

Figure 17 Coverage by Nonsubsidy SSNs, Middle east and North Africa Relative to Other Regions

Figure 18: Benefit Generosity of Nonsubsidy SSNs, Middle East and North Africa Compared with Other Regions Source: Middle East and North Africa Author’s calculations based on national household surveys. Other regions World Bank 2012

Social assistance played a significant role as a safety net during the sharp downturn experienced in Gaza in 2007. At 6% of GDP, social assistance spending in Palestine is high by international standards. The current social assistance program is the result of the 2009/10 merger of two pre-existing programs: the Social Safety Net Reform Program (funded by the World Bank) and the Relief and Social Services Safety Net (funded by the EU’s TIM/PAGASE mechanism). As noted, it performs exceptionally well compared to other countries in the region.

The most important inidicator of socal safety net (SSN) effectiveness is the impact on povery and inequality.  As the Bank notes in its report, this indicator combines the separate forces of coverage, targeting, and generosity of the SSN programs to assess the overall effect of the presence of SSNs on the welfare distribution of the econony. With the exxception of Palestine and Jordan, the report found that the region’s SSNs have little effect on povery rates, as estimaed through a simulation of poverty in the absence of SSN’s. It also found that in Palestine, the SSN program impacts well the most poor in society (which is precisely what it is meant to do with good targeting – and little leakage).

Figure 19: Poverty and Inequality Impact of Nonsubsidy SSNs in the Middle East and North Africa, Selected Economies, c. 2005-10. Source: Authors’ calculations based on national household surveys. Note SSN=social safety net

The report notes considerably less leakage than in other countries of the region where a significant share of benefits go to the richest quintile. In Palestine (and Egypt and Jordan), only 1 in 10 SSN beneficiaries come from the top quintile showing a greater degree of targeting accuracy. Since 2009 with the creation of the unified CTP which uses a proxy means test targeting mechanism and a unified payment mechanism, targeting performance has improved further. The Bank report notes that the CTP is poised to become one of the most advanced cash assistance programs in the Region.

While there is no doubt that the CTP is well targeted and generally well run, the actual impact of the program at the individual level is somewhat open to question.  The AETS Consortium report “Impact Evaluation of the EU Contribution to the Palestinian Cash Transfer Program in the Framework of the PEGASAE Program to Support Vulnerable Palestinian Families”, July 2013, findings note that:

“…., in the West Bank, we observed that for key measures from MOSA’s logframe, including child health, major depression amongst adults, electricity cuts, and total per capita expenditures, intervention and comparison households are not statistically different.  This suggests that either the assistance received in the framework of the CTP has positively impacted the intervention group or that there are no between-group differences at baseline.  In Gaza, we found statistically significant differences favoring the intervention group for income and total per capita expenditures, but not for other measures.  This suggests that while households had cash transfer income, they may still have lacked the resources need to yield positive impacts”.

One part of the Palestinian social security system that has not received adequate attention is the pension system. This system is among the most generous in world for a society with Palestine’s level of income and it is insolvent. It is effectively being operated as a “pay as you go” system, where current contributions fund the cost of retirees instead of being built up to support future retirees. Due to its unique history, there are four different pension schemes operating in WB&G, including those inherited from Jordan and Egypt. However, the older three are being phased out and all new employees in both the West Bank and Gaza fall under the same scheme. But even this scheme is not properly funded and is in arrears.

The pension system remains unsustainable with projected revenues insufficient to meet obligations.  As noted in the May 2010 Progress Report there has been no progress in the adoption of an action plan for reform of the pension system. The PA maintained that it was working on a pension reform action plan but little or no progress has been noted.  This has real potential to undermine the long-term sustainability of the PA.

Figure 20: Household Food Insecurity and food Security Levels by Refugee and Non Refugee West Bank and Gaza strip, 2009-2012 Source:Socio-Economic and Food Security Survey, West Bank and Gaza, 2012

Food Security. The results of a 2012 survey on food insecurity depict a harsh situation.  Over 34% of Palestinian households – approximately 1.7 million individuals – were found to be food insecure. This figure is seven percentage points higher than the 2011 figures, which represents a complete reversal of the progressive improvements in food insecurity reported since 2009.

The report notes that the surge in food insecurity mainly reflects the deterioration of socio economic conditions resulting from the combination of sustained economic constraints and of the shock generated by the PA fiscal crisis in late 2012.  The disturbingly high levels of food insecurity in Gaza can be explained primarily by the prolonged blockade, which continues to prevent any meaningful recovery of the local productive economy. According to the report, lifting the blockade and easing the West Bank access restrictions remain the most critical factors affecting food insecurity.  Addressing the symptoms of food insecurity rather than tackling the root causes will not lead to sustained improvement. The report goes on to explain that, in the context of rising food insecurity and limited financial resources, needs-based targeting should be further strengthened.

The below figures are very stark. That said, data on wasting and stunting as discussed above, show very little evidence of either in Gaza or the West Bank. There thus appears to be something of a contradiction in the data. Most likely the trend data show correctly the deteriorating situation but the absolute numbers of insecure may be overstated

Figure 21: Household food security levels in the Gaza Strip, 2009-2012 Source:Socio-Economic and Food Security Survey, West Bank and Gaza, 2012

EU payments of salaries in the social sectors. The largest share of government expenditures goes to wages and salaries, which were about US$1.75 billion in 2012 or 54 percent of expenditures. This underestimates the true cost of the payroll. Transfer payments, which include a substantial amount of pension payments, were another nearly US$700 million. Combined wages and salaries and transfers accounted for about three quarters of the PA’s recurrent budget in 2012.

As noted in many EU documents (see for example “PEGASE programmes of Direct Financial Support to the Recurrent Costs of the PA dated 31 August 2103), PEGASE has five main components. The first two of these impact directly on the social sector:

- Salaries of PA civil servants and pensioners to ensure that essential public services keep operating, and

- Social allowances to Palestinian households living in extreme poverty for the Cash Transfer Program

A third component relates to the payments of arrears to East Jerusalem hospitals and thus also impacts on the social sector related as it is to referrals. The EU pays about 29.1% of the civilian wage bill and directly supports around 66,000 active civil servants such as teachers and health workers.  Around 10,000 pensioners, paid directly under the PA budget, are also eligible to and benefit from EU support. As noted in the Desk Report, up to 70% of total DFS and UNWRA allocations go to the social sectors. Salary payments, which go directly from the EU to Palestinians (without passing through the PA), make up the lion’s share of this. With such a significant share of PEGASE funding directly paying the salaries of so many health and education workers – and DFS is not budget support as it goes directly into the pockets of designated PA staff -- salary payments and the social sectors are inextricably linked. The EU Representative Office in Jerusalem in its draft progress report 2014/15:  Single Support Framework notes the overall objective of PEGASE support is to maintain the viability of the two-state solution by avoiding the fiscal collapse of the PA. There is no doubt that PEGASE has helped achieve this objective but not perhaps long-term sustainability which is linked of course to the size of the Government sector and affordability. The number of PA employees has been growing rapidly over the years:

Figure 22: PA staffing 1994-2013

* Data for 2013 is as of September.  Source:  World Bank.

Justice, Democracy and Human Rights Background

The main obstacles to political reform in Palestine and the rule of law remain the conflict with Israel, the existence of two legal systems in the same territory applied according to community, periodic external interventions including a resulting donor dependency and the internal political and physical split between WB and GS.

Democracy: Democracy, as a means for Palestinian national self-government has been largely aspirational, not realized, despite the declarations of the peace process agreements, the international community, the PDP and PNDP since the establishment of the PA in 1994. Palestinian demand for democratization, frustrated by the failure of elections in 1998-1999, persisted through the Second Intifada and emerged clearly in 2005 as the preference of the majority of Palestinians over any other governance system.

Despite the cleavages of 2006-2007, democratization also remained a declared priority of the PA which in 2009 declared “The formation of a democratically-elected leadership that enjoys popular and factional support, as well as regional and international recognition”. Nevertheless, although democratization was strongly supported by several donors, including the EU, and despite demonstrated PA capacity to hold elections in line with international standards, there has been no progress towards re-establishing a national participatory democratic process. No elections, other than a few local elections in 2012, have been held since 2006. Hence, the Palestinian Legislative Council (PLC) remains paralyzed. While laws and regulations continue to be issued by Presidential Decree, the democratic legitimacy of the PA as well as the Hamas authorities in Gaza continues to decrease in the absence of national elections. Holding national elections across Palestine remains a priority precondition for the reinvigoration of democratic legitimacy, institutional sustainability and the reinforcement of good governance.

Justice. The administration of justice is central to Palestinian civic life. Palestinians face an unequal, dual system of governance and justice. Within the Palestinian community, access to justice has improved since 2008 but Palestinian judicial administration remains fragmented with consequent uncertainties which in turn undermine credibility of the rule of law.

To build institutional capacity to address some of the many  challenges faced by this sector, the EU’s programme “Empowering the Palestinian Judiciary” has sought  to respond to priorities of the judiciary reform in line with the Palestinian National Justice Sector Strategies 2008-2010 and 2011-2013..While these programs have made progress, the lack of a duly elected legislature, the expiry of the legal terms of the PA executives and budgetary uncertainties have perpetuated a lack of clarity.

The PA’s commitment to integrity and accountability have been advanced by a 2005 law to combat illegal gains, amended in June 2010, and leading to the establishment of a new anti-corruption commission. Ongoing progress is evidenced by internal audit reforms, the work of the Audit Committee and enhanced capacity for fraud prevention. However, the anti-corruption commission has not yet become significantly and visibly operational.  Surveys indicate that the Palestinian public continue to believe that nepotism, cronyism, favoritism in services and job appointments, abuse and misuse of public property remain unpunished. These attitudes in turn further undermine institutional progress and legitimacy.

Human rights. The human rights situation remains a matter of high profile concern, particularly in the Gaza Strip, but also in the West Bank. In 2012, there was some progress on human rights issues such as the development of a PA national action plan for human rights and the removal of security clearance as a requisite for public sector recruitment. Yet various human rights violations, particularly freedom of expression and assembly, denote an overall narrow democratic space. There was also an increase in alleged human rights abuses by the security forces. Human rights defenders in Palestine have benefited from various international efforts including the European Initiative for Democracy and Human Rights. However, human rights oriented NGOs have criticized the absence of focus on accountability in the ENP progress report for Palestine 2012,  calling upon the EU to ensure that it is a priority in EU-PA relations, including in the implementation of the 2013 Action Plan.

Environmental profile

Water. Water is one of the factors which most influences life in the Middle East and is one of the major problems in the Palestinian-Israeli conflict since it constitutes a fundamental geostrategic issue for subsistence in the area. The Israeli occupation strongly influences the Palestine water situation both in terms of access to the available water resources, and by limiting the Palestinian National Authority’s capacities to actively improve the situation (e.g. construction of wastewater treatment, drilling of wells, construction of sewage and wastewater treatment infrastructure). Pressures on water availability include population growth, growth in agricultural and industrial production, as well as general economic development.

Figure 23: Groundwater flow and divide Source: Adapted from Palestinian Academic Society for the Study of International Affaires (PASSIA)

Surface water resources: Although the rainfall in the region is fairly abundant - yet irregular and much concentrated in time and space - there are currently few surface water resources in the West Bank, and none anymore in the Gaza Strip, where the main wadis (Gaza Wadi) has been dried up by upstream water abstraction. Most of the wadis flow only for a few weeks a year, usually as flash-floods after thunderstorms, and this resource is hard to use and capture as, in most valleys, the complicated geological/ geographical features complicate the construction of large storage dams (few plains, karstic limestone substratum).

The main permanent surface water resource on the West Bank is the Jordan River, which is used heavily for irrigation and domestic water supply by Israel. Since 1967 the Palestinians do not have access to this resource. It is a trans-boundary resource, shared between Jordan, Syria, Lebanon, Israel and Palestine. The integrated management of this resource and the conclusion of a basin wide agreement is a key component of any long-term strategy.

Gaza and the West Bank rely on groundwater resources for more than 95% of their water needs come from this source either by wells or springs. The total renewable groundwater resources have been estimated as 578-814 Mm3/year in the West Bank and around 55-60 Mm3/year in the Gaza Strip. In the West Bank, groundwater resources are contained in deep (karstic) limestone and dolomite aquifers and the aquifer system is classified according to flow direction into three main groundwater basins, namely the Western Aquifer, the Northeastern Aquifer and the Eastern Aquifer system (map). Most large production wells are 200-800 meters deep and the water table lies between 100 and 450m below the surface.

These aquifers are commonly divided into three main aquifers-Basins (Western, Eastern and North-Eastern). The Western and North Eastern basins flow to Israel where it constitutes one of the main groundwater resources. In Gaza, groundwater resources are contained in a shallow sandy aquifer, extending eastward to Israel and southward to Egypt. There are more than 5,000 water wells, most of them are for agriculture purposes with an average depth of 40-70 meters and the water table lies between 20-50m below the ground surface. Gaza is a dry area and the local aquifer recharge is very limited (55-60 Mm3/year on average). Abstraction by all users (Israelis, Egyptians and Palestinians) already far exceeds natural recharge. Consequently, the aquifer has been depleted and suffers from seawater intrusion.

Besides the fact that the Wall consumes Palestinian land and restricts access and movement, the construction of the Wall in the northern part of the West Bank has the effect of a concrete dam that retains the water, preventing it from flowing westward, and causing floods in the neighbouring areas. Moreover, the route of the wall is an obstacle to essential water resources of the Palestinian population, since a great part of the western aquifer recharge area will be trapped between the wall and the Green Line and, consequently, will fall under Israeli control. One of the most important consequences of these limitations caused by the Wall’s construction is that Palestinian farmlands do not get water. Consequently, after over three years the uncultivated Palestinian lands became Israel’s property and were confiscated from the private owners. In this manner, water use restrictions by the separation Wall’s zone can be used as a tool for land annexation.

Table 3: Recharge estimate for the main aquifers (source PWA, 2012)

| Aquifer-Basin | WB area (km2) | Average rainfall (mm) 2010/2011 | Recharge 2010/2011 (Mm3) | Long-term* Average Recharge (Mm3) |
| --- | --- | --- | --- | --- |
| Western Aquifer | 1,767 | 407 | 311 | 318-430 |
| North Eastern Aquifer | 981 | 433 | 134 | 135-187 |
| Eastern Aquifer | 2,896 | 281 | 153 | 125-197 |
| West Bank Total | 5,644 | 347 | 598 | 578-814 |
| Coastal Aquifer | 365 | 225 | 33 | 55-60 |
| Palestine Total | 6,009 km2 |  | 631 | 633-874 |  |

*PWA assessment

There is one seawater desalination plant located in the middle area of Gaza Strip (Deir El Balah) with a capacity of 600 m3/day by using two beach wells, that will be expanded to about 2000 m3/d by the year 2014. A large seawater desalination plant with a capacity of 50 Mm3/year, as a first phase, is scheduled to be constructed by year 2017 and to be located in the central part of Gaza Strip. In addition, there are 8 groundwater desalination plants operated by the CMWU in the southern parts of the Gaza Strip (Khan Younis- Deir Al Balah and Rafah) whose water is distributed through the domestic distribution networks, which is mixed with well water (total capacity of 1 Mm3/year).  It must be noted that the desalinated seawater facilities impact significantly on the water tariff due to their high needs in energy.

In the Gaza Strip there are about one hundred water vendors selling drinking water produced through brackish water desalination plants with a capacity of 20-40 m3/day and operated for 4-6 hours/day, with total supplied quantities of 2.8 Mm3/year. More than 80% of the Gaza people use this water for fulfilling their drinking and cooking water needs. The remaining 20% use in-house reverse osmosis units for desalination. Small pilot desalination projects for Brackish Water exist mainly in the Jordan Valley established by the private sector with a total capacity of less than 0.5 Mm3/year and are used mainly for agricultural purposes.

The reuse of treated wastewater remains up to now as small pilot projects in scattered areas with total reuse quantities of around 1 Mm3/ year. There are very few activities or projects for reuse (small scale projects on community level are implemented such as Anza, Attil, Kharas). Additional water resources will become available through the scheduled developments of wastewater treatment plants and this potential resource could be relatively large, but its development raises some important issues that are yet to be resolved.

Water resources availability between West Bank-Gaza (WBG) and Israel shows a large discrepancy, with fresh water per capita in Israel about four times that of WBG. Whereas Israel is known for efficient water infrastructure and management, Palestinians are struggling to attain the most basic level of infrastructure and services of a low-income country. In the Gaza Strip, scarcity and overuse reach critical levels which result in the intrusion of seawater into the Coastal Aquifers and a consequent deterioration in water quality. The West Bank, with groundwater abstraction being within sustainable limits, suffers from the uneven distribution of water between the Palestine, Israeli settlements and green-line Israel, rather than from absolute water scarcity.

Currently, Israel consumes about 2,000 MCM of water for all uses when only 1,700 Mm3 are available. This generates an annual water deficit of 300 Mm3 that is essentially covered by the overexploitation of aquifers and the River Jordan. This overexploitation of the aquifers produces a progressive salination process and will probably be accentuated in the future as a consequence of the continuous water abstraction for consumption.  The West Bank controls and consumes about 20% of groundwater resources (138 Mm3), while Israel controls approximately 80% of these resources (562 Mm3) to meet 25% of its water needs.

This imbalance is reflected in the per capita water consumption. In the West Bank the water available per capita range around 103 l/inhabitant/day and Israel consumes approximately 293 l/inhabitant/day. Inadequate maintenance of municipal water systems has led to the deterioration of water services and some parts of the Palestinian population therefore rely on tankers to deliver water. This water does not necessarily meet the required water quality standards, despite increasing water prices.

Table 4: WATSAN facilities coverage (2011) and national targets (2013)

| Indicator | 2011 | 2013 Targets |
| --- | --- | --- |
| % of households connected to clean water supply | 88.4% | 95% |
| Per capita water consumption (litres/day) | 80 | 84 |
| % of households connected to sewage network – WB/GS | 35,5% / 83,3% | 65% / 92% |
| % of households connected to solid waste collection services | 80% | 97% |
| % of total solid waste disposed in sanitary landfills | 22% | 90% |
| % of treated wastewater reused | 1% | 30% |
| % of solid waste recycled | 5% | 20% |
| % of losses from leakage from water network | 37% | 25% |
| % of existing sanitary landfill operating costs covered by revenues | 80% | 100% |

Source: National Development Plan 2011-2013 – Establishing the State, Building our Future – April 2011

Table 5 : Quantity of water supply and daily allocation per capita, 2012

Wastewater. A key problem related to water is the pollution from wastewater and associated public health impacts due to polluted and standing waters. The wastewater treatment plants in Palestine are inadequate to serve the amount of wastewater being generated, with 58% of total generated wastewater being discharged without treatment to the environment (PWA 2011). There is at this stage no proper wastewater treatment in the West Bank. On the whole, only 5% of all wastewater is treated adequately, the rest is discharged into the environment without treatment. As the West Bank is the area of recharge for its aquifer system, the direct discharge of untreated or partially treated wastewater into open areas endangers the groundwater quality. In Gaza, three wastewater treatment plants exist but these operate well above their capacity and are in need of upgrade and maintenance, and therefore do not function effectively. Most of the networks receive industrial wastewater resulted from several industries such as, food industry, dairy industry, quarries, olive oil mills, textile factories and car wash garages. However, a few quantity of the industrial wastewater is being pre-treated before being discharged into the public sewage network.

Appropriate treatment of wastewater has been neglected (both from Israel and PA) and little investment has been made in the field of wastewater treatment since the Oslo Accords. Only 6.3% (2,836 MCM) of the generated wastewater in the West Bank is treated in a centralised and collective wastewater treatment plant, the remaining 93.7% being discharged untreated into the environment.

The lack of effective wastewater treatment leads to deteriorating nature, biodiversity and groundwater quality while it endangers public health. The improper treatment of sewage and wastewater remains the single most detrimental factor behind the spread of infectious and parasitic diseases in many Palestinian communities. The flooding of collection systems (cesspits, open channels, and pipelines) can result in spillage of raw sewage in residential areas, encouraging the spread of pathogens and insect breeding. This causes public health risks through direct exposure, as well as the reuse of untreated wastewater on irrigated lands. The pollution of the water aquifer in Gaza has the potential to significantly damage the drinking water for almost 1.5 million Palestinians. The most common waterborne diseases found include Amoebas, Hepatitis A, and blue baby syndrome.

Table 6: Volume of treated wastewater in the West Bank (source ARIJ – 2013)

The Israeli occupation prevents an effective management and operation of wastewater treatment infrastructure in Palestine, including the maintenance of existing and construction of new infrastructure. Since the current governance system under the Oslo Agreement requires the Israeli approval of any proposed management measure or infrastructure project related to water and wastewater, and since the Israeli authorities have withheld this approval in several occasions, an integrated planning and management of water and wastewater infrastructure is essentially impossible.

Solid Waste. Municipal Solid Waste (MSW) is a significant contributor of environmental and health-related problems in Palestine with waste management being still at its infancy. Existing waste infrastructure are deteriorated and only limited development of new infrastructure take place. There are only few sanitary landfills built to international standards, while the majority of the waste is still dumped on random dumpsites, which lack proper management or monitoring. This results in a number of environmental and health problems, such as increased air pollution, continued degradation of nature and biodiversity including increased salinity and heavy metal concentrations in the soil, an aesthetic distortion of the visual environment, and an overall lower quality of life for the Palestinian population. In most cases, neither the location nor the set-up of the dumping sites is selected in accordance with minimal environmental, health or economic considerations.

Most solid waste dumping sites are unlined, which causes leachate to seep into the ground and may pollute the groundwater aquifers. Solid waste is also often burned on the site to reduce the bad odours, thereby adding to air pollution by leading to emissions of acidifying and greenhouse gases. Biological degradation of remaining unburned organic waste adds to their emissions by generating landfill gases. Burning medical waste may pollute air with various heavy metals, especially cadmium, mercury, and dioxins that form through burning PVC.  Effective waste management is also hindered by the geographical discontinuity of land under Palestinian control (most clearly evidenced by the segregation wall). Finally, both Israeli settlements and Israeli industries in the West Bank are reported to release solid waste into the surrounding Palestinian environment without effective controls or restrictions.

Air Quality. Air quality is not regarded as the most pressing issue. This perception is due to the fact that there is no power generation in the West Bank, and only one oil-fired power station in Gaza. Heavy industry is virtually absent both in the West Bank and Gaza. However, there are sources of air-borne emissions, such as the transport sector (in particular due to the aged fleet or cars and trucks), which is estimated to contribute about 40%-50% of the observed air pollution. Further sources are the widespread unmanaged burning of solid waste, as well as dust emissions from stone quarries and stone crushing facilities (stones being one of the Palestine most important export products).

Water and Sanitation sector Governance. The Palestinian Water Authority (PWA) is the regulatory body for the water sector in the Palestinian Authority (PA). Its duties include the communications with the Israeli side and the management and distribution of the water resources in Palestinian areas. Other institutions working in the water sector in one form or another with the PWA are:

- Ministry of Agriculture (Environmental Quality Authority EQA);

- Ministry of Local Government (Association of Water Service Providers);

- Ministry of Health;

- Ministry of Industry;

- Water Consumers Association;

- Regional Water Institutions (WB Water Department, Coastal Water Authority, Jerusalem Water Undertaking);

- Local universities, environmental and research centres;

- NGO’s.

The private sector role is restricted to only executing infrastructure water sector projects.

The Israeli control over Palestinian water resources is sustained by numerous laws and regulations, military orders, restrictive bureaucracy and other limitations which have led to a structural imbalance between the two sides. In 1995 the Oslo II agreement (Art. 40) contained provisions on water and sewage that recognized undefined Palestinian water rights, and returned some West Bank water resources and services responsibility to the PA.

Essentially Article 40:

- Set governance arrangements for a five year interim period, notably a Joint Water Committee (JWC) to oversee management of the aquifers, with decisions to be based on consensus between the two parties;

- Allocated to either party specific quantities of the three West Bank aquifers underlying both territories - the share allocated to the Palestinian West Bank was about one quarter of the allocation to Israel and the settlements;

- Provided for interim extra supplies from new wells and from Mekorot - an extra 28.6 MCM was to be allocated to Palestinian needs;

- Estimated “future needs” for the Palestinian West Bank at 70-80 MCM.

The Oslo Accords divided the West Bank into three geographic areas: A, B and C. This territorial administration is also relevant in terms of water management within the West Bank. In Areas A and B, springs and wells to access groundwater are mainly under control of local Palestinian municipalities and private Palestinian owners. In Area C, the full control of water infrastructure (wells) and natural springs is under Israeli control. Article 40 of the Oslo Accord did not acknowledge the excessive allocation of water to the Jewish settlements and have far underestimated the amount of water available to the Palestinians. Both the projected population growth and the expected supply of water from different aquifers were miscalculated. Moreover the calculations were based on limited access to water data especially concerning extraction from the Eastern Aquifer (West Bank).

The over-exploitation of water resources available and the lack of infrastructure to manage them were issues that were not addressed in the negotiations. Moreover, the lack of regulation on the access to water for Jewish settlers made the procedures for extraction more complex and less sustainable. International investment strategies in the water sector were developed in order to address the short-term needs of the population as a way to delay a potential water crisis. No clear long-term strategy was developed by international donors or by the Palestinian Water Authority (PWA) concerning the drilling of new wells and sewage disposal.

Table7: Allocation of water from the main groundwater aquifers in the oPt

| Acquifer | Potential (MCM/year) | Palestinian allocation* (MCM) | Proposed Palestinian allocation *** | Palestinian abstraction 2008 (MCM) |
| --- | --- | --- | --- | --- |
| Eastern | 172 | 74.5** | 172 (100%% of 172) |  |
| Northeastern | 145 | 42 | 116 880% of 145) |  |
| Western | 362 | 22 | 181 (50% of 362) |  |
| Total/year | 679 | 138.5 | 469 | 91.50 |

*According to Article 40 (Oslo II Agreement, September 18, 1995)

** Including extra 20.5 MCM of “immediate needs” to be developed for Palestinina use from Eastern Aquifer

***The proposed allocation was considered according to the aquifer location and recharge area

Source: Palestinian Ministry of National Economy, September 2011, on the basis of World Bank (2009)

Source: Palestinian Ministry of National Economy, 09/2011 & World Bank (2009)

An obstacle to the efficient operation of the PWA is the power imbalance between Israeli and Palestinian actors. PWA departments responsible for licensing or permits are controlled by the Joint Water Committee (JWC) and needs its approval for every suggested project. For the purpose of coordination, a Joint Water Committee (JWC) and several Joint Supervision and Enforcement Teams (JSETs) were established under the Oslo II Agreement. The JWC was supposed to act as an overall regulatory body and every water infrastructure development project in the West Bank (Palestinian or Israeli) needs to be approved by this coordinating body. This includes every pipeline greater than 5 cm diameter and 200 m length, every well that needs constructing or rehabilitating.

Figure 24: The Procedure of licensing water projects in the JWC

Even though the provisions of Article 40 aim to ensure equality and cooperation between the two parties, the Palestinian party and international entities have criticized the current arrangements in the JWC as one of the causes for the inability of the Palestinian people to exercise their right to water. Most often, criticism of the JWC focuses on several arguments:

- The mechanism set forth in Art 40 and especially the consensus requirement, provides the Israeli members of the Committee with a de facto veto right on all of its resolutions. Because Israel enjoys water allotment from West Bank sources in sufficient quantities to supply the needs of the Israeli settlements it is the Palestinian population which is more often in need of obtaining the approval of the JWC.

- Reportedly, Israel often conditions permits for Palestinians on reciprocal approval of development of water sources for settlements, an arrangement the Palestinian side has rejected so as not to legitimize them.

- Since Israel is also the residual downstream beneficiary of the Western and North-Eastern Aquifers, it lacks the motivation to approve projects that will increase Palestinian extraction of water.

- The most significant projects approved by the JWC are the improvement of existing water systems, rather than creating additional water sources for the Palestinian population – most of which are rejected. According to the World Bank, 202 applications for drilling wells have been filed over the years, out of which the Joint Committee has approved only 65 applications (32%). Moreover, since the implementation of projects approved by the JWC for Area C require a permit from the Israeli Civil Administration, only 38 of the 65 approved applications have been implemented (equalling only 19% of the total applications), after the Israeli Civil Administration approved and completed planning and relevant proceedings.

- The frequency of the JWC’s meetings is influenced directly by the political situation, and its meetings are scarce and insufficient. In the first years after signing the agreements, the Committee met on average ten times a year. Commencing in 2002, the annual average number of meetings is three meetings, while in 2008 only one meeting was held.

- Article 40 allowed Israel to continue enjoying the water sources in the West Bank, including exclusive use of the Jordan River, and at the same time prevented an increase in the Palestinian extraction of water, in spite of increasing needs.

- More than once, the granting of approval by the Israeli Civil Administration to the implementation of a wastewater treatment plan was subject to the connection of adjunct settlements to facilities funded by NGOs or the Palestinian Water Authority, adding financial constraints on the execution of such plans, and compromising their humanitarian nature.

In conclusion, the mechanism created by the Interim Agreement in the form of the Joint Water Committee has perpetuated the exclusive control of Israel over the water sources of the West Bank, and limited Palestinian access and ability to develop new water sources. Moreover, Palestinian water sources in Area C are subject to additional scrutiny and supervision of the Israeli Civil Administration which exercises its authority to approve or deny construction work in a manner that strengthens Israeli control over the West Bank.

Palestinians are systematically denied building and/or drilling permits for water structures, while Mekorot is allowed to drill into water sources in a manner that dries out existing wells that serve the Palestinian population. As a result, Palestinians extract about 20 per cent of the estimated potential of the Mountain Aquifer, while Israel extracts the balance, and overdraws on the estimated potential of the aquifer by more than 50 per cent. In addition, settlement activity around springs, and over-extraction of water from the Mountain Aquifer by Israel have led to dramatic decline in discharge in recent years, as well as restrictions on Palestinian access to water. As a result, Palestinian water consumption in the West Bank barely reaches 70 litres a day per person, while water consumption in Israel and the Israeli settlements reaches four times that much. The World Health Organization’s (WHO) recommended minimum of daily water consumption is 100 litres per person.

Between 1995 and 2011 the Palestinians submitted 30 wastewater treatment plant projects for approval of the JWC. Only four of these projects have been accepted. In 2011 the PWA submitted a total of 38 projects to the JWC. Of these 3 were approved in 2011. These were fast track projects, which should have been approved in 2010 as part of a list of agricultural wells in need of rehabilitation. That’s an approval rate of 7.8%. The PWA observed that Israeli bureaucratic constraints have caused some donors to withdraw and as a result current investment in the West Bank water sector is one tenth of planned levels. The impact of these delays and bureaucratic obstructions have made it difficult for EWASH agencies to adequately respond to needs of the population.

Figure 25: JWC approval rate by type between 1995-2008 Source : Dr. Jan Selby 2012 - This chart combines information on JWC and Israeli Civil Administration approval, as projects proposed for Area C require Israeli Civil Administration approval as well.

Besides the administrative measures, the complex legal system issued by the Military Commander functions as a codification of control as well as an institutional framework of the occupation. From the beginning of the Israeli occupation, with not more than three Military Orders, Israel has created a “mechanism of total control” over water in the West Bank. Shortly after the June 1967 War, Military Order 92 transferred full authority over all water concerning issues in West Bank and Gaza Strip from various local utilities to an Israeli official appointed by the area military commander. Moreover, Military Order 158 introduced a permit system for all water projects.

The combination of Military Orders No. 92 and 158 gives the Israeli authorities complete control over the entire water supplies in the West Bank and Gaza. Only the Head, appointed by the Area Commander, has influence in any issue regarding « transportation, extraction, export, consumption, sale, distribution, inspection of its use, purification, allotment of shares, the establishment of water projects, measurement, prevention of contamination, carrying out of studies and measurements in anything that deals with water matters, drilling wells, hearing of objections and all proceedings dealing with any of the above laws, etc., fixing and collecting fees, taxes and any payments for any of the above and any other matter which has not been mentioned specifically above which deals in any way whatsoever with water subjects ». For example, Article 4(A) of Order 158 specifically states that « it shall not be permissible for any person to set up or to assemble or to possess or to operate a water installation unless he has obtained a license from the Area Commander ». Thus the law prohibited the construction of any new or reconstruction of old water infrastructure without a permit from an official appointed by the area military commander.

The military order also provided this Israeli official with the right to refuse a permit without a justification and no mechanism was established to appeal the official’s decisions. Lastly, Military Order 291 declared all water resources to be the property of the State of Israel. In this way the military orders ensured full control of state-owned natural resources and built up the legal system for issuing drilling permits and extraction rates for Israel.

Destruction of Humanitarian Aid. Lacking any alternative, communities as well as humanitarian agencies, are left to proceed without the required construction permits. EWASH estimates the cost of demolished infrastructure in the West Bank to have exceeded 100,000 USD in 2011 alone.

In October 2011, a member of the European Parliament asked the European Commission for details regarding the destruction of EU-funded development projects in the OPT between

2001 and 2011. In response, the European Commission made public a list of « physical damages inflicted by Israel Defence Force attacks on EU-funded development projects » and further elaborated that « the total cost of physical damage inflicted by Israeli armed forces attacks on EU-funded Development Projects amounted to approximately EUR 49.14 million for the period from 2001-2011, with the estimated EU-funded share in the loss amounting to EUR 29.37 million»

Following the destruction in January 2008 of trees, retaining walls and fencing co-funded by the EC near Beit Ula, close to Hebron, the Commission wrote on 21 February 2008 to COGAT (Coordination of Government Activities in the Territories) requesting details and clarifications. Despite the sending of subsequent letters, and various meetings, no reply to the Commission's letter had been sent by the Israeli authorities by 19 March 2009. The Commission recognises that armed hostilities have a very serious effect on development, and result in a loss of both human and fixed capital. Most assessments of damage to infrastructure following hostilities are carried out on a general basis and do not identify the separately any damage to the projects which may have been financed by individual donors. Typically, such assessments form the basis of a needs assessment, which gives a very approximate estimate of the cost of reconstruction and which donors can use to decide on a possible contribution to a reconstruction exercise. The Commission entered into a trilateral joint declaration with the World Bank and the UN in September 2008 in relation to a common platform for carrying out such post-crisis needs assessments.

As for the Occupied Palestinian Territory, following the Operation Cast Lead (December 2008- January 2009), the Commission carried out a comprehensive needs and damage assessment, including an evaluation of the destruction of EU‑funded projects. According to this evaluation EU‑ funded projects (EU Member States and EC projects included) were damaged for an amount of over EUR 12.3 million during this conflict. This should be compared with an estimate of overall damages to EU‑funded projects in both the West Bank and Gaza for an amount equivalent to EUR 39.6 million since 2001 (including also the Operation Cast Lead damages).

Article 53 of the Fourth Geneva Convention prohibits the Occupying Power from destroying all property, whether public or private, situated in the occupied territory for any reason other than imperative military necessity. While imperative military requirements may permit the Occupying Power to carry out destruction, in whole or in part, of certain private or public property in occupied territory, it must act in good faith to interpret the provision in a reasonable manner that respects the principle of proportionality. In these instances, this principle must be applied restrictively as the military necessity has to be absolute.

Destruction of enemy property not justified by military necessity constitutes a war crime. This crime amounts to a grave breach of the Fourth Geneva Convention when carried out unlawfully or wantonly, and when extensive in nature. The ostensible administrative nature of Israel’s destruction of water infrastructure makes it apparent that such destruction is not justified by military necessity, thereby constituting prima facie evidence of its unlawfulness. Furthermore, while it has been argued that the Occupying Power’s responsibility to ensure and maintain public order and civil life includes the exercise of administrative powers, such powers must be exercised. In violation of its duty of good governance, Israel has rendered any reasonable access and use of water resources in the OPT practically impossible for the occupied population. Seen in this light, the current practice of demolishing water infrastructure, premised on the specious lack of permits, is a clear abuse of the obligation to administer the occupied territory for the benefit of the occupied population.

Israel perspective. According to some Israel reports, the international community has been wilfully misled by Palestinian propaganda on water issues. It is not the Israeli occupation policy but the Palestinian political resistance against joint management and cooperation that is responsible for the relatively slow development of the Palestinian water sector and the deteriorating human rights situation in the Palestinian Territories and there is convincing evidence of mismanagement within the Palestinian Water Authority.

Although the PWA embarked on an institutional reform process in reaction to international critics such as the World Bank this did not solve the issue of mismanagement within the institution. The PWA also did not manage to gain control over many municipalities (where Israel has no control) due to the autocratic and undemocratic manner in which they are managed. These power holders did not want to loose control of the water systems since it was one of the main services provided by the municipalities. As a result the water supply is not centralized and illegal drilling is rampant.

The Palestinians claim political and legal ownership over the groundwater reservoir of the Mountain Aquifer, including its three internal basins – western, eastern and northern. They also claim rightful access to the waters of the Gaza Strip Coastal Aquifer and the Jordan River. Quantitatively, these demands amount to about 400 million cubic meters per year (MCM/Y) from the Mountain Aquifer, about 100 MCM/Y from the Coastal Aquifer and about 200 MCM/Y from the Jordan River. This totals roughly 700 MCM/Y, which is more than 50% of the total natural water available between the Mediterranean Sea and the Jordan River. The Palestinians' on-going drilling of unauthorized wells in the Mountain Aquifer is a clear breach of the Oslo II water agreement. By 2005, more than 250 such wells were drilled in Judea and Samaria (West Bank), specifically in the western basin near Qalqiliyah and Tulkarm and in the northern basin near Jenin, providing about 10 MCM/Y. Consequently, the Israeli extraction of groundwater from all three sub-aquifers has been reduced by the same amount in order to prevent the groundwater table from dropping below the sustainable level, which would deteriorate the water quality by salinization. In addition, the Palestinians have in some instances hooked themselves up to Mekorot water pipelines without permission. In the villages of Sair and Ash-Shuyukh, for example, the unlicensed water connections are used to irrigate fields at the edge of the Judean desert. The consumption from these connections totals about 3 MCM/Y.

In the Oslo II Agreement, Israel stated its recognition of the water rights of the Palestinians, which would be quantitatively defined in the future in the permanent agreement. Both parties concurred that the future needs of the Palestinians would be about 70-80 MCM/Y more than their existing water consumption (118 MCM/Y in 1995). During the interim period, the Palestinian consumption would increase by 28.6 MCM/Y (including the 5 MCM/Y to Gaza), most of which would be supplied from the Eastern Aquifer basin. It was also agreed that new water sources should be developed (for example, sewage recycling and seawater desalination) and that management of water sources must be coordinated. As well, both sides agreed to prevent contamination and treat sewage effluents.

Over the last 15 years, the development of water supply systems for the Palestinian communities has been carried out on an extensive scale, much larger than that was called for in the Interim Agreement. In practice the Palestinians' water supply increased by about 50% (60 MCM/Y in 2006, not including Gaza), reaching a total of 180 MCM/Y and Israel has fulfilled its signed obligations. When examining water consumption among Israelis and Palestinians, only ‘fresh, natural’ water sources, which are under dispute, are considered. Treated sewage and desalinated seawater are artificial sources, which both sides can produce, and are not part of the fresh, natural water supply.

Table 8: The changes in Israeli and Palestinian water consumption over 40 years

| Year | Israel |  |  | Palestinian in Judea & Samaria |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Population | Natural water amount (MCM/Y) | Per capita consumption (m3/y) | Population | Natural water amount (MCM/Y) | Per capita consumption (m3/y) |
| 1967 | 2,776,000 | 1,411 | 508 | 700,000 | 65 | 93 |
| 2006 | 7,117,000 | 1,211 | 170 | 1,400,000 | 180 | 129 |

Figure 26 : Amount of water supplied to the PA since the 1995 Interim Agreement Source: The Begin-Sadat Center for Strategic Studies - BAR-ILAN University- Mideast Security and Policy Studies No. 94 - The Israeli-Palestinian Water Conflict: An Israeli Perspective - Haim Gvirtzman - January 2012 (p.8)

In 1967, Israel's total water consumption was 508 m3 per capita per year (m3/c/y), while that of the Palestinians was 93 m3/c/y. By 2006 the gap had significantly narrowed to 170 m3/c/y for Israelis and 129 m3/c/y for Palestinians. Since 2006, these trends have continued due to the drilling of 15 new wells for Palestinian consumption that produce 15 MCM/Y. The current per capita consumption is 150 m3/c/y for Israelis versus 140 m3/c/y for Palestinians. The significant increase in Palestinian per capita water consumption over the last few decades is a unique phenomenon. While general global trends indicate a decrease in per capita consumption over time due to population growth and deterioration of water resources, the Palestinians exhibit the opposite trend due to their increased access to water since 1967.

In contrast to the extensive improvement of water supply installations, mainly due to Israel's assistance, no significant progress has been made by Palestinian wastewater treatment plants. The quantity of wastewater generated by the Palestinians at present is estimated at about 52 MCM/Y. Of this, only about 4 MCM/Y is treated in Palestinian plants, roughly 14 MCM/Y is treated in Israeli plants, and the rest (about 34 MCM/Y) pollutes the groundwater and the environment. Apart from the wastewater treatment plant at El-Bireh, no new plants have been constructed in the past 15 years, and even this plant is not maintained properly – its effluent is not used for agriculture, as planned, but is discharged to Wadi Qelt, thereby contaminating it. Furthermore, the Palestinians, possibly due to negligence, have allowed sewage to flow into Israeli territory, polluting the environment and the common aquifer. In stark contrast, 90% of the wastewater from Israeli settlements is already undergoing treatment.

Since it is difficult to quantify the various criteria outlined in international legal norms, signed agreements between countries are binding on the parties and cannot be overruled by customary legal principles. Consequently, the 1995 water agreement signed by Israel and the PA leaves no room for further demands by the Palestinians. This agreement quantified the Palestinians' "future needs" as approximately 70-80 MCM/Y in addition to the 118 MCM/Y already available to them. Israel has met its obligations regarding water supply, not only for the interim period, but also for any future final status agreement. The Palestinians' current demands are not only unjustified according to international legal norms but also fall short according to several international legal parameters regarding disputed water resources, as discussed below.

As has been the case in Israel, increasing the Palestinian water supply can be achieved by improving water use efficiency and wastewater development. The immense water savings that would accrue as a result of plugging leaks in urban pipes is at least 10 MCM/Y, though obviously it is impossible to totally prevent leaks. In addition, the great savings that would result from improving irrigation techniques is at least 15 MCM/Y, which could contribute significantly to the water supply for agricultural lands. Furthermore, the collection and treatment of urban sewage would produce at least 30 MCM/Y to be used for irrigation. This enormous amount would replace freshwater that could be used instead for domestic purposes. Seawater desalination plants could supply any quantity of water that the Palestinians desire. Finally, the Palestinians should be working to pay individually for their water consumption, to prevent leaks in domestic pipelines, to implement conservative irrigation techniques, and to reuse sewage water for irrigation. The fact that they have taken none of these steps and have not adopted any sustainable development practices precludes their demands for additional water from Israel.

# Annex 7: Inventory of devco and echo interventions

- INVENTORY methodology

Elaboration of the Inventory of the interventions financed by the European Commission in Palestine and for the Palestinian People

From the beginning of the evaluation, the team has started to work in order to reconstruct the inventory of all interventions financed by the European Commission in Palestine from 2008 to 2012.

It is worth noting that the goal of the inventory and of its analysis is twofold:

- First, the inventory enables to illustrate the realised (ex post) intervention logic, as compared to the intended (ex ante) intervention logic coming out from the analysis of policy documents.

- Second, it helps to show in a synthetic way, through tables and graphs, the size, the sectoral and financial distribution of the EC interventions and their evolution over time, based on  data retrieved from the Data Warehouse of the DG DEVCO.

As depicted in the figure 1, the process followed can be synthesized in four main steps, which will be presented in further detail in the following sections.

Figure 1: Inventory Process

1.EXTRACTION of Contracts and Decisions from Datawarehouse: temporal criterion (2008-2012) 36.702 contracts 2. FILTERING Removal of canceled contracts and filtering by ”geographical zone” and selection of relevant contracts (Country level, Regional & Multi-country level) 110 Decisions 46 Bilateral Level 11 Regional level 56 Thematic level 3.VALIDATION Classification by type of cooperation looking to the corresponding decision of each contract. BIL, REG; THEM 406 contracts 187 Bilateral Level 145 Regional level 142 Thematic level 6 Not available 4.CLASSIFICATION by type of cooperation, track, mechanism, sector, sub-sector, nature of contract, type of aid, contracting party, regional classification 5.ENRICHMENT The ECHO interventions have been added to the inventory 214 interventions DEVCO 108 contracts 34 Decisions ECHO 19 Contracts 6.UPDATE The DEVCO and ECHO interventions have been updated up to 2013

Step 1: Data Extraction

Interventions undertaken in the Palestinian territories are included in various programmes at both country and multi-lateral level, as a result the first step aimed at including the largest possible sample of interventions in order to avoid the possible exclusion of  relevant interventions. To this end, all available data from Data Warehouse were extracted on the basis of the time criterion, i.e. the 2008-2012 period covered by the evaluation. The application of this first criterion gave a result of 36.702 contracts.

Step 2: Filtering process

This step consisted in applying two main intervention-filtering criteria through which the number of selected interventions was gradually reduced in order to match the scope of the evaluation.

The first action undertaken was to remove the interventions that had been committed, but afterwards cancelled, for a total of 732.

- The number of remaining contracts after the removal of cancelled contracts was 35.970

Geographical relevance

Among the 35.970 contracts, an additional selection was done based on the criterion of the geographical relevance. Under this perspective two different screenings have been carried out in order to retrieve all interventions falling under the bilateral programmes, but also regional and multi-country programmes of significance for Palestine.

Country level

This was done firstly by looking at the column “Benefiting Zone” of the Data Warehouse database and selecting the interventions falling under the denomination “West Bank and Gaza Strip”(code PS).

- The number of contracts falling under the country level was 408.

Regional and Multi-country level

An additional screening from the 35.970 contracts was carried out in order to retrieve all interventions that are of relevance for the country, but not directly linked to Palestine by having a broader geographical scope (either a regional or a multi-country scope). These programmes are registered into the system with the following geographical definitions, that are also included under the column “Benefiting Zone”:

- All countries:(code TPS): 1.749 contracts

- Mediterranean region(code RMD): 253 contracts

- Near and Middle East(code PMO): 24 contracts

- The number of contracts obtained from this selection was 2.026

The selection of relevant contracts at regional and multi-country level has been refined following several criteria:

- Financing instrument: 327 contracts have been excluded since they fall under financing instruments with a geographic or thematic reference that is clearly out of the scope of the evaluation or those ones under financing instruments corresponding to pure administrative procedures;

- Project title

- Key words: Partnership for Peace, Tempus, Euromed Youth

- Delegation in charge: Palestine, Egypt, Jordan, Israel, Lebanon, Syria.

The above mentioned criteria are based on relevant programmes for Palestine, including also those programmes corresponding to neighbouring areas that have a close relation with the Palestinian territories and people.

- The number of relevant contracts obtained following this selection was 72, as follows :

- All countries: 14

- Mediterranean region: 39

- Near and Middle East: 19

Step 3. Data Validation process

In order to avoid discrepancies and to make sure that the inventory does include all relevant projects, the full list of 480 contracts was carefully checked. This validation process consisted of five main actions:

- Withdrawn of Decisions from DWH through the geographical criterion (Palestine) and the temporal criterion (2008-2012), the total number of Decisions resulting from this selection is 57;

- Research of the corresponding decision of each project in the Decision/Contract sheet through the “Contract Reference” and cross-check with the Decisions database;

- Classification of each project for “type of cooperation” looking at the columns “zone benefiting the action” and the “title” of the corresponding decision in order to obtain only 3 main categories: BIL (Bilateral), REG (Regional), MULTI (All countries), NA (Not available);

- Creation of the inventory of Decisions divided by type of cooperation;

- Cross checking of decisions with the EU/PS Action Programmes and Thematic Strategy Papers.

- The number of decisions obtained with this research is:

- Bilateral Cooperation: 57 decisions

- Regional Cooperation: 11 decisions

- Multi-country Cooperation: 42 decisions

The above decisions do not include contracts belonging to decisions issued prior the evaluation period. For these contracts the decision has been individuated in order to classify the intervention but they won’t be included in the presentation and in the analysis since out of the temporal scope of the evaluation.

Step 4: Classification

With a view to enhancing the understanding of EC interventions in Palestine the relevant contracts selected on the basis of the previous steps (i.e. 406 bilateral contracts plus 72 regional and multi-country contracts) have been classified by mechanism, sectors and sub-sectors, nature of contract, type of aid and contracting party.

- Mechanism/Track

The classification by mechanism has been done bearing in mind the three track approach adopted by the EU cooperation in Palestine, which has been defined on the basis of the documentary analysis carried out by the team and encompassing a number of documents, mainly at programming level (Annual Action Programmes, Decisions and Action Fiches) but also at policy level (Action Plans and Communications). The three tracks are as follows:

- First Track: Direct Financial Support (DFS) through the PEGASE Programme: the objective of this track is to support the state-building of Palestine by helping the PA achieve the objectives of the PRDP (2008-2010) and NDP (2011-2013) through working towards fiscal sustainability and efficient public services. The specific PEGASE components have been detailed in the table below.

- Second Track: Developmental goals, supported through several instruments (ENPI, EIDHR, NSA, DCI-FOOD/FOOD) and the PEGASE Development Cooperation component: the objective of this track is to support various initiatives, including support to rule of law/justice, job creation through private sector/trade driven growth and infrastructure improvement in water and sanitation, with initiatives in East Jerusalem and Area C;

- Third Track: support to Palestinian refugees through UNRWA.

Table 1: Classification by Mechanism – EU/Palestine contracts

| Mechanism | Definition | Track |
| --- | --- | --- |
| PEGASE DFS - GLOBAL | Contracts under PEGASE DFS with no specific reference to a particular programme and technical support | Track 1 |
| PEGASE DFS - PRIVATE SECTOR | Private Sector Arrears | Track 1 |
| PEGASE DFS - CSP | Support to Civil Servants and Pensioners | Track 1 |
| PEGASE DFS - VPF | Support to Vulnerable Palestinian Families | Track 1 |
| PEGASE DFS - SEPS | Support to Essential Services | Track 1 |
| PEGASE DFS - CPD | Payment of salaries to the Civil Police and Civil Defence | Track 1 |
| PEGASE DEV COOP | PEGASE Development Cooperation projects including Private Sector Reconstruction in Gaza (PSRG) | Track 2 |
| DEV | All other contracts not related to PEGASE | Track 2 |
| UNRWA | Contribution to the general fund UNRWA | Track 3 |

- Sector and sub-sectors

The sectors have been defined on the basis of the analysis of main relevant policy and programming documents and correspond to the main areas of EC intervention as foreseen under the EU/PA ENP Action Plans 2005 and 2013. The definition of the sectors and sub-sectors has also been defined following a first analysis of the content of the inventory. Overall, 7 sectors have been identified (see Table 2) with 22 sub-sectors.

Table 2: Classification by sectors and sub-sectors – EU/Palestine contracts

| 1 | Government and Political dialogue (GOV) |  |
| --- | --- | --- |
|  | Civilian peace-building, conflict prevention and resolution | Support for civilian activities related to peace building, conflict prevention and resolution, including capacity building, monitoring, dialogue and information exchange |
|  | Democratic participation and civil society | Community participation and development; co-operatives; grassroots organisations; development of other participatory planning and decision making procedures and institutions |
|  | Human Rights | Monitoring of human rights performance; support for national and regional human rights bodies; protection of ethnic, religious and cultural minorities |
|  | Justice | Constitutional development, legal drafting; institutional strengthening of legal and judicial systems; legal training and education; legal advice and services; crime prevention. |
|  | Security | assistance to institutions to enhance its competence and capacity to develop and scrutinise the security system so that it is managed in accordance with democratic norms and principles of accountability, transparency and good governance. It also includes weapons clearance. |
|  | Public sector policy and administrative management | Technical assistance, institutional strengthening and training for the development of internal administrative capacities Macro-economic, fiscal and monetary policy and planning, strengthening financial and managerial accountability; public expenditure management, support to Palestinian administration and services |
| 2. | Privare sector and trade (PSD) |  |
|  | SME/private sector development | Business environment development and private sector restructuring and assistance |
|  | Trade | Trade policy and planning, trade-related legislation and regulatory reforms; simplification and harmonisation of international import and export procedures; support to customs departments. |
|  | Employment | Job creation policies and instruments |
| 3 | Water and Sanitation (WATSAN) |  |
|  | Waste management | Municipal and industrial solid waste management, including hazardous and toxic waste; collection, disposal and treatment; landfill areas; composting and reuse. |
|  | Water supply and sanitation | Water sector policy, planning and programmes; inland surface waters conservation and rehabilitation; activities including protection of maritime water and de-pollution, improvement of waste water governance and management |
| 4 | Infrastructure (INFR) |  |
|  | Energy | Support to energy market integration and sustainable energy, capacity building and technical assistance, rehabilitation of outdated infrastructures |
|  | Transport | Initiatives aiming at improving regional transport dialogue and networks interoperability, safety and security of infrastructures, and rehabilitation of networks |
|  | Urban planning | Integrated urban development projects; local development and urban management; urban infrastructure and reconstruction of buildings; urban; urban development and planning; urban renewal and urban housing; land information systems |
| 5 | Social (SOC) |  |
|  | Education | Education policy including support to primary education, higher education, education facilities, vocational training |
|  | Gender | Activities aiming at enhancing equality between men and women, support to institutions and organisations working for gender equality and women’s empowerment |
|  | Health | Health policy, medical services, Basic and primary health care programme, Basic health infrastructure, Reproductive health care |
|  | Welfare services | Social legislation and administration; institution capacity building and advice; social security and other social schemes; social dimensions of structural adjustment; unspecified support to social infrastructure and services, including aid to refugees More specifically, it includes interventions under PEGASE DFS-CSP such as funds for pensioners and other not well defined areas under PEGASE DFS-CSP and also interventions under UNRWA for relief activities, support services and social infrastructures. |
|  | Youth | Activities for youth empowerment and protection |
|  | Social Protection | Interventions under PEGASE DFS-VPF and all development activities for protection of vulnerable groups and technical assistance to the Ministry of Social Affairs |
| 6 | Culture and communication (CUL) |  |
|  | Communication | Communications policy, promotion of development awareness through radio/television/print media |
|  | Culture | Activities to promote historical heritage (conferences and literary, music, dance and film festivals), and develop culture |
| 7. | Food security (FOOD) |  |
|  | Food security | Supply of edible human food under national or international programmes including transport costs; cash payments made for food supplies; project food aid and food aid for market sales when benefiting sector not specified and for rural development; excluding emergency food aid. |

- Type of aid

The classification by type of aid has been carried out by analysing the column “type of aid” of each single contract, resulting in seven categories, as shown in Table 4. For very specific type of aid (i.e. developmental food aid, emergency and distress relief and developmental awareness) the title of the contract has been used in order to define the broad category to which the contract is related.

Table 4: Classification by Type of Aid – EU/Palestine contracts

| New classification of Type of Aid | Code Type of Aid | Type of aid |
| --- | --- | --- |
| Budget support-general and sectoral | A01 | General budget support |
|  | A02 | Sector budget support |
| Administration costs | ADM | Administration cost |
|  | G01 | Administrative costs not included elsewhere |
| Support to NGOs, private bodies, PPPs and research institutes | B01 | Core support to NGOs, other private bodies, PPPs and research institutes |
|  | PPP | Public-private partnership |
|  | NG2 | Aid to NGOs |
| Contributions to multilateral institutions | B02 | Core contributions to multilateral institutions |
|  | B03 | Contributions to specific-purpose programmes and funds managed by international organisations (multilateral, INGO) |
|  | B04 | Basket funds/pooled funding |
|  | DFA | Developmental food aid |
|  | EMD | Emergency & distress relief |
| Project type intervention | C01 | Project-type interventions |
|  | PGM | Programme Aid |
|  | PRJ | Investment project aid |
|  | H01 | Development awareness |
| Not specified | OTH | Other |
|  | Blank | Blank |
| Technical assistance | TCO | Technical co-operation |
|  | D02 | Other technical assistance |

- Contracting party

Last, the classification by type of aid has been carried out by analysing the column “contractor” and “operator category” of each single contract, resulting in nine categories, as shown in Table 5. For every specific type of aid (i.e. developmental food aid, emergency and distress relief and developmental awareness) the title of the contract has been used in order to define the broad category.

Table 5: Classification by contracting party – EU/Palestine contracts

| New classification of contracting party | Definition |
| --- | --- |
| Association and NGOs | Association, Foundations, Institutes of research |
| Commercial organisation | Consultant companies, specific sector enterprises |
| Single Expert | Contract to a single consultant |
| United Nations | International Organisation - United Nations Family |
| International organisations except UN | International Organisation except United Nations Family (WB and others) |
| EU Member states public organisations | Cooperation agencies of Member states, local institutions, support institutions |
| University/Education | University, Education Institutes |
| Palestine - Public Administration and Institutions | Palestinian authority, Statistical Bureau of Palestine and other institutions |
| Na | Not available |

- Geographical classification

The geographical classification provides information on the geographical allocation of EC funds throughout Palestine (West Bank, Gaza, East Jerusalem). In particular the categories found are the following:

- Palestine (all Palestinian territories)

- West Bank

- Gaza Strip

- East Jerusalem

- Palestine, Jordan, Syria, and Lebanon (refugees camps)

- Jordan (refugees camp)

Step 5: Enrichment of Database

ECHO inventory

The inventory needed to be completed with Humanitarian Assistance data, in order to have a comprehensive view of all cooperation efforts in Palestine. Data on Humanitarian Assistance have been received from ECHO at the end of October 2013 with data referred to only allocations, data on committed and disbursed amounts are missing.

The interventions funded by ECHO during the period of the evaluation (2008-2013) are 215. The interventions have been classified by sector and by partner as shown in the below tables.

Table 7: Classification by sector , ECHO interventions in Palestine

| Sector | Description |
| --- | --- |
| Children | Emergency assistance to children: psychosocial support, post trauma rehabilitation |
| Health | Health, psychosocial support and rehabilitation services |
| Food | Food security assistance |
| Water & sanitation | Emergency Water Assistance |
| Social Protection | Emergency shelter, Economic relief, Emergency livelihoods recovery, Protection activities, Support to livestock-based livelihoods |
| Technical Assistance | Information, Counseling and legal assistance, Humanitarian coordination |
| Na | Title not available |

| Type of Partner | Description |
| --- | --- |
| NGO/Associations | ICRC, OXFAM, Save the Children, Terre Des Hommes etc |
| UN | UNRWA; UNICEF; UNOPS; OCHA etc |

Table 8: Classification by type of partner , ECHO interventions in Palestine

Step 6: Update

The inventory has been updated with data related to interventions committed on 2013. Data for DEVCO interventions have been retrieved from Datawarehouse on January 2014 whereas data for the inventory of ECHO have been received through email by the relevant unit.

The new data have been classified following the same steps described above and then included in the analysis.

Challenges and Presentation

The analysis of the inventory has presented a number of challenges related to the validation process due to the absence of strategic documents in which sectoral priorities and specific amounts should be specified. Indeed, the sectoral classification carried out for the reconstruction of the inventory is based on the Action Plans 2005/2013 and Action Fiches, which however do not present a breakdown of costs involved in the interventions from a strategic point of view.

Overall, the overview and analysis of the inventory allows to provide information with regard to the sectoral distribution of interventions. In addition, the sectoral distribution of interventions will also be presented with a view to provide information that will feed into the analysis of issues of relevance and coherence, and into the process leading to the selection of country-case studies.

The evaluation team has built the inventory on a number of selected fields available in the Datawarehouse database. The fields are the following:

- Contract Year: from 2008 to 2012

- Funding instrument: DCI (ENV, FOOD, GENRE, HUM, NSA, NSAPVD, EIDHR), ENPI, IFS-RRM. MED

- Contract Reference Number;

- Status: Ongoing (O) / Closed (C)/ Provisional (P);

- Title;

- Zone Benefiting from the action; (only for regional level contracts);

- Committed Amount;

- Disbursed Amount;

- Starting date of activities

- End date of activities

- Nature

- Type of Aid

A number of additional fields were then added by the evaluation team in order to increase responsiveness of the inventory to the needs of the evaluation, with particular attention to the sectoral classification of the interventions and to the main tracks to which they belong. Accordingly, these fields are:

- Sector as presented in table 2;

- Sub-sector as presented in table 2;

- Mechanism as presented in table 1;

- Contracting party

- Type of cooperation

- Geographic destination

- INVENTORY ANALYSIS

2.1 	Overall Amounts - DEVCO and ECHO

The analysis covers all contracts being implemented during the period January 2008 – December 2013 by DEVCO and ECHO. This section summarizes amounts allocated in Palestine by the EC during the evaluation period (2008-2013); in the subsequent sections details for the DEVCO and ECHO interventions will be provided.

Table 10: DEVCO and ECHO Amount to PS (2008-2013) and Country data Total amounts; DEVCO Allocated amount; ECHO Committed Amount. GDP nominal 2011 - current prices €; 7,409,100,000. Population tot in 2012; 4,293,313. EC total allocated amount (euro); 2,530,998,102; 2,220,202,160; 310,795,942. EC average allocated amount per year €; 421,833,017; 370,033,693; 51,799,324. EC total contribution per year as % of GDP; 5.7%; 5.0%; 0.7%. EC total allocated amount per capita €; 590; 517; 72. EC average allocated amount per year per capita €; 98; 86; 12. Source: Palestinian Central Bureau of Statistics www.pcbs.gov.ps and DWH

Over the evaluation period the EC pledged €2.5billions to Palestine including both DEVCO and ECHO interventions, which amount to €2.2M of Allocated amount (88%) and €311M (12%) of Committed amount respectively. The EC’s total annual contribution amounts to an average of €422M and represents 5.7% of Palestinian GDP, which corresponds to an average of €98 per capita.

2.2	DEVCO - Interventions

Overall Amounts

Figure 2 describes distribution of allocated, committed and disbursed amounts throughout the evaluation period 2008 – 2013.

Figure 2: DEVCO Allocated/Committed/Disbursed amount to Palestine by year, 2008-2013 - €M

Source: DWH/CRIS and DRN elaboration

The EC issued a total of 589 contracts for a total committed amount of €2.1bn  and the figure evidences significant variations in resources distribution through the evaluation period, with a significant drop of 50% of committed amount from €542m in 2008 to €272m in 2012. The trend of cooperation resources needs to be interpreted in the light of:

- A significant peak of allocations in 2008, a result of Paris’ Donors Conference.

- The decreasing trend in cooperation resources between 2010 and 2012, shown by the graph, can be partially explained as on several occasions there have been decisions on DFS at the end of a year to enable money committed in one year to be used in the following year.

The overall disbursed amount of €1.9bn accounts for 91% of the overall committed amount. In 2008 the disbursed amount covered 99.9% of the committed amount. Over the years the percentage of the disbursed amounts in relation to the committed amounts has decreased somewhat, and in 2012 was 70%.

Type of Cooperation

The EC contracts can be classified by type of cooperation as follows:

- Bilateral Cooperation – (BIL): including contracts falling under Decisions relating to the EC’s Annual Programs for Palestine and financed through geographical funding instruments (ENPI and MED);

- Regional Cooperation – (REG): interventions belonging to regional programs financed by the ENPI ;

- Multi-country Thematic Cooperation (THEM): interventions falling under multi-country thematic programs and Instruments such as European Instrument for Democracy & Human Rights (EIDHR); Non-State Actors & Local Authorities in Development (NSA&LA) Program; DCI-FOOD and IFS-RRM  and Global Commitments.

Contracts falling under BIL represent the vast majority of the total committed amounts at €2bn, (90% of the overall amount); see Figure 3.

Contracts supported by Multi-country Thematic Cooperation amount to €183m (9% of the committed amount), including two large contracts relating to implementation of measures to combat soaring food prices in developing countries, for a total committed amount of €39m, and one contract of €10m, “Support to the UNRWA Social Safety Net Programme (SSNP) in the West Bank, Gaza Strip, Jordan, Syria, and Lebanon”, pledged through UNRWA,

Regional Cooperation contracts (REG) amount to €25m, accounting for 1% of the total committed amount, and include interventions under the “Middle East Peace Projects” (€9m), “EU Partnership for Peace” (€5m), “Global Allocation ENPI South” (€8m), “Euro-Mediterranean Partnership Global Allocation for 2012-2013” (€1.1m) and.

| Figure 3: DEVCO committed amount by type of cooperation in Palestine – 2008-2013 Type of Coop; Committed amount; N. Contracts. BIL; 1,878,720,965; 246. THEM; 183,210,838; 169. REG; 25,439,384; 167. na; 133,553; 7. Total; 2,087,504,740; 589. Source: DWH/CRIS and DRN elaboration | Figure 4: DEVCO Committed amount by Track to Palestine - 2008-2013 Source: DWH and DRN elaboration |
| --- | --- |

Cooperation Tracks

The EC’s contributions to Palestine are disbursed through three tracks, as already described in chapter 2:

  - The first track - Direct Financial Support (DFS) through PEGASE - receives the most significant share, with 56% of total committed amounts accounting for €1bn (Figure 4). In particular the Support to Civil Servants and Pensioner (CSP) receives the majority of funds with €844m, accounting for 72% of the total committed under Track 1. Support to Vulnerable Palestinian Families (VPF) and Support to Essential Services (SEPS) follow with €193m (16%) and €119m (10%) respectively (Table 11).

  - The second track - Development Programs - receives only 18%, accounting for €372m of the total committed amount and including all development programs under the PEGASE Development Cooperation component (PEGASE DEV COOP) and the Development mechanism (DEV). In particular the PEGASE DEV COOP receives a total amount of €189m, including all contract under the program “Private Sector Reconstruction for Gaze” (PSRG) for a total of €34m and contracts such as “Support to Delivery of Community Services in East Jerusalem” (€20m), “Public Infrastructure Development and Facility” (€58m) “PEGASE:EU support for the PA Two-Year Plan for Statehood” (€28m); while DEV receives a total of €183m, including contracts such as “Construction of Community Police Stations” (€6m), “Short Term Low Volume Sea Water Desalination Plant for Southern Governorates of the Gaza Strip” (€10m), “Support livestock based livelihoods of vulnerable population in Palestine - the institutional level component " (€3.5m), “Land Development and Basic Infrastructure in Area C”.

  - The third track - Contributions to UNRWA - receives 26% of the total committed amount, that is €535m) and includes all interventions supporting UNRWA activities. Notably €68.5m supports interventions related to food security programs such as ''Food Facility - EC UNRWA  I& II” (€40m), “Implementation of the Special Hardship Case Program Reform Initiative in Gaza” (€9m) and FSTP (€5m).

|  | Table 11: DEVCO Committed amount by Mechanism to Palestine – 2008-2013 |
| --- | --- |

| Track |  | Mechanism | Committed amount | N. of contracts | % on track | % on total |
| --- | --- | --- | --- | --- | --- | --- |
| Track 1 |  | Total | 1,179,407,214 | 65 | 100.0% | 56% |
|  |  | PEGASE DFS - CSP | 15 | 844,350,000 | 72% | 40% |
|  |  | PEGASE DFS - VPF | 24 | 193,859,147 | 16% | 9% |
|  |  | PEGASE DFS - SEPS | 5 | 119,630,000 | 10% | 6% |
|  |  | PEGASE DFS - PRIVATE SECTOR | 2 | 10,027,486 | 1% | 0% |
|  |  | PEGASE DFS - GLOBAL | 8 | 6,963,930 | 1% | 0% |
|  |  | PEGASE DFS - CPD | 2 | 4,576,652 | 0% | 0% |
| Track 2 |  | Total | 372,752,391 | 505 | 100% | 18% |
|  |  | DEV | 183,307,787 | 366 | 49% | 9% |
|  |  | PEGASE DEV COOP | 189,444,604 | 139 | 51% | 9% |
| Track 3 |  | Total | 535,345,134 | 28 | 100% | 26% |
|  |  | UNRWA | 535,345,134 | 28 | 100% | 26% |
| Total |  |  | 2,087,504,740 | 589 |  | 100.0% |

Source: DWH and DRN elaboration

Funding Instruments

Palestine receives the majority of funds through the geographical instruments ENPI and MED which cover 90% of the committed amount (Table 12).

Table 12: DEVCO Committed amount by Funding Instrument and track to Palestine 2008-2013, values in € Funding Instrument; Track 1; Track 2; Track 3; Total; %. MED; 2,850,723; 3,718,054; 23,240,521; 29,809,298; 1.4%. ENPI; 1,209,023,962; 250,688,389; 414,762,254; 1,874,474,604; 89.8%. DCI-FOOD; 26,096,629; 64,500,549; 90,597,178; 4.3%. IFS-RRM; 4,500,000; 15,575,187; 32,841,810; 52,916,998; 2.5%. DCI-NSAPVD; 14,989,395; 14,989,395; 0.7%. EIDHR; 13,253,736; 13,253,736; 0.6%. DCI-GENRE; 6,386,118; 6,386,118; 0.3%. DCI-HUM; 3,311,072; 3,311,072; 0.2%. DCI-ENV; 1,309,440; 1,309,440; 0.1%. DCI-MIGR; 346,164; 346,164; 0.0%. DCI-NSA; 86,236; 86,236; 0.0%. ADM-MULTI; 24,500; 24,500; 0.0%. TOT; 1,216,374,685; 335,784,921; 535,345,135; 2,087,504,740; 100.0%. Source: DWH and DRN elaboration

The remaining 10% is disbursed through thematic instruments, which mainly support interventions under Track 2 (Table 12).

DCI-FOOD is the main thematic instrument with €91m, accounting for 4.3% of the total committed amount. It includes two “Food Facility” contracts for a total of €40m and 11 contracts under FSTP for a total amount of €25m. The remaining €20m of DCI-FOOD relates to rural and agricultural interventions or to the development of safety nets.

IFS-RRM follows with a total committed amount of €52m, including inter alia two contracts for “Emergency Job Creation Programme in the Gaza Strip – 2009 & 2011” (€33m) and one  contract for “Support to the Palestinian Civil Police” (€4.5m).

Sector distribution

The inventory includes cooperation contributions to the seven sectors described in Table 2 of the methodology and synthesized in figure 5, figure 6 and table 13 here below.

Figure 5: DEVCO Committed amount by sector to Palestine 2008-2013 - €%

Source: EC Datawarehouse and DRN elaboration

Figure 6: DEVCO Committed amount by sector and year to Palestine 2008-2013 - €M

More than €1.5m of EC Cooperation with Palestine is attributed to the social sector (SOC), accounting for 75% of the total committed amount (Figure 5), and representing the most important sector for the period 2008-2013 (Figure 6).

Under the Social sector a number of relevant subsectors are included, see table 13, and the analysis presets the following results:

- the Education sub-sector absorbs 32.4% (€677M) of the total committed amount, by far the largest beneficiary of EC cooperation, including interventions under PEGASE – DFS - CSP (€396m), UNRWA (€251m) that includes the large project “Provision of Quality Education Services” (€10M) and under the Development mechanism (€18m) that includes the “Quality Systems for Quality Teachers (QSQT)” (€4M) and the “Support to the Implementation of the Teacher Education Strategy for Palestine” (€3.6M).

- The Welfare services subsector ranks second with €425M (20.4%) and includes under PEGASE-DFS-CSP funds for pensioners (€101M) and funds for other not specified activities (€219M); while under UNRWA includes funds for relief activates, support services and social infrastructures (€104M).

- The Health subsector follows and receives €230M of the committed amount accounting for 11% and includes interventions under PEGASE – DFS- CSP (€127M), to be mentioned the project “East Jerusalem Hospitals: Network for Quality” (€2.6M), under UNRWA (€81M) that funds projects such as “Mental Health and Psychosocial Services Support” (€3.4M) and under DEV (€8.5M). Large projects under the DEV mechanism are in particular the “Mental Health and Psychosocial Support in West Bank and Gaza, Phase II (MHPSS II)” (€14M) and the project “Improving health and well-being among people affected by mental illness in Gaza: Building local capacity for service provision and support”(€10M).

- The remaining amount of €208M (10%) under the Social sector is channeled to the Social protection subsector. In particular under this sub-sector the PEGASE-DFS-VPF mechanism receives €190M and the DEV mechanism €17M. The last includes among others the projects “Technical assistance to the Ministry of Social Affairs (MoSA) in the occupied Palestinian territory” (€2M) and “Protect the rights and improve resilience of vulnerable communities in East Jerusalem (€3.5M).

- The smallest subsectors under SOC are gender and youth that amount to €9.7M and €9.2M respectively.

The second sector after SOC is the INFR sector with €172M (8.3%) and includes interventions under the sub-sectors Energy that receives €125M, of which €108M pledged by the PEGASE-DFS-SEPS, and the sub-sector urban-planning that receives €46M for construction of hospitals, Spatial Planning for Area C, prisons and other infrastructure facilities not included under transports and energy.

The Government and Political Dialogue (GOV) sector ranks third, accounting for 6% (€124m) of the total committed amount. The main contracts included under this sector are: “Support to the Palestinian Civil Police” (€4.5m),“Support to the Office of the Quartet Representative” (€3m) and “Seyada II - Empowering the Palestinian Judicial System” (€4.4m).

Table 13: DEVCO Committed amount to Palestine by sector and tracks 2008 – 2013

*The subsector “other welfare services” under DFS-CSP includes funds for pensioners (€87M) and funds for other activities (€189M) as defined in the “Evaluation of PEGASE 2012 while under UNRWA includes relief activities

The Private Sector Development and Trade (PSD) ranks fourth accounting for 4% (€85M) of the total committed amount. The largest interventions are channeled through the PEGASE-DEV mechanism for a total of €42m; including the Program “Private Sector Reconstruction in Gaza” (€34m) and the project “Trade diversification/competitiveness enhancement program” (€3m).

The Water and Waste sector ranks sixth after the FOOD sector with €55m (2.7%) including one large contract, “Short Term Low Volume Sea Water Desalination Plant for Southern Governorates of the Gaza Strip” (€10m) and other small projects such as the “EU contribution to KFW Water and Sanitation Programme Palestinian Territory in Deir Al Balah and Rafah City” (€3.5m), “Beit Dajan and Anzah villages- North West Bank- produce more food through sustainable and safe use of reclaimed wastewater in agriculture” (€3.2)  and the “Rehabilitation and expansion of three water infrastructure projects in Herbon District”(€1.6m).

Geographic Distribution

In terms of geographic distribution, it is worth noting that Gaza Strip received 8% (€175m) of the committed amount with an increasing trend throughout the years, see table 14, from €6M received in 2008 to reaches €61M in 2011. East Jerusalem received a total of €28m disbursed with an increasing trend throughout the whole period.

Table 14: DEVCO Committed amount by sector and year to Palestine 2008-2013 - €M

|  | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | TOTAL | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Palestine all territories | 532,064,849 | 259,998,751 | 304,058,982 | 221,888,915 | 178,366,972 | 255,972,974 | 1,752,351,441 | 84% |
| Gaza Strip | 5,942,165 | 20,689,903 | 31,688,692 | 61,573,666 | 49,879,905 | 5,750,070 | 175,524,401 | 8% |
| Jordan | 1,309,440 |  |  | 78,505,280 |  |  | 79,814,720 | 4% |
| West Bank | 1,713,669 | 1,106,460 | 18,106,035 | 10,415,501 | 9,170,830 |  | 40,512,494 | 2% |
| East Jerusalem | 1,170,934 | 800,000 | 5,634,458 | 4,021,398 | 6,964,175 | 9,907,355 | 28,498,320 | 1% |
| WB, GS, Jordan, Syria, and Lebanon |  |  |  |  | 10,000,000 |  | 10,000,000 | 0% |
| Israel |  |  |  |  | 457,200 | 346,164 | 803,364 | 0% |
| TOTAL | 542,201,057 | 282,595,114 | 359,488,166 | 376,404,759 | 254,839,082 | 271,976,563 | 2,087,504,740 | 100% |

Technical Composition of EC funds

The analysis of distribution by type of aid and contracting parties offers interesting results.

On the basis of the “type of aid”:

- 33% falls under Direct Financial Assistance (categorized as Budget Support in the database) (€687m);

- Contribution to multilateral institutions accounts for 26% (€538m);

- Project-type intervention account for 23% (€473m).

The main contracting parties are Palestine’ “Public Administration Institutions” receiving 47% (€980m) of the total committed amount (see Figure 7) and the United Nations Family, receiving 32% (€595m) of the total committed amount, of which disbursed to UNRWA (€535m).

Figure 7: DEVCO Committed amount by contracting party to Palestine 2008-2013 - €M

2.3 	ECHO Interventions

During the period 2008-2013 Palestine has received through ECHO a total committed amount of €311M for a total of 215 interventions following a decreasing trend throughout the years. Indeed, funds have been largely disbursed in 2008 (€71.6M) and in 2009 (€67M); while in 2010 funds have dropped of 27% and reached €34M in 2013, see figure 8.

Figure 8: ECHO Committed amount by sector and year – 2008-2013 - M€ and units (for contracts) Source: ECHO data

In terms of sectoral allocation the “Social Protection” and “Food” sectors receive the majority of funds with €122M (39%) and €115M (37) respectively, see figure 9. “Health” ranks third with a total of €34M (11%); “Children”, “Water6Sanitation” and “Technical Assistance” sectors follows with €14M, €13M and €12M respectively.

Figure 9: ECHO Committed amount by sector – 2008-2013 - %

Another interesting results is related to the partners involved in the interventions. Indeed, while funds are disbursed with a slight different to NGOs (€168M) and UN (€142M) the number of activities covered are sensibly different, with 169 for NGO/ Associations and 46 for UN Agencies, see table 15.

Table 15: ECHO Committed amount by type of partner – 2008-2013  - €

| Type of partner | Allocated Amount | N. of interventions | % |
| --- | --- | --- | --- |
| NGO/association | 168,253,424 | 169 | 54% |
| UN | 142,542,518 | 46 | 44% |
| Total | 310,795,942 | 215 | 100% |

# aNNEX 8: Others Donors’ Cooperation

Between 2008 and 2012 the Official Development Aid (ODA) commitments to Palestine from OECD/DAC donors amounted to US$12.2bn (equal to €9bn).

Figure 10: Total ODA Commitments to Palestine by year – 2007/2012 – € Millions

Source: OECD CRS database and DRN elaboration

Figure 10 shows that ODA commitments reached a peak in 2009 with a total of US$2bn; from 2010 commitments decreased dropping by more than 30% in 2012 when the total amount was €1.2bn.

Figure 11: Total ODA Commitments to Palestine by Donors – 2007/2012 - %

Source: OECD CRS database and DRN elaboration

Figure 11, based on OECD/DAC data, (not including significant contributions from Arab funds and States), shows that the EU Member States represents the largest donors to Palestine with a total aggregated amount of €2.5bn, accounting for 28% of total commitments.

In particular, Germany and Norway are the two major donors with €459m and €413m; and France and Spain rank third and fourth with contributions each amounting to €281m and €260m of, while Sweden ranks fifth with €236m.

United States follow the EU Member states with a total contribution of US$2.3bn while the EU Institutions rank third with a total contribution of US$1.7bn.

The UN family ranks only fifth and deployed a total of US$1.14bn, of which 97% is funded by UNRWA.

In terms of sectoral distribution (see Figure 12) 78% of commitments have a specific sectoral allocation of which “Social Infrastructure & Services” absorbs the majority of funds with a total of €5.5bn. “Commodity Aid / General Program Assistance” follows with €547m while “Multi-Sector/Cross-Cutting”, including gender and environment interventions, ranks third with €347m. Last, “Economic Infrastructure & Services” and “Production Sectors” receive €277m each.

Figure 12: Total ODA Commitments to Palestine by DAC sector 2007/2012 – € Millions

# ANNEX 9: LIST OF DEVCO INTERVENTIONS IN PALESTINE

This section presents the list of EC interventions in Palestine during 2008-2012 extracted from the DataWarehouse and CRIS following the methodology described in Annex 5.

The inventory is organized through two main sections:

- Decisions

- Contracts

The decisions have been divided by type of cooperation:

- Bilateral

- Regional

- Multi-country

While the contracts have been divided by Sector:

- Culture and communication Sector

- Food security Sector

- Governance and Political Dialogue

- Infrastructure Sector

- Private Sector Development and Trade

- Social Sector

- Water and Sanitation Management

The column selected for the presentation of decisions will be the following: Decision Reference; Title; Decisions Year, Allocated Amount, Committed Amount, Disbursed amount, Number of contracts.

The Decision presented are listed by decision year and allocated amount in ascending order.

The column selected for the presentation of contracts will be the following: Contract reference, Title, Status, Domain, Mechanism, Sub-sector, Allocated, Committed Amount, Disbursed amount, Decision Number.

The contracts presented are listed by subsector, track, committed amount in descending order.

EC Decisions in Palestine - Bilateral Cooperation

EC Decisions in Palestine – Regional Cooperation

EC Decisions in Palestine – Multi Country Thematic Cooperation

EC Contracts in Palestine – Culture and Communication Sector

EC Contracts in Palestine – Food Security Sector

EC Contracts in Palestine – Governance Sector

EC Contracts in Palestine – Infrastructure Sector

EC Contracts in Palestine – Private sector Development

EC Contracts in Palestine – Social sector

EC Contracts in Palestine – Waste water and sanitation

# ANNEX 10: LIST OF ECHO INTERVENTIONS IN PALESTINE

# Annex 11: Comparative analysis of projects “Result-Oriented Monitoring”

Introduction

The focus of the evaluation being on the political goals and strategies of cooperation efforts, the evaluation team debated the relevance of using Results-Oriented Monitoring reports, a tool for project-level assessment.

A detailed analysis of ROM documents showed that valuable information could be extracted, since:

- ROM is implemented over a representative sample of EC projects;

- the application of a harmonized methodology and scoring system allows comparability of data across projects;

- several assessment criteria used by ROM address specific issues raised by the Evaluation Questions and Judgment Criteria.

Therefore a detailed analysis of available ROM documents has contributed to the evaluation findings, building additional evidence through external assessment of projects.

Overview of available result-oriented monitoring reports

Table 1 provides an overview of the available ROM data in relation to the interventions funded in the period covered by the evaluation. Out of the 480 funded contracts in Palestine 36 (7,5%) have at least one ROM, a full list being provided below.

Table 1: Summary of ROMs for 2008 – 2012 Cooperation with Palestine

| Contract Year | MR | Committed Amount € | N. of contracts in the inventory | % of contracts of the inventory having MR |
| --- | --- | --- | --- | --- |
| 2008 | 1 | 545.000 | 90 | 1,1 |
| 2009 | 5 | 27.956.193 | 87 | 5,7 |
| 2010 | 10 | 18.703.638 | 96 | 10,4 |
| 2011 | 18 | 24.510.981 | 111 | 16,2 |
| 2012 | 2 | 3.769.533 | 96 | 2,1 |
| Total | 36 | 75.485.345 | 480 | 7,5 |

Source: DRN elaboration based on CRIS data.

Figure 1 : ROMs average performances for 5 DAC criteria and by sector

Source: DRN elaboration based on retrieval on July 2012.

The criterion with the highest average score is Relevance (3.0), meaning that the monitors’ assessments found projects to be well designed and relevant to their objectives. The criterion with the lowest average score is that of sustainability (2.7), which however is not too low and means that the projects seem to have a medium capacity for maintaining a continuation of the stream of benefits once the period of external support has ended.

In terms of sectors, the figure shows good overall project level performances, with weaker performances for projects related to the governance sector with an overall score of 2.7.

Table 2 describes in more detail performance by sector and sub-sector for each of the five main evaluation criteria (relevance and design, efficiency, effectiveness, impact and sustainability)

Table 2: Average ROMs score for EU Cooperation projects by sector 2008-2012

| SECTOR/Subsector | N. of contracts | Relevance | Efficiency | Effectiveness | Impact | Sustainability | Total avarage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ADM |  |  |  |  |  |  |  |
| Capacity-building | 1 | 3,0 | 3,0 | 3,0 | 3,0 | 2,0 | 2,8 |
| Total ADM | 1 | 3,0 | 3,0 | 3,0 | 3,0 | 2,0 | 2,8 |
| ECO |  |  |  |  |  |  |  |
| Trade/PSD | 1 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 |
| Total ECO | 1 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 |
| FOOD |  |  |  |  |  |  |  |
| Food security | 5 | 3,2 | 2,6 | 2,8 | 3,2 | 3,2 | 3,0 |
| Total FOOD | 5 | 3,2 | 2,6 | 2,8 | 3,2 | 3,2 | 3,0 |
| GOV |  |  |  |  |  |  |  |
| Civilian peace-building, conflict prevention and resolution | 2 | 3,0 | 3,0 | 3,0 | 2,5 | 2,5 | 2,8 |
| Democratic participation and Civil Society | 1 | 4,0 | 4,0 | 3,0 | 3,0 | 3,0 | 3,4 |
| Human Rights | 2 | 3,0 | 3,0 | 3,0 | 2,5 | 3,0 | 2,9 |
| Justice | 4 | 1,8 | 1,8 | 2,0 | 2,0 | 1,8 | 1,9 |
| Total GOV | 9 | 2,9 | 2,9 | 2,8 | 2,5 | 2,6 | 2,7 |
| INFR |  |  |  |  |  |  |  |
| Energy | 1 | 3,0 | 4,0 | 3,0 | 4,0 | 3,0 | 3,4 |
| Urban planning | 1 | 3,0 | 3,0 | 3,0 | 2,0 | 2,0 | 2,6 |
| Total INFR | 2 | 3,0 | 3,5 | 3,0 | 3,0 | 2,5 | 3,0 |
| MULTI |  |  |  |  |  |  |  |
| Multisector aid | 1 | 3,0 | 4,0 | 4,0 | 3,0 | 3,0 | 3,4 |
| Total MULTI | 1 | 3,0 | 4,0 | 4,0 | 3,0 | 3,0 | 3,4 |
| SOC |  |  |  |  |  |  |  |
| Culture | 1 | 4,0 | 4,0 | 3,0 | 3,0 | 3,0 | 3,4 |
| Education | 4 | 3,0 | 3,0 | 2,5 | 2,8 | 2,8 | 2,8 |
| Employment | 2 | 3,0 | 3,0 | 2,5 | 3,5 | 2,0 | 2,8 |
| Gender | 1 | 3,0 | 3,0 | 3,0 | 2,0 | 2,0 | 2,6 |
| Health | 2 | 3,0 | 3,0 | 3,0 | 3,0 | 2,5 | 2,9 |
| Welfare services | 5 | 3,2 | 3,0 | 3,0 | 3,4 | 3,2 | 3,2 |
| Youth | 2 | 3,0 | 2,5 | 2,5 | 2,5 | 2,5 | 2,6 |
| Total SOC | 17 | 3,2 | 3,1 | 2,8 | 2,9 | 2,6 | 2,9 |
| Total | 36 | 3,0 | 2,9 | 2,8 | 2,9 | 2,7 | 2,8 |

Table 3 provides a comparative analysis of project performance for the five criteria for the three main cooperation tracks. It shows that track 2 has the worst scores, with an overall average score of 2,8, while tracks 1 and 3 each have a better average score of 3,2, due particularly to the high scores for Impact and Efficiency. However, it must also be noted that the majority of projects fall within track 2 and therefore the overall score is more modest. These data have been used by the evaluation team to support findings.

Table 3: Overview of ROMs track and mechanism for the 5 DAC criteria

| Track/Mechanism | N. of contracts | Relevance | Efficiency | Effectiveness | Impact | Sustainability | Total average |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Track 1 |  |  |  |  |  |  |  |
| PEGASE DFS - GLOBAL | 1 | 3,0 | 4,0 | 3,0 | 4,0 | 3,0 | 3,4 |
| PEGASE DFS - PRIVATE SECTOR | 1 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 | 3,0 |
| Total Track 1 | 2 | 3,0 | 3,5 | 3,0 | 3,5 | 3,0 | 3,2 |
| Track 2 |  |  |  |  |  |  |  |
| DEV | 15 | 3,1 | 2,9 | 2,8 | 2,7 | 2,7 | 2,9 |
| PEGASE DEV COOP | 18 | 2,8 | 2,7 | 2,7 | 2,8 | 2,6 | 2,7 |
| Total Track 2 | 33 | 3,0 | 2,8 | 2,8 | 2,8 | 2,7 | 2,8 |
| Track 3 |  |  |  |  |  |  |  |
| UNRWA | 1 | 3,0 | 4,0 | 3,0 | 4,0 | 2,0 | 3,2 |
| Total Track 3 | 1 | 3,0 | 4,0 | 3,0 | 4,0 | 2,0 | 3,2 |
| Total | 36 | 3,0 | 2,9 | 2,8 | 2,9 | 2,7 | 2,8 |

An in-depth analysis has been carried out to build evidences in support to preliminary findings for the EQs, in particular for sectoral EQs. The analysis is based on a selection of 10 projects, see the projects highlighted in yellow in the below table, and findings have been included in the main report under relevant judgment criteria, in particular 4 ROMs under EQ6, 5 ROMs under EQ7 and 1 ROM under EQ8, for EQ9 none ROM has been considered relevant for the analysis. Here below a summary of the results of the analysis divided by EQ and JC.

EQ6. GOVERNANCE

EQ6/ JC3. Cooperation efforts contribute to institutional capacity - building for governance, accountability and credibility of key institutions

Four monitoring reports were screened to throw light on contributions to capacity-building; all interventions, although with different targets and mechanisms, have contributed significantly to capacity-building.

Table 4: Results on capacity building from ROM on selected projects under Governance

| Contract Number | ROM reference | Project | Findings on contributions to capacity building |
| --- | --- | --- | --- |
| 271613 | MR-145102.01 | Enhancing capacity and professionalism of lawyer community in OPT | - Intervention explicitly supporting lawyers capacity building |
| 215524 | MR-124580.03 | SEYADA II, Empowering the Palestinian Judicial system | - Significant contributions in capacity-building; |
| 258913 | MR-145038.01 | Promoting freedom of thought, association and movement in Gaza through support to Civil Society (EIDHR) | - Capacity-building for Civil Society in Gaza |
| 266673 | MR-144276.01 | Provision of Advisors to the Justice Sector, West Bank and Gaza | - As in SEYADA II, positive contributions to capacity-building in Ministry of Justice |

EQ6/ JC4. EU – Palestine Cooperation effectively supports goals of good governance, democracy, and respect for human rights and rule of law, contributing to a viable and democratic Palestinian state.

Four monitoring reports were reviewed to appraise the effectiveness, sustainability and impact of governance sector interventions, see table 10.

Table 5: ROM Scoring of selected project under Governance for effectiveness, impact and sustainability criteria

| Contract Number | ROM reference | Project | Effectiveness | Impact | Sustainability |
| --- | --- | --- | --- | --- | --- |
| 271613 | MR-145102.01 | Enhancing capacity and professionalism of lawyer community in oPt | D | D | C |
| 215524 | MR-124580.03 | SEYADA II, Empowering the Palestinian Judicial system | C | C | C |
| 258913 | MR-145038.01 | Promoting freedom of thought, association and movement in Gaza through support to Civil Society; (EIDHR) | B | B | B |
| 266673 | MR-144276.01 | Provision of Advisors to the Justice Sector, West Bank and Gaza | B | B | C |

EQ7. SOCIAL SECTOR

EQ7 / JC2 Cooperation Interventions respond to needs and demands of the Palestinian people.

At a more detailed level, relevance has been checked through the review of five Monitoring Reports for the social sector; these reports unanimously assess positively the relevance of EU-funded interventions to beneficiaries’ needs; the following table summarizes the findings.

Table 6: Conclusions of ROM of selected projects under Social Sector (relevance criteria

| Contract Number | ROM reference | Project | Assessment on relevance to needs |
| --- | --- | --- | --- |
| 270253 | MR-145033.01 | EU support for TVET development in Palestine | - High relevance to development of a standardized TVET system in Palestine; - Labor-market-driven training relevant to demand; |
| 268270 | MR-145669.01 | Supporting food security and livelihoods of poor families through improving water harvesting and water demand management for agriculture; | - The project (building 450 storage cisterns) is highly relevant, fully in line with NDP (which fosters building of cisterns) - Responds to findings of the needs analysis framework for food security and agriculture; |
| 237071 | MR-145077.01 | Enhancement of food security in Taybeh and Ramoun through rural development and agricultural extension; | - The project is highly relevant and clearly addresses the issues of food insecurity in the villages; Note by the Evaluation Team: the report however mentions the cancellation of 170 onsite residents who considered connection charges too high; this may raise questions of relevance to the context and capacities /willingness to pay for services. |
| 233062 | MR-142461.02 | East Jerusalem Hospitals network for quality | - The report does not address the score of relevance to needs, but a score “B” for “relevance and design” suggests that no major relevance issues were raised; |
| 237072 | MR-145099.01 | Beit Dahjan and Anzah villages produce more food through sustainable and safe use of reclaimed waste water for agriculture; | - The project is high relevant and clearly addresses the issues of food insecurity and lack of household sanitation systems in the two villages; |

Q7 / JC3 Cooperation efforts contribute to institutional capacity-building and good governance in the sector institutions

Analysis of contributions to capacity-building have been cross-checked through the review of the five Monitoring Reports for the social sector, see below table.

Table 7: Results on capacity building from ROM on selected projects under Governance

| Contract Number | ROM reference | Project | Findings on contributions to capacity building |
| --- | --- | --- | --- |
| 270253 | MR-145033.01 | EU support for TVET development in OPT | - Contributions to empowerment of training services - Improved availability of human resources matching labor market demands |
| 268270 | MR-145669.01 | Supporting food security and livelihoods of poor families through improving water harvesting and water demand management for agriculture | - The intervention was mostly about infrastructures and the report does not point to a capacity-building component; It also reveals the existence of local capacity to manage the cisterns |
| 237071 | MR-145077.01 | Enhancement of food security in Taybeh and Ramoun through rural development and agricultural extension | - The MR does not highlight any contributions to institutional capacity-building |
| 233062 | MR-142461.02 | East Jerusalem Hospitals network for quality | - Project consistent with EU policies on “investing in people” and institution-building |
| 237072 | MR-145099.01 | Beit Dahjan and Anzah villages produce more food through sustainable and safe use of reclaimed waste water for agriculture | - Limited relevance of the project to institutional capacity-building; aspect not addressed by the Monitoring Report |

For the two large “institutional projects” (TVET and East Jerusalem Hospital network) reports confirm significant contributions to institutional capacity-building.

The issue is less relevant for food security grass root interventions; Monitoring Reports for food security do not support meaningful findings in respect of institutional capacity building.

EQ7 / JC4 EU-Palestinian cooperation effectively supports goals of a socially viable sustainable Palestinian state

Five Monitoring Reports were reviewed to appraise effectiveness, sustainability and impact of social sector interventions: 1 education (TVET), 1 health and 3 food security, see below table.

Table 8: ROM Scoring of selected project under Social for effectiveness, impact and sustainability criteria

| Contract Number | ROM Number | Project | Effectiveness | Impact | Sustainability |
| --- | --- | --- | --- | --- | --- |
| 270253 | MR-145033.01 | EU support for TVET development in oPt | A | A | A |
| 268270 | MR-145669.01 | Supporting food security and livelihoods of poor families through improving water harvesting and water demand management for agriculture; | B | A | A |
| 237071 | MR-145077.01 | Enhancement of food security in Taybeh and Ramoun through rural development and agricultural extension; | B | B | B |
| 233062 | MR-142461.02 | East Jerusalem Hospitals network for quality | B | B | C |
| 237072 | MR-145099.01 | Beit Dahjan and Anzah villages produce more food through sustainable and safe use of reclaimed waste water for agriculture; | C | B | B |

(A = the best score; D = worst score)

The result of this random sample of projects shows remarkably positive assessments for aspects of effectiveness (capacity of the specific intervention to contribute to goal), sustainability (capacity to maintain benefits after the end of external assistance) and impact (long-term changes). We note however that Monitoring Reports do not necessarily assess projects against political cooperation goals, an aspect of which the Evaluation team took during the field visits.

EQ8. PRIVATE SECTOR DEVELOPMENT

EQ8 / JC2 Cooperation interventions respond to the needs and demands of the project partners and targeted beneficiaries

The following table reveals a positive assessment for relevance by the one Monitoring Report for PSD.

Table 9: Monitoring Report analysis of relevance for PSD / Trade intervention

| Contract Number | ROM reference | Project | Relevance Score | Assessment on relevance to needs |
| --- | --- | --- | --- | --- |
| 268587 | MR-145023.01 | Trade diversification/competitiveness enhancement program | B | The project is highly strategic as it is in line with the economic priorities identified in the PNP 2011-2013 and fully supported by key stakeholders |

EQ8 / JC3 Cooperation efforts contribute to institutional capacity-building and good governance

The Monitoring Report on contributions to capacity-building reveals weak design and is not conclusive on outcomes, see below table.

Table 10: Results on capacity building from ROM on selected projects under PSD sector

| Contract Number | ROM reference | Project | Monitoring Reports finding |
| --- | --- | --- | --- |
| 268587 | MR-145023.01 | Trade diversification/competitiveness enhancement programme | The provision of capacity building is a challenging process as it is the first time that TiS is being addressed. The World Trade Institute (WTI, UK) was awarded a contract to provide Policy Advice and to deliver training on C3. WTI identified a necessity to provide bilateral coaching via Skype to support beneficiaries, as a basic lack of knowledge was identified during their initial analysis which was not taken into account during project design. |

EQ8 / JC4 EU-Palestine cooperation effectively supports Private Sector Development, contributing to an economically viable Palestinian state

Table 16 summarizes the very positive scoring for criteria of effectiveness, impact and sustainability from the Monitoring Report for Trade Diversification and Competitiveness Enhancement Program; the Evaluation team needs, during the field visit, to gain insights on the meaning of these scores:

Table 16: ROM Scoring of selected project under PSD/Trade for effectiveness, impact and sustainability criteria

| Contract Number | ROM reference | Project | Effectiveness | Impact | Sustainability |
| --- | --- | --- | --- | --- | --- |
| 268587 | MR-145023.01 | Trade diversification/competitiveness enhancement program | A | A | A |

List of available ROM (in yellow the selected ROM for in-depth analysis)

# Annex 12: Conclusions and Recommendations TABLE

This table provides an overview of the links between Evaluation Questions, Conclusions and Recommendations

| EQ | CONCLUSIONS |  |  |  |  | RECOMMENDATIONS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| 1 | X | X |  | X | X | X | X | X | X |  | X |  |
| 2 | X | X |  | X | X |  | X |  |  |  | X |  |
| 3 | X |  |  | X | X |  |  | X | X | X |  |  |
| 4 | X |  |  | X | X | X |  |  |  |  | X | X |
| 5 | X |  |  | X | X |  |  |  | X | X |  |  |
| 6 | X |  | X | X | X |  | X | X | X |  | X |  |
| 7 | X |  |  | X | X |  | X |  |  |  | X |  |
| 8 | X |  |  | X | X |  | X |  |  |  | X |  |
| 9 | X |  | X | X | X |  | X |  |  |  | X |  |

The methodological note on the quality control system will be produced together with the final report

Palestine, as referred to in this Evaluation includes three separate parts: the West Bank, East Jerusalem and the Gaza Strip. While the Oslo Agreement reserved the status of East Jerusalem for final status negotiations, Israel has annexed all of Jerusalem, extending its municipal boundaries into what Palestinians consider to be the West Bank. The Oslo II Accord designated three levels of  territorial and functional governance within the West Bank:

Area A – Palestinian autonomy as far as most public service delivery is considered but no exclusive competence for authoritative allocation of resources or security (currently 18%)

Area B - Palestinian civil administration with joint Israeli-Palestinian security control (currently 21%)

Area C - Full Israeli control, with some exceptions for Palestinian residents (currently 61%)

Sources: Natural Earth, B'Tselem U.N. OCHA Palestine

Agreement on Prepatory Transfer of Powers and Responsibilities between Israel and the PLO, Article 1, 1994.

Egypt, Jordan, and Saudi Arabia declared in late June 2007 that the Fatah led PA was the sole legitimate representative of the Palestinians and Egypt moved its Embassy from Gaza to the West Bank.

The Israeli newspaper Haaretz reported at end of 2008, a total of over 800 tracks, the US Congressional research Service reported in 2010 over 1,000, with about 400 paying a tunnel trade tax to Hamas of about US$2500 each per year. By contrast, UNSCO reported an average of 10,000 trucks per month entering the Gaza Strip before the blockade.

IMF Staff Report: Recent Experience and Prospects of the Economy of the West Bank and Gaza.  March 19, 2013

World Development Report 2009.

These restrictions are extensively documented in any number of documents by USAID, World Bank and UN

2009 PCBS’ economic survey.

Doing Business in the Arab World, 2011, p.87

Source:  World Bank, Coping with Conflict:  Inclusion in the West Bank and Gaza, October 2011

The GOI cites security concerns that restrict its ability to ease restrictions.

Coping with Conflict:  Poverty and Inclusion in the West Bank and Gaza.  The World Bank, October 2011.

This section draws substantially from a report of the World Bank, Coping with Conflict: Poverty and Inclusion in the West Bank and Gaza, October 2011.

UNICEF “Investing in Public Education in Gaza:  A Case Study.” March 2013

World Bank.  From Education-to-Work:  exploring Opportunities and Challenges for West Bank and Gaza, March 2011.  And, World Bank, Towards Economic Sustainability of a Future Palestinian State:  Promoting Private Sector-Led Growth.  April 2012.

Coping with Conflict:  Poverty and Inclusion in the West Bank and Gaza: Overview.   World Bank 2011.

Abdul Rahin, 2009.

Palestinian Bureau of Statistics and Ministry of Health.   National Health Accounts 2009, 2010, Main Findings.  Published Feb 2012

Reforming Prudently Under Pressure:  Health Financing Reform and the Rationalization of Public Sector Health Expenditures.  World Bank,  August 2009.

Health and Education efficiency in UNRWA, UNRWA 2013.

The World Bank.  Targeting Assesment of the Cash Transfer Program in West Bank and Gaza.  June 25, 2012

Socio-Economic and Food Security Survey, West Bank and Gaza, 2012.  Joint Effort between the Palestinian Central Bureau of Statistics and the UN through FAO, UNRWA and WFP.

Palestine country report of the Arab Barometer, http://www.arabbarometer.org

Palestine Ending Occupation Establishing the State, Palestine National Authority, 2009;

Transparency Palestine, Corruption report, 2012 ;

EMHRN and the Palestinian Human Rights Organisations Council’s submission to the EU ahead of the EU-PA sub-committee on human rights, good governance and the rule of law, 2012

From ‘National Water and Wastewater Strategy’ - PWA - July 2013

Scarpa, David (2004), Hydropolitics in recent Israeli-Palestinian relations, Water and Soil Environmental Research Unit, Palestinian National Authority.

World Bank report n°46657-GZ WB&G – Assessment of restrictions on Palestinian water sector development – April 2009

Ref. Statistical Abstract of Israel, 2010

However, due to poor maintenance and old facilities, the leakages in the water networks are estimated to be about 33% on average, leaving only around 69l/inhabitant/day as effective available water (source ARIJ – 2013)

Source: Statistical yearbook of Palestine 2013 – Palestinian central bureau of statistics

First sentence of art.40 is « On the basis of goodwill ».

World Bank - West Bank and Gaza: ‘Assessment of Restrictions on Palestinian Water Sector Development’

From ‘Construction and rehabilitation of water sources in area C: an overview of the applicable legal and permit regime’ – Norwegian Refugee Council NRC – Malvina Khoury - March 2013

EWASH - Down the Drain

Centre for Economic and Social Rights, Thirsting for Justice

OCHA - How Dispossession Happens: The Humanitarian Impact of the Takeover of Palestinian Water Springs by Israeli Settlers, March 2012.

Amnesty International - Thirsting for Justice: Palestinian Access to Water Restricted, October 2009 & EWASH -Thirsting for Justice, Palestinian Rights to Water and Sanitation, March 2012

Messerschmid 2004

« Powers of the Officer in Charge : All the powers that were vested in the Director on the strength of or pursuant to the Settlement Law (Law for Settlement of disputes in Land and Water Law No. 40, 1952, and every proclamation, regulation, directive, notification or order issued on the strength of or pursuant to it) before the Prescribed Day shall be vested in the Officer in Charge ».

EWASH (Emergency Water, Sanitation and Hygiene group) ‘“Down the Drain” (n 148)

Chris Davies (ALDE UK)

Joint answer given by Mr Füle on behalf of the Commission Written questions: E-009278/11 and E-009905/11

The right provided for under Article 55 of the Hague Regulations does not “[i]nclude the privilege to commit waste or strip off the property involved, nor it is conceivable that the administrator or usufructuary [the Occupying Power] may with impunity so use the property as to ruin or destroy the economy of the occupied territory, or to deprive its inhabitants of […] coal, oil, iron, steel […],” as this would amount to unlawful spoliation.

Among others i/ Mideast Security and Policy Studies No. 94 - The Israeli-Palestinian Water Conflict: An Israeli Perspective - Haim Gvirtzman - The Begin-Sadat Center for Strategic Studies - January 2012; ii/ How water became a weapon in Arab-Israeli conflict – Yochanan Visser – 2013 - Missing Peace Information, Gush Etzion; iii/ The Politicization of the Oslo Water Agreement – Lauro Burkart – Institute of International and Development issues - Geneva 2012

National (Israel) water supply company

Source: Mideast Security and Policy Studies No. 94 - The Israeli-Palestinian Water Conflict: An Israeli Perspective - Haim Gvirtzman - The Begin-Sadat Centre for Strategic Studies - January 2012

Those figures appear quite lower than those from the Palestinian Bureau of Statistics (PBS), last estimation in 2013 gave a population of 4,420,549.

The EEAS has adopted the practice that the denomination “Palestine” will be used on all occasions when referring to what to date has been referred to as “Palestinian Authority” or occupied Palestinian territory, source note of the EEAS Executive Secretary General of the 27th of March 2013.

The Data Warehouse is a repository of electronically stored data, housing data sourced from various operational systems used in an organisation. At DEVCO, the data available in the Data Warehouse are extracted from the information systems developed by the IT Unit, including

- CRIS: Common Relex Information System

- PADOR: Potential Applicant Data On-line Registration Service

- PLS: Picture Library System

- ROM: Results Oriented Monitoring system

- Other: data from other information systems might be included in the future

The benefits offered by this system are: speed, data combination, availability of data, consistency throughout the DG, Independence from the source system. Source: EC DATA WAREHOUSE DEVCO'S REPORTING TOOL User Manual

The data were extracted on the 13.03.2013 from the Data Warehouse.

The reference to “cancelled” is included under the column “Status” of the excel sheet retrieved through Data Warehouse.

DCI-ALA (Development - Latin America), DCI-ASIE (Development – Asia).

ADM-MULTI (Administrative Expenditure), BAN (Bananas), COMOROG (Commodity organizations), DCI-EDUC (Development Education) , DEVCOM, DEVPOL, EOM (Electoral observation of which none were referred to Palestine), FINHCRIS (Framework Contract - Financial follow-up outside CRIS), INFCO (Information and coordination (DG DEV).

These are all regional or multi country programmes which finance interventions in Palestine.

This has been useful in order to identify the geographical scope of those contracts with a very general title and broad geographical coverage.

8 out of 56 Decisions have any contract issued during the evaluation period. Indeed those 8 decisions fall under the year 2012, and this is the reason why contracts might have not been issued yet.

This database has been withdrawn from DataWarehouse applying the temporal criterion (2008-2013). This database contains all decisions issued in the relevant period and all corresponding contracts. All contracts belonging to decisions falling before the evaluation period have been cross checked with another database withdrawn from CRIS, which included all contracts from 2002 to 2010.

The REG and MULTI categories include contracts that have been filtered through the country level, this is because some contracts belong to regional interventions but have been registered in DWH with a clear geographical definition.

For 7 contracts difficulties have been faced for the research of the corresponding decision. Indeed, for those contracts the decision number was not shown in the relevant column.

The PEGASE Development Cooperation component is defined by the Evaluation of PEGASE 2008-2011 carried out by  Business and Strategies Europe Consortium.

The titles of the interventions, and, when needed, additional information gathered via Internet and with the support of the OECD/DAC classification which is defined under column “DAC sector”. The DAC sector classification as indicated in the Data Warehouse database was taken in consideration in case of unclear definition of the sector.

The missing data will be presented in the final report

The extracted excel file gathered from Datawarehouse generated 35 columns.

The amounts reflect the content of the inventory which is based on the data collected through CRIS and Datawarehouse and data received from ECHO. Data have been compared to the data presented in the “EU Direct Financial Support to the PA” of the European Court of Auditors, 2013.

The allocated amount refers to the allocation of funds at Decision level

The Committed amount refers to the single commitment issued at Contract Level. For ECHO interventions, amounts at decision level were not available, therefore, the committed amount has been summed to the allocated amount of DEVCO interventions in order to have an overview of the total EC pledged funds.

The figure presents the allocated amounts per year of decision and the committed and disbursed amounts per year of contract. This means that what has been committed in one year has not been necessarily allocated during the same year, this is the reason why in 2009, 2011 and 2013 the committed amount is higher than the allocated amount.

The 589 contracts also include 85 contracts belonging to decisions issued before the evaluation period for a total amount of €33M, accounting for 1.6% of the total contracted amount

The MED instrument has been replaced by ENPI in 2007, however, all contracts emanated from decisions falling prior to 2007 and funded by MED keep the funding instrument of the relevant decision, namely MED. This occurs in particular to 20 contracts of the inventory.

ENPI is an instrument introduced in 2007 replacing MED and TACIS and funding both bilateral and regional programmes

Multi country interventions refer to contracts belonging to decisions having as zone benefitting the action "all countries". This means that the decisions so not specify the geographical specification but at contract level the geographic destination of funds is specified and in the inventory only contracts dealing with Palestine are included.

As per DWH/CRIS definition DCI-FOOD is the domain/funding instrument that supports the Food Security Thematic Programme (FSTP) but also emergency measures not covered by strategic papers, Food Facility programmes and also UNRWA Food Security Contribution Agreements.

This category includes those contracts which the corresponding decision was not possible to find, therefore it is unclear under what kind of cooperation they belong to.

The PEGASE Development Cooperation component is defined by the Evaluation of PEGASE 2008-2011 carried out by  Business and Strategies Europe Consortium, which states in page 7 "EU PEGASE Programme...includes the PEGASE Direct Financial Support (DFS) mechanism and the comprehensive programme of development assistance, covering the four sectors set out in the PRDP (i.e. governance, economy, infrastructures, and social) through PEGASE-Governance, PEGASE-Social, PEGASE-Infrastructure, and PEGASE - Private Sector, deployed by the Office of the European Union Representative (West Bank and Gaza Strip)".

Track 1 includes CSP (Support to Civil Servants and Pensioner), VPF (Vulnerable Palestinian Families), SEPS (Support to Essential Services), PSD includes support to “Private sector arrears'' and CPD (Support to the Palestinian Civil Police)

PEGASEDFS – GLOBAL includes contracts referring to DFS interventions without a clear component destination

Contracts funded by MED refer to interventions emanated by decisions issued before 2007 when ENPI, which replaced that instrument, entered into force.

ENPI includes both contracts falling under the Bilateral and Regional Cooperation, however, the Regional Cooperation receives only €25M, accounting for 1,2% of the total funds pledged under ENPI.

Instrument for Stability - Rapid Reaction Mechanism

Non-State Actors and Local Authorities in Development

For a detailed description of the sector and corresponding sub-sectors refer to table 2 of the methodology.

The contributions to UNRWA are in general multisectoral and correspond to activities under three main sub-sectors: education, health and social services. However, the contracts do not allow to differentiate the amounts related to each particular sub-sector, therefore, the team has decided to dived this amounts following the percentages between sectors as shown in the Annual Report to UNGA.

Exchange rate of February  2014 (http//:ec.europa.eu/budget/inforeuro)

The Decisions presented do not include those decisions falling under years out of the scope of the evaluation. However, contracts belonging to those Decision are included in the inventory.

The allocated amount of the Regional and Multi-country/Thematic decision have been substituted with the contracted amount since the original allocated amount refers to interventions covering more countries and regions and it is not possible at this stage to reconstruct the allocated amount for each contract.

The allocated amount in the spreadsheet refers to the global commitment at decision level, the committed amount is the corresponding amount of each single contract under the relevant decision