## Slide 1
Twinning Manual 2017 - update 2018 What you can and cannot do
DG NEAR – Unit C3 – Twinning Team
RTA Training, 3 December 2019

## Slide 2: Short overview
1. The Team
2. Introduction to Twinning
3. Twinning Contract
4. Implementing and Reporting
5. Rolling Work Plan and changes to the contract
6. Final considerations
7. Coffee break

## Slide 3: 1. The Team
Name | Function
Francesca Aquaro | Team Leader
Nikolina Mijolovic | DEVCO
Ela Horoszko | ENI East + Mandated Bodies
Mihaela Popa | IPA + Institution Building days
Jordi Rodríguez Ruiz | ENI South + RTA Training

## Slide 4: 2. Introduction to Twinning

## Slide 5: Main principles
Projects are built around jointly agreed policy objectives
The Beneficiary retains ownership of the project
Beneficiary selects its Member State*
Full time MS RTA during the project
Concrete operational results
Joint commitment for achieving the results
Joint project of a grant nature
Work plan is jointly drafted by both MS and PC
Results should be maintained
MS NCPs are the only recipients of the calls.
The configuration of the respective selection meetings depends on the applicable rules whether it is direct management, indirect with ex ante control or with ex post control.
The PRICE should not be considered at the time of the evaluation.

## Slide 6: Stakeholders in Twinning project
EU Member State | Partner Country
Lead Project Leader + Junior PLs | BC Project Leader
RTA | RTA counterpart
Component Leaders | BC Component Leaders
National Contact Point (s) | National Contact Point
Twinning Team (Brussels)
EU Delegation
Contracting Authority

## Slide 7: 3. Twinning Contract

## Slide 8: Composition of the contract
Special Conditions
Annex A1: Description of the action (Twinning fiche + MS proposal later the rolling work-plan and STE CVs)
Annex A2: General Conditions for EC financed grant contracts for external actions
Annex A3: Budget for the Action
Annex A4: Contract – award procedures
Annex A5: Standard request for payment and FIF
Annex A6: Model Expenditure Verification Report
Annex A7: Special Financial Annex
Annex A8: Mandates (if MS have formed a consortium)
Annex A9: CV and declaration of availability of the RTA
Notes: In red the documents that need to be “filled” during the preparation of the contract but do not think the others are irrelevant.
Annex A2 is very important, we will talk later.
Annex A4 is basically resuming the steps to de taken for the award of any tendering (services or goods), please, remember that the recruitment of the RTA assistant or the award of a service contract for translation and interpretation, shall follow those rules (to publish locally and to choose among three offers, at least).
Annex A7 is of paramount importance as it resumes the Twinning Manual in there, and it is part of the contract.
The contracts shall be read in order of prevalence, first Special Conditions, that prevails over the Annex A1, that prevails over Annex A2 and so on and so forth.

## Slide 9: Special Conditions
Article 2 – Execution and Implementation period of the Action (legal and work plan duration).
  Execution period: starts on the date of notification of signature of the contract.
  Implementation period: starts upon arrival of the RTA.
Article 7 – Other specific conditions
  Article 7.1 Supplement to General Conditions
  Article 7.2 Derogations to the General Conditions

## Slide 10: Annex A1–Description of the Action
Twinning Fiche + MS Proposal + Rolling work plan and STE CVs;
Clear benchmarks to allow for close monitoring of progress towards the final results;
Rolling work plan must be a joint MS/BC exercise;
Flexibility/adaptability shall be incorporated;

## Slide 11: Mandatory results
Concrete operational results;
‘mandatory results’ should be achieved by limited, well-defined, measurable and precise institutional targets;
‘mandatory results’ must keep as a minimum the level of ambition of the twinning fiche;
Achievements of mandatory results should be maintained after the end of implementation, disseminated and consolidated.

## Slide 12: Twinning Review Missions
Each project can be followed, 6 to 12 months after its finalisation, by a Twinning Review Mission;
This mission aims at reporting whether sustainable impacts or spin offs have been observed after Twinning project finalisation;
Twinning Review Missions are organized and financed by TAIEX instrument;
RTA, BC PL and another former RTA or former STE in similar project.

## Slide 13: Annex A2 - General Conditions
Be careful with supplementary provisions and derogations as per Special Conditions – Art 7;
States rules on: data protection, liability, conflict of interest, confidentality, visibility, suspension/termination, payments, record keeping);
See Annex A7 for: amendments to the contract, reporting and eligibility of costs.

## Slide 14: Annex A3 Budget
Initially, at the signature of the contract, it corresponds to the budget sent by EU MS within the proposal plus corrections applied during contracting phase;
Simplified cost options;
Budget headings: RTA, Horizontal activities and Components;
Dossier with information regarding how the unit costs have been fixed shall be annex to the Budget;
Twinning Project Support Costs, Reserves and Indirect Costs;

## Slide 15: Simplified cost options
Unit cost: cost for one category of items agreed by the Contracting Authority. It is important to prove what was the process that led to the definition of these unit costs (e.g travel cost needing quotation, etc).
Flat Rate: unit cost established for one category of item (twinning project support cost).
Real costs: paid against invoice (e.g. audit cost, interpretation, venues, etc).
All records (including invoices, reports, certificates, etc.) shall be kept for a period of 5 years after the administrative closure of the project as per article 16.7 of the General Conditions.

## Slide 16: Commission Decision – 1122 of 2017 defining the methodology for unit cost items and flat rates in the contract
Secures compliance of Twinning with FR Art 124 and defines the very existence of the Twinning manual
Methodology of Commission Decision now Annex B of Twinning Manual
As consequence:
  Unit costs defined at contracting stage (less supporting document requirements at expenditure verification stage) and definition of what the flat rates compensates
  One rate for all EU MS for experts (one fixed flat daily allowance at 350€) and compensation for RTA simplified)
Link: Commission Decision

## Slide 17: Unit Costs
(a) the monthly remuneration and non-wage labour costs of the RTA;
(b) the monthly payment for the services provided by the RTA assistant(s);
(c) the daily compensation, that is to say the flat daily allowance;
(d) the monthly travel allowance for the RTA who does not move to the partner country with household effects or family, or both, as alternative to the item referred to in point (e);
(e) the yearly travel allowance for the RTA and each accompanying member of the family who moves with him or her to the partner country, as alternative to the item referred to in point (d);
(f) the travel allowance for short-term experts going on mission to the partner country;
(g) the daily subsistence allowance for the RTA aimed at covering all extra costs related to daily life in the partner country including, among other things, lodging and insurances;
(h) the daily subsistence allowance for short-term experts while on mission in the partner country, aimed at covering, among other things, lodging, local transport, meals and sundry expenditures;
(i) the daily subsistence allowance for officials or other agents of the recipient administration while on study visits to a Member State, aimed at covering, among other things, lodging, local transport, meals and sundry expenditures

## Slide 18: Flat rate
Twinning project support costs (136% of each STE fee), and in particular costs for work performed outside the partner country by Member State’s officials and assimilated agents.
Indirect costs (6%) as a compensation for the implementing body.

## Slide 19: Main budgetary considerations
Following Commission Decision:
One flat daily allowance (former expert fee) set at 350€ for all expert categories
Twinning Project Support Costs and setting the flat rate at 136%
Indirect cost fixed at 6%
Reserve funds fixed at 2.5%
Methodology for flat rates established
Methodology and timing for CA fixing unit costs described
When fixed evidence of "event" triggering the compensation, not of amount

## Slide 20: Budget breakdown - and advice on defining amounts in the contract (which is now signed BEFORE the rolling work plan & related budget is finalised)
There are 3 budget headings:
Budget Heading 1: RTA and RTA related costs *guestimate 10-25% / DC
Budget Heading 2: Horizontal Cost items *guestimate 10-15% / DC
Budget Heading 3: Mandatory results *guestimate 60-80% / DC
* These percentages are a result of having exposed a representative sample of old Twinning contracts to the compensation levels and rules in the New Manual. These could be used to set the amounts at the contract stage since the rolling work plan and the related budget is not yet finalised). DC=Direct Costs.
Budget line for Indirect costs fixed at 6% of Σ headings 1-3 (DC)
Budget line for Reserves/Contingency fixed at 2,5% of Σ headings 1-3 (DC)
NB1: The cost item sub-headings under the budget headings in Annex A3 of the Twinning Manual is not exhaustive
NB2: Since Unit costs and flat rates are defined: recommendation to reflect these in an Annex to Annex A3 to the contract
Notes: When asked WHY we changes the system for compensating costs for developing Work-plan before Contract signature. This was clearly unacceptable to DG BUDGET who would only exceptionally accept to pay RTA/PC Counterpart training costs if appearing before contract signature. Instead we now compesate the PL (and component leaders and a support staff if relevant) in a capacity as Short Term experts to come to the country and develop the rolling work-plan AFTER the contract is signed only.

## Slide 21: Budget Breakdown (II) Defining the amounts under the budget headings until a rolling plan and the related budget is fixed after first SC
Unit costs and flat rates
  All unit costs defined as such in Commission Decision must be defined and flat rates in decision (136%, 6%) and Manual (reserves 2.5%) introduced
  (Recommendation: Reflect all such in an Annex to Annex A3)
RTA and RTA related costs:
  - Can be fixed with high level of precision (recommendation: 10-25% of DC)
Horizontal costs:
  - up to sums since cost items to some extent are not unit costs but will be actually incurred costs for Communication/Visibility plan (recommendation: 10-15% of DC)
Mandatory results:
  details of activity costs only known when first rolling work-plan is established and the related budget is ready (Recommendation: 60-80% of DC)
Notes: Pages 22-38 is a detailed review on cost items and could be skipped for certain audiences.

## Slide 22: Budget Heading I: RTA
Notes: Compensation of wage and non-wage: The institution dispatching the RTA shall receive a reimbursement equalling the remuneration of the RTA on the basis of an analytical accounting statement of the last closed accounting year taking full account of all statutory rights according to the civil service legislation of the given Member State (among other things salary, incentives, statutory bonus schemes, and predictable salary changes). The monthly rate will be calculated on the basis of the estimated costs for the months of assignment, divided by the number of months of assignment.
Travel for RTA:

## Slide 23: Compensation wage and non-wage (salary)
The institution dispatching the RTA shall receive a reimbursement equaling the remuneration of the RTA on the basis of an analytical accounting statement of the last closed accounting year taking full account of all statutory rights according to the civil service legislation of the given Member State (among other things salary, incentives, statutory bonus schemes, and predictable salary changes). The monthly rate will be calculated on the basis of the estimated costs for the months of assignment, divided by the number of months of assignment.

## Slide 24: Compensation for daily subsistance - RTA
Paid per overnight stay in the Beneficiary country as per Annex B and Annex A7. This rule also applies to Beneficiary member of staff travelling to a Member State in the framework of a study visit as per Annex B and Annex A7.
Link: Per diems – DEVCO

## Slide 25: Travel of RTA – Monthly travel
If the RTA moves to the partner country without household effects or family, or both, travel costs can be compensated as a monthly travel allowance to cover return fares with one registered luggage. The amount of this monthly allowance shall be established based on the economically most favourable quote among those provided by three travel agencies or the quote provided by the entity of the MS administration selected by competitive procedure in charge of travel arrangements before the signature of the Twinning contract. The quotes shall be endorsed by the authority signing the Twinning contract.
Monthly travel allowance is not a flat-rate payment, hence, it needs to be supported by a triggering event (e.g. travel has happened).

## Slide 26: Travel of RTA – Yearly travel
If the RTA moves to the partner country with household effects or family, or both, travel costs can be compensated as a yearly travel allowance to cover return fares with one registered luggage for the RTA and each accompanying member of his or her family. The amount of this yearly allowance shall be established with the same method used for the monthly allowance.

## Slide 27: Other costs - Budget Heading 1
School fees: paid against invoice (discuss with relevant Contracting Authority about the prices in the local market)
Removal: three quotations required. Paid against invoice.
RTA Training Brussels: (step done, hopefully)
RTA Assistant(s): unit cost to be established on a case-by-case basis taking into consideration conditions prevailing in the partner country and indications provided by the local EU Delegation.

## Slide 28: Budget Heading II: Horizontal Costs

## Slide 29: Budget Heading III: Components

## Slide 30: Coordination costs
Preparation costs: for the contribution of EU MS officials to the preparation of the Rolling Work Plan;
Steering Committees: for the participation of MS PL and Junior PL to the meetings;

## Slide 31: Communication/Visibility Programme
It is mandatory and in line with Communication and Visibility guidelines as well as with CA/EUD
Visiblity: to acknowledge the funding source of the project (EU) via banners, leaflets, pencils…
Communication: who says what in which channel to whom with what effect?
Always coordinate with CA and EUD for more effective public action.
Notes: who says what in which channel to whom with what effect? It was the question raised by Harold Lasswell, an expert on political communication who basically underlines the important of the communicator (who), says what (message), in which channel (oral, written, tv, internet…), to whom (the audience) with what effect (what do you want to achieve with your communication)

## Slide 32: Compensation for daily subsistance - others
Paid per overnight stay in the Beneficiary country as per Annex B and Annex A7. This rule also applies to Beneficiary member of staff travelling to a Member State in the framework of a study visit as per Annex A7, reference is DEVCO.
For traineeships or internships lasting more than 28 days, the daily subsistence allowance however is reduced by 50% as of the 29th day.
Link: Per diems – DEVCO

## Slide 33: Compensation and Travel of Short Term Experts
Fee for STEs is established at 350 euros per day.
Full or half working days can be remunerated for work done in the Partner Country even for travel days if the work can be documented.
Ways for establishing travel cost:
- the economically most favorable quote among those provided by three travel agencies gathered by the MS administration;
- the quote provided by the entity of the MS administration selected by competitive procedure in charge of travel arrangements;
- incurred real costs if unit cost for a specific route could not be established before hand.

## Slide 34: Others costs
Interpretation (service)
Translation (service)
Venue (service): preference that venues are provided by the Partner country and to use rented venues only for exceptional cases (e.g. special visibility events of kick off/opening)

## Slide 35: Direct Costs + Reserves + Indirect Costs

## Slide 36: Reserves
Maximum 2,5% of the direct costs;
Can be used only with approval from the CA;
They can contribute to fund activities;
Notes: Remember to use the reserves wisely. There may be an Icelandic vulano erupting and leaving your experts in places far away from home or from workplace and with extra costs that need to be borne.

## Slide 37: Coffee Break

## Slide 38: Recap
Mandatory Results
Annex A3 Budget
  Unit Costs / Flat Rate – only TPSC/ Real Costs
  Composition of budget:
    Budget Heading I: RTA costs
    Budget Heading II: Horizontal costs
    Budget Heading III: Mandatory Results
    Reserve
    Indirect Costs
Notes: Twinning Project Support Cost - TPSC

## Slide 39: Sli.do time

## Slide 40: 3. Implementation and reporting

## Slide 41: Project Steering Committees
Once per quarter (plus ad hoc, if need be)
Members: Lead MS PL, Junior MS PL, BC PL, RTA, RTA Counterpart
Observers EUD and BC NCP + any other relevant stakeholder (when relevant / optional)

## Slide 42: Reporting
Reports shall consist of a narrative section and a financial section
RTA is responsible for submitting them to the concerned authority (ies) (e.g. EUD + Contracting Authority – if different from EUD)
The BC Project Leader is fully involved in this process and should be given adequate time to put forward comments. S/he must also co-sign each report together with the MS Project Leader.

## Slide 43: e-Reporting (I)
New requirement included in the contracts: OPSYS.
Operational Manager in EUD grants access to the portal Funding and Tender Opportunities as Lead Implementing Partner.
Lead Implementing Partner introduces data directly and the Operational Manager in EUD approves.
E-Reporting does not replace written reporting (for now) !!!

## Slide 44: e-Reporting (II)
What needs to be introduced in e-Reporting:
  Log Matrix
  Update of the current values in the Log Matrix
E-Reporting does not replace written reporting for now

## Slide 45: Interim Quarterly Report (Annex C4)
Describe progress in the implementation making direct reference to the timetables and benchmarks
Update on the general environment, assumption and risks
Make an overall evaluation of the progress achieved
document the actual expenditure in relation to budgeted expenditure

## Slide 46: Final Report (Annex C5)
Executive summary of the project
Background information
Listing of objectives, purpose and mandatory results
Implementation process
Achievement of mandatory results

## Slide 47: Final Report (Annex C5)
Analysis of the long-term impact of the project, its sustainable results and identification of potential relevant follow-up actions
Information on visibility of EU financing
Conclusions, recommendations, including lessons to be learned for future Twinning projects
Proof of transfers of ownership (if applicable) and a final statement of all eligible costs of the Twinning project plus a full summary statement of the Twinning project’s income and expenditure and payments received
Expenditure verification report from a recognized, independent auditor

## Slide 48: 4. Rolling work plan and changes to Twinning contract

## Slide 49: Type of changes
Addendum (substantial change – modification of the contract)
Side Letter (non substantial change, mostly used between rolling work plans – notification to the Contracting Authority)
Rolling work plan (developing activities for 6 months period)
Changes cannot be retroactive

## Slide 50: Addendum (Annex C12)
Changes to:
  Union Acquis applicable
  MS Adminstration in Special Conditions
  Execution and implementation period of the Action
  Mandatory results/outputs and targets
  Identity of Project Leader (MS and PC) or MS RTA
  Re-allocations beyond 25% of the budget headings
Requires going through all financial circuit
Requires time to agree and to process (1 month)

## Slide 51: Budgetary change (section 2 of Annex A7)
“Changes to work plans and side letters and corresponding budgets resulting in re-allocations above 25% between budget headings require an addendum to be processed”
“The work plan is composed of two parts, the description of activities and the corresponding budget. Activities must be identified with the same reference and title in both parts, so that costs can clearly and unambiguously be associated to each budget heading and components.”
“The budget modification by which the 25% threshold is reached requires an addendum. After such an addendum, budgetary changes can again be introduced through side letters/work plans, until the total cumulated amount of the further modifications reaches again 25% between the budget headings of the Twinning Grant Contract.”

## Slide 52: Budget from Proposal to Contract to Rolling Work Plan
Proposal
Indicative Budget* compliant with Template proposal
Contract
Budget revised by FCA and compliant with Annex A3
Rolling Work plan
Budget developed on the basis of the Annex A3 and the rolling work plan.
* The assessment of the indicative budget is not part of the evaluation criteria as per template C7.

## Slide 53: Side Letter (Annex C13)
Any change that does not require addendum.
Can be signed by RTA and BC PL.
Must be submitted to the CA.
CA has 48 hours to reject. Silence is positive. Positive reply can be obtained in shorter delay.
Recommendation: share the text with CA before.

## Slide 54: Rolling Work Plan (Annex C15)
Detailed activities for a period of minimum 6 months approved in the Project Steering Committee;
RWP is like a side letter unless budgetary changes require an addendum;
You have to add indicators and benchmarks for the activities;
Two parts: activities and budget associated with same numbering;
RWP shall include description of departments and resources involved in the activities;

## Slide 55: 6. Final considerations

## Slide 56: Use of experts
All experts shall be civil servants or equivalent from mandated bodies.
Temporary public staff may exceptionally be hired by Member State administrations, semi-public or mandated bodies, as per the provisions in the Twinning Manual for at least 6 months before the assignment.
Recently retired experts may be reactivated as temporary public staff no later than 3 years after retirement, either by administrations or mandated bodies.
It is further reminded that should avoid at all costs to use mandated bodies as umbrella organisations to involve private sector experts hired for contractual assignments limited to their Twinning involvement, without any structural linkage to the body involved.

## Slide 57: Financial control
Expenditure Verification Report: done by external auditor and attached to the Final Report (Annex A6);
Check of payments at any time by CA/EUD: original documents shall be made available except for the flat rates defined as Twinning Project Support Costs and the indirect costs;
Other audits launched by EU services: obligation to cooperate.
Records must be kept for a 5-year period after the last payment made by the BC and the MS

## Slide 58: Twinning Project Support Costs
a) Costs related to time spent by officials or assimilated agents in the Member State in order to prepare and follow-up their missions in the Beneficiary country;
b) Costs related to time spent by the Member State(s) project leader(s) in order to coordinate project implementation from his/her home administration without being seconded from his/her post;
c) Costs related to time spent and costs incurred for the delivery of activities during study visits of Beneficiary country's officials or agents in a Member State;
d) Costs related to time devoted to the logistical arrangements necessary for the organisation of activities in the Beneficiary country.

## Slide 59: Procurement (Annex A4)
Supply of Goods: Limited to € 5000 per Twinning
Supply of Services: Limited to € 5000 per Twinning Component
In both cases a single tender procedure is managed by a MS PL.

## Slide 60: Payments (Article 15 of the GC)
A pre-financing of 100% of the budget for the first 12 months of execution period (excluding contingencies) at the receipt of:
- the Twinning Contract signed by both parties
Further pre-financing of 100% of the budget for the next reporting period if at least 70% of the previous pre-financing*;
Final payment will be executed against approval of final report (narrative, financial and expenditure verification report). Pre-financings cannot exceed 90%.
Notes: * If the 70% Is not matched, the further pre-financing will deduct the difference between the incurred costs and the 70%.

## Slide 61
Twinning is
much easier
than it looks now

## Slide 62: Thank you for your attention
Twinning Coordination Team
Francesca Aquaro
Ela Horoszko
Mihaela Popa
Jordi Rodríguez Ruiz
E-mail: NEAR-TWINNING@ec.Europa.eu