## Slide 1: Feedback by a former Resident Twinning Adviser
Lessons learned and recommendations
Brussels, 8 December 2016
Rudolf SPAN

## Slide 2: My Twinning-experience
2005 - 2007 Short-Term Expert - Romania
2007 - 2009 Resident Twinning Advisor - RO
2010 – 2011 Resident Twinning Advisor - RO
2011 - 2012 Short-Term Expert – Kosovo
<number>

## Slide 3: Let‘s start our excursion! What comes next?
<number>

## Slide 4: Content
The Resident Twinning Advisor (RTA)
Environment of the RTA
Implementation of the project
Conclusions
<number>

## Slide 5: The Resident Twinning Advisor
Tasks
Coordination of the implementation of the project
Achievement of the mandatory results
Professional support for the beneficiary institution – a real colleague!
<number>

## Slide 6: The Resident Twinning Advisor
Behaviour - Diplomatic skills
An 'ambassador' of your country of origin
An 'ambassador' of the European Union
Collaboration on high level: -Ambassadors, Ministers, Secretaries of State, -EU-Delegation/Representation, EU-Commission,
-Executive board of different stakeholders -e.g. associations, NGOs, industry etc.
<number>

## Slide 7: The Resident Twinning Advisor
Skills
Management
Communication
Intercultural competences
Professional expertise
Union legislation
EU - structure and functioning
<number>

## Slide 8: The start
Your expectation?
<number>

## Slide 9: The reality?
<number>

## Slide 10: First steps
Accommodation - Hotel => apartment for rent
Office
Contact - EU Delegation
Contact - own Embassy
Car registration
Health insurance
Doctors etc.
<number>

## Slide 11: First steps
Beneficiary institution
Hierarchy and counterparts in the beneficiary institution
Other relevant institutions
National experts
Central Finance and Contracts Unit (CFCU) / IPA
Project Administration Office (PAO) / ENI
EU Delegation
<number>

## Slide 12: Assistants
Assistant
Interpretation vs. translation
Early selection
Selection procedure for assistants
Advertisement in public media, on the website of the EU-Delegation and of the Beneficiary Administration
<number>

## Slide 13: Assistants
Be careful with recommendations
Choice of the RTA
Can involve the EU-Delegation,
BC – no need to be in the panel.
<number>

## Slide 14: Assistants
Distribution of tasks between assistants
Cooperative behavior is important - no competition
Attendance at missions outside of the capital city
<number>

## Slide 15: Kick-off meeting
It has to be well organised - start in due time
The first highly official appearance of the RTA
High level guests - Invitations
Essential for technical presentations and discussions
A crucial opportunity for visibility
It has to take place as soon as possible but not to early
Already something concrete to present
<number>

## Slide 16: Kick-off meeting
Presentation of the project
Presentation of the team (MS, BC, office)
Overview about the launching of the project
Presentation of the work plan + implementation tools
Visibility material
Website!
Press release / press-conference
<number>

## Slide 17: Your new environment
The country:
History, culture,
Gouvernement,
Political parties – Parliament,
Justice,
Economy, Trade
Language,
Behaviour,
Media etc.
<number>

## Slide 18: International context
International relations of the beneficiary country (BC)
European Union (Accession negotiations, benchmarks, progress reports, IPA program, Association agreements, country strategies, support programs)
EU Member States BC
Your country of origin  BC
Neighbours  BC
<number>

## Slide 19: Your professional environment
EU projects (previous, current, future)
Other projects (bilateral cooperations, World Bank, etc.)
TAIEX
Resident experts
Stakeholders – international and national
<number>

## Slide 20: The institution to be supported
Get familiar with the:
Organisational chart,
Budget, infrastructure,
Regional offices,
Local authorities,
Competencies,
Cooperation with other institutions.
<number>

## Slide 21: Get familiar with the structure
Who is who?
Behaviour, habits
Working hours
Public holidays
Communication tools
<number>

## Slide 22: Current situation?
<number>
'Current Situation Report'
Situation probably changed since the twinning-fiche was drafted,
You need more details and additional special data,
Contact the leadership of the relevant institutions, units and stakeholders,
Work together with the leaders of the Working Groups.

## Slide 23: Reports
<number>
As specified in the Twinning contract!
RTA Office
Current Situation Report /Inception Report (can be part of the first Quarterly report)
Quarterly Reports
Final Report
Short-term experts
Mission Report

## Slide 24: Management meetings Steering committee meetings
BC project leader, RTA counterpart,
Directors, Head of Units,
EU-Delegation
Central Financial and Contracting Unit (CFCU)
Project Administration Office (PAO)
regularly, discussing the progress - activity plan
However, try to solve the problems before the meeting!
<number>

## Slide 25: EU Delegation
What do the EU Delegations do?
a key role in presenting, explaining and implementing EU’s foreign policies;
analyse and report on the policies and developments of their host countries;
conduct negotiations in accordance with given mandates.
How do the Delegations operate?
Maintaining political dialogue;
administering development aid;
supervision of EU trade issues and building cultural contacts.
<number>

## Slide 26: EU Delegation – support and monitoring
Close cooperation with the EU-Delegation is essential and of course beneficial for you as RTA and for the project
General support in the implementation
Support in the collaboration with the BC-administration
Participation of the EU-Delegation at all important events
Kick-off, Steering Committee meetings, Final meeting etc.
<number>

## Slide 27: Implementing a project
Working groups
set up working groups
for each component
BC official as leader
set up rules
activity plan
regular meetings
discussing the progress
<number>

## Slide 28: Activity plans
follow up of the benchmarks
clear time schedule
what needs to be done?
by whom?
by when?
calendars
expert missions
study visits
<number>

## Slide 29: Additional useful documentation
minutes of the meetings
results of discussions
recommendations made
informal or formal character
to be circulated to the beneficiaries – transparency!
reminder for yourself
<number>

## Slide 30: Coordination of the Short Time Experts (STEs)
RTA shall be the bridge and the catalytic agent between the STEs and the national experts/working group members etc. (be proactive!)
input, briefings,
overview and details
understanding the context
absorption capacity of the BC
no need to separate the experts by MS
continuity makes sense.
<number>

## Slide 31: Coordination of the STE-missions
prepare terms of reference, objectives and agenda of the missions in due time
don’t waste 'expert days'
allow the beneficiaries to evaluate the experts – feedback is added value!
mission reports of the experts have to be done in due time!
<number>

## Slide 32: Communication
Web based Intranet / share point
Developed with the beneficiary administration
Included on the website of the beneficiary administration
Access:
- Management of the project
Experts MS and BC
Working Group members etc.
<number>

## Slide 33: Share point - Intranet
<number>

## Slide 34: Communication
Visibility
Website – open for the public
Information for the stakeholders and for the citizens
It takes time but it is essential during the implementation
Added value after finalisation of the project.
<number>

## Slide 35: Website
<number>

## Slide 36: Visibility – start without delay
<number>
Flyer
Brochures
Roll-up banners
Useful gifts:
USB-Sticks
Pencils
etc.

## Slide 37: During implementation Support the needs of the BC
Scope of the project
Benchmarks - Output orientation,
Help the partners to contribute,
RTA shall provide additional input,
Be realistic with your expectation,
Remain optimistic and motivated,
Prepare alternatives for the emergency cases.
<number>

## Slide 38: Challenges
Political instability - Continuity in the BC
Absorption capacity – prioritisation of the project
Working stiles,
You need:
- patience, enthusiasm,
- intercultural skills, - target-oriented work, not forget the goals!
<number>

## Slide 39: Finalisation of the project
Final quarterly report
Final meeting
Final report
Focus on results
Recommendations
Follow up.
<number>

## Slide 40: Time table
<number>
Arrival RTA
Assistant Interpreter
Study visits
Current
Situation rep.
Kick-off
STE-Missions
SC-Meeting + Quarterly
Reports!
Final meeting
Final report
Twinning Review Mission (TRM)

## Slide 41: Follow up
Website
Keep outputs of the project
Networking – Keep in touch
Ensure that all contact details are available
Continue your support so far as possible
Lessons learned?
Future cooperation?
<number>

## Slide 42: Added value for the RTA
Meaningful activity,
Cooperation, collegiality,
Additional professional and life experience,
Intercultural and diplomatic skills,
Management experience,
Be familiar with the EU Institutions
But: it is hard work !!! 
<number>

## Slide 43
THANK YOU FOR YOUR ATTENTION!
<number>
GOOD LUCK AND
SUCCESS!
Rudolf.Span@ec.europa.eu