## Slide 1
Practical advice on Twining working methods and management issues
DG Enlargement – Unit D2
November 2013
Practical advice on Twinning working methods and management issues
Christophe Casillas
DG NEAR – Unit C 3 – 16 & 17 May 2017
Notes: General comments
ask the participants during the meeting if somebody has something against the publication of the pictures in our next quarterly Twinning Newsletter or yearly activity report
Materials: Distribute Twinning Newsletter bring activity reports and manuals
Good morning, my name is

## Slide 2: Presentation content
The instrument and the actors
Twinning Contract
Implementation and Reporting
Addendums and Side letters
Payments
Notes: Today and tomorrow we will present you indetail rules and procedures in Twinning.
Today we will look more particularly the contract and get a general overview of the Twinning instrument while tomorrow we will see some relevant aspects more in detail.
Since the presentation is quite detailed, may I suggest you ask your questions at the end
Before going to the core of my presentation I will give you a brief refresher on what is Twinning, where it is implemented, since when and by whom

## Slide 3: Twinning in numbers since 1998 IPA+ENI
More than 2,700
Twinning projects circulated
More than €2.3 Billion
Budget expenditure
Justice, Agriculture,
Environment and Finance
Main sectors

## Slide 4: WHERE?
EU MS 28 countries
Instrument for Pre-Accession Assistance (IPA)(in light blue)
7 partners
Albania
Bosnia and Herzegovina
Kosovo*
Montenegro
Serbia
Turkey
the former Yugoslav Republic of Macedonia
∗ This designation is without prejudice to positions on status, and is in line with UNSCR 1244 and the ICJ Opinion on the Kosovo Declaration of Independence
IPA
Notes: Croatia special case conferred management power without ex ante control, very active in circulating Twinning fiches mostly TWG lights until December 2016 and participating in calls most of the time as junior partner
Iceland

## Slide 5: WHERE ? ENI
 | ENI Countries (in orange) Morocco Algeria Tunisia Libya* Egypt Israel Palestine* Jordan Lebanon Syria* Armenia Georgia Azerbaijan Ukraine Moldova Belarus*

## Slide 6: When it all started…
Launched in May 1998, aiming to help potential and candidate partners to EU accession in the development of modern public administrations, able to implement the UNION ACQUIS to the same standards as EU Member States (MS) through legal harmonisation.
Twinning is a cooperation tool between two Public Administrations one in a European Union (EU) Member State (MS) and its equivalent in the Instrument for pre-accession (IPA) region.
When? IPA

## Slide 7: When it started in the ENI region?
In 2004 The Twinning instrument was also made available to Neighbourhood countries
It aims at upgrading/modernising an administration though training, reorganisation as well as drafting of laws and regulations through legal approximation
...and to respond to agreements (cooperation or association).
When? ENI

## Slide 8
  Twinning provides the framework
  for public administrations
  and semi-public organisations
  to work with their counterpart in
  Member States.
...to achieve the "mandatory results" commonly agreed by the MS and the beneficiary partners in the contract...
For whom, what for?
Notes: Peer to peer cooperation instrument, best way to ensure a fruitful cooperation

## Slide 9
It consists in sending to a beneficiary
administration a resident twinning
adviser (RTA) from 12 up to 36 months,
and a number of short-term experts
coming from the EU MS administration(s) implementing the twinning...
The mobilisation of both administrations is ensured through the designation of their respective project leaders (high civil servants) the MS PL and beneficiary PL.
HOW?

## Slide 10: TWINNING CYCLE: KEY ACTORS
PAO-CFCU
Beneficiary Administration
MS NCP
EU Delegation (Twinning focal point/Press and information Officer/PAR coordinator)
EC Headquarters
Project Leaders
Resident Twinning Advisers
Component Leaders
Short Term Experts…

## Slide 11: Mandated Bodies
Mandated bodies are semi-public bodies that must satisfy the following criteria:
  Proven competence in a field of the EU Acquis
  Non-profit structure, non-commercial purpose
  Public ownership
  Under the permanent and structural supervision of a government authority
  A sufficient and proportionate level of permanent staff
In case criteria 2 and 3 are partially fulfilled, an ad hoc mandated body status can be granted.
Twinning Manual page 36

## Slide 12: Different kinds of status
- MS Administration/Public body
- Full Mandated Body
- Full Mandated Body, Restricted
- Ad Hoc Mandated Body Status
- Ad Hoc Mandated Body Status, Restricted
private companies, NGOs, Excluded from Twinning? (No Management costs, very limited)
Notes: Page 37
In some cases, where criterion 2 and/or 3 is only partially fulfilled, the mandate is restricted subject to an exclusion from commercial tenders in the direct follow-up to the Twinning project. (…)
Mandated bodies involved in Twinning projects are thus in principle not excluded from providing Technical Assistance under commercially tendered contracts. They must however be excluded from tendering commercially for follow-up contracts to the Twinning projects, if their involvement gives them a commercial advantage. They are also excluded from making a proposal for a Twinning project where they have been involved in drafting the Twinning project fiche (or terms of reference). By the same token, mandated bodies must not include in their proposal/contract any expertise that was involved in the drafting of the fiche.
There are many bodies in the MS which could satisfy the formal criteria to be mandated but which can only make a small, very specialised contribution to a Twinning project (i.e. phytosanitary laboratory training). Their inclusion in the consolidated list is therefore not necessary and they can be given an ad hoc mandate.
- MS Administration (MS public administration, no need of status toparticipate in a Twinning project, for example a Ministry)
Full Mandated Body (Public or semi-public administration fulfilling all 5 eligibility criterias)
Mandated Body Restricted (criterion 2 and/or 3 are partially met)
Ad Hoc Mandated Body Status (institution with a specialised area of expertise, contributing to some activities of a specific project – valid for a specific project)
Ad Hoc Mandated Body Status Restricted
(excluded from tendering commercially for follow-up contracts to the Twinning projects)

## Slide 13: MS Project Leader
The responsibility and involvement of the PL grows significantly:
"In particular, the Project Leader must ensure his/her presence at all meetings of each quarterly Project Steering Committee (PSC) during which the detailed description of activities is updated."
Roles in Twinning IPA

## Slide 14: Junior Project Leader
JPL has a role to play as facilitator for the project.
the JPL can attend Project Steering Committees at the cost of project
STAFF | TASKS | INPUTS
Junior Project Leader | Ensures the good coordination with Project Leader | Attendance to quarterly project steering committees is recommended.
Who?
Notes: The change of the Junior Partner Project Leader is not foreseen as a major change in Twinning and Junior Partner doesn't sign the contract. According to the point before, so the side letter should be enough for notifying this modification.
According to the Twinning Manual 2012, the attendance of the Junior PL to a PStC is not compulsory, but 'recommended' (section 4.3).
On the other hand, section 4.1 specifies that: "In the case of implementation by a Consortium, the MS Project leader and the RTA must ensure that the junior partner it fully involved in the preparation of the operative side letter and immediately informed of the details of activities, in particular with regard to its contribution to the project."

## Slide 15: Role of the RTA
No standard twinning can run without the RTA.
Reinforced importance of RTA’s presence (subsection 2.2.1 of TM 2012)
  …The RTA is the backbone of a Twinning project throughout the entire duration of the implementation period of the Action. He or she is supported in his or her MS administration for logistics, accounting and administrative tasks. This support should allow the RTA to concentrate on the essence of the project.
Addition in first paragraph Annex B1:
  …RTAs made available by MS… throughout the entire duration of the implementation period of the Action.
Who?

## Slide 16: Repeated assignments as RTA
No more than 36 months in one Beneficiary country
No more than 2 assignments in the same region (IPA, ENI South, ENI East)
Maximum 4 assignments in total
Uninterrupted period of 6 months back in MS Administration between the 2nd and the 3rd
3 years back in MS Administration if a 4th assignment is sought.
Who?

## Slide 17: RTA assistant(s)
RTA's choice
One or two, the MS must demonstrate it is more economical to recruit a language assistant than to use the budget line for interpretation, clear distribution of tasks: Interpreter/translator/administrative tasks;
Can be identified and selected before the implementation period during the contract preparation so he/she/they are operational from the very first day of venue of the RTA;
If the RTA assistant must be replaced, a new public selection procedure must be carried out with public advertisement (beneficiary's webpage, EU Delegation, newspapers);
If RTA assistant participates as interpreter in study visit, he/she receives travel costs and Per Diem but no interpretation fees;
Service contract (local legislation applyes) should start day of arrival of RTA, not before.
Notes: pages 84-85
  "RTA Assistant
The RTA should have a full time project assistant at his/her disposal for the purposes of translation and interpretation on a daily basis and general project duties. In most cases the costs for hiring an assistant have to be included in the project budget.
Only in very exceptional cases should the requirement for an assistant be waived.
Note that project assistants remunerated by the project cannot have or recently (past six months) have had any contractual relation with the beneficiary administration.
The recruitment of a suitable project assistant may commence before signature of the Twinning Contract and particulars inserted in the Twinning work plan. A minimum of three candidates must be assessed/ interviewed.
(…)
In line with these provisions the contract with the RTA assistant will be prepared and entered into either by the MS Project Leader or by the CA.
If the service contract for the RTA assistant is entered into by the MS project Leader, he/she will comply with the contract award procedures detailed in the public procurement legislation of his/her Member State, provided it is compliant with the relevant European legislation.
(…)
Whatever the procedure followed (service contract by MS project Leader or by AO) the RTA will have the decisive say into the choice of his/her assistant. This decisive input by the RTA is crucial and cannot be discarded.
The classification list possibly prepared in the framework of a selection procedure cannot be used if, at a later moment, the RTA Assistant needs to be replaced. In such case a full new selection procedure must be launched.

## Slide 18: Role of the Beneficiary PL and RTA
Master words:
Commitment
Mobilisation of the institution's staff
Ownership
Relation of equals
Best practices:
- BA component leaders
- Working groups
- Synergies with other stakeholders?
Who?
Notes: Not to forget most essential actor: the beneficiary without whom a project cannot be successful.
Very important message to convey today
Twinning is not TA: joint commitment, efforts
Open door policy
colleagues

## Slide 19: CONTRACTING AUTHORITY (CA)
Twinning partners should always refer to the Contracting Authority for financial and contractual issues
The CA can be:
1.the Commission (for Direct/centralised management programmes), with the EU Delegation
2.the CFCU (indirect/decentralised management mode after conferral of management power to the national authorities) in IPA region,
3.or the PAO for decentralised ENI region partners
How?
Notes: Tax payers money time of crisis
NO micro-management

## Slide 20
The formal commitment will be in the form of a ‘Twinning Contract’. Specifies the obligations of both administrations in the MS and its beneficiary counterpart
Drafting Twinning contract and work plan must be a joint MS/ Beneficiary administration exercise;
Twinning projects are not bilateral but european projects!
What is a Twinning contract?
EU funded project

## Slide 21: What is a Twinning contract?
Once the choice of the MS partner(s) has been made, it is entirely the duty and responsibility of both Twinning partner administrations (MS and BA) to draw up the Twinning work plan with a corresponding budget.
Together with the other annexes defined in the manual, these elements will form the Twinning Contract.
The structure of the standard Twinning Contract will correspond to the following model:

## Slide 22: Structure of the standard Twinning Contract
- Special Conditions (up-front document)
- Annex A1: Work Plan (Description of the action) ;
- Annex A2: General Conditions applicable to EU-financed grant contracts for external Actions;
- Annex A3: Budget for the Action (including co-financing part by the Final Recipient of the Action);
- Annex A4: Contract-award procedures;
- Annex A5: Standard request for payment and financial identification form;
- Annex A6: Expenditure Verification Report;
- Annex A7: Special Financial Annex;
- Annex A8: Mandates (if MS have formed a consortium)
- Annex A9: CVs
Notes: We invite you in particular to read the general conditions in Annex 2 when preparing the contract
Involvement of the beneficiary in drafting the contract, joint exercise

## Slide 23: MANDATORY RESULTS (OUTPUTS)
Concrete operational results
‘mandatory results’ should be limited, well-defined, measurable and precise institutional targets
Achievements of mandatory results should be maintained after the end of implementation, disseminated and consolidated
ANNEX A1 Description of the Action + WP
Notes: Sustainability
Not outputs but learning by doing, transfer of best practices, Network

## Slide 24: Assumptions
Internal conditions related to the project that must be fulfilled in order to guarantee its success
Risks
Risk is the possibility of loss or injury
A risk is not an uncertainty

## Slide 25: ANNEX A1 Description of the Action + WP
Work plan with clear benchmarks to allow for close monitoring of progress towards the final results;
A work plan consists of a sequence of activities which together constitute a strategy aimed at achieving the results.
The Twinning work plan details the relevant organisation and methods, including work and time schedule, a very precise division of tasks between the partners and a detailed breakdown of costs.
The Workplan, what level of details?

## Slide 26
The Workplan- under ENI
Twinning partners shall submit a draft Twinning Contract for assessment to the Contracting Authority within a maximum period of 2 months from the notification of the selection.
The Contracting Authority is committed to formulate a consolidated feedback within no more than six weeks. The overall target is to have the Twinning Contract signed within a maximum of 5 months from the selection notification date.
ENI

## Slide 27
The Workplan under IPA
Under IPA, information can be provided in an abridged version, i.e. listing only the denomination of components, results to be achieved and most relevant activities.
IPA
Notes: Twinning News 53
On 16 July 2014, Mr Schumann-Hitzler, Director at DG Enlargement, sent a note to the NIPACs in order to clarify some issues related to the preparation of Twinning fiches. The note included also the following considerations:
"The main purpose of the TF is to provide the Member States' administrations with the information necessary to develop a concrete and coherent proposal. Its essential components are therefore:
•a brief description of the situation with regard to the concerned acquis,
•a summary overview of the most relevant activities which are expected,
•the indication of the results to be achieved and
•the basic requirements for the key experts to be involved.
It is reminded that in the Twinning fiche (TF) any description of the suggested arrangements shall remain broad enough to offer Member States the possibility to elaborate proposals which put in due evidence the added value of their methodological approach and the comparative advantage of their offered input. Detailed lists of foreseen activities and disproportionate requirements for the key experts must therefore be avoided."
No need of detailed activities
OSL for first six months
we will see with more detail later

## Slide 28: Annex A3: Budget
Kick-off and closure meetings introduced as ‘Activity 0’ (small catering and venue can be charged – max 500 Euro per event)
No need to submit a request for the first pre-financing (article 4.3 of the Special Conditions)
Annex A5: Request for payment for Twinning Contract

## Slide 29: Annex A3: Budget
Under IPA, limited information required (budget for activities at level of activity heading).
IPA

## Slide 30: Annex A7: Special Financial Annex
Budgetary Addendum required when cumulated changes are above 25% of the global budget. Then side letters can be used until the total reaches again 25%.

## Slide 31: ELIGIBLE COSTS (1)
RTA salary, allowances (as per TM Section 5.3 and Annex B), training, Assistant
Project preparation (TM section 5.2.1)
Project Leader (fees, travel, visibility costs and audit certificate - TM section 5.4)
Experts per activity (fees, travel, per diem, local travel)

## Slide 32: ELIGIBLE COSTS (2)
“Management Costs”: 150% on all fees
Translation – Interpretation
Training in beneficiary administration – Study visit in MS? (different rules IPA/ENI)
Expenditure verification report costs (according to Annex 4)
Procurement of Supplies/Services (limitations)
Contingencies (2,5%)
Notes: For private experts no 150 management costs, the project only covers fees. Must remain exceptional 1 or 2 experts per project, if there is no public expertise available to perform an activity
Contingencies ex ashes cloud
For extension of project better take from savings or from non essential activities cannot be refiled.
Translation interpretation: The CA to give an indicative price every year

## Slide 33: Project Management Costs
Costs of STE/PL working in the MS and backstopping costs
Management of Logistics and Accounting are provided by the MS administration (and Partner MS) and covered out of the Management Costs (no additional cost to the contract)

## Slide 34
Salary, benefits, allowance
Salary and non-wage labour costs
Subsistence allowance (50% of per diem rate)
Health insurance RTA + spouse (max. €200 per person)
(6% of salary and non-wage costs)
Accommodation
Full per diem for first 30 days (RTA) + ½ per diem for spouse/children)
Accommodation
Estate agent fees (max 2 months’ rent)
RTA COSTS
Notes: RTAs PER DIEM remains the same during the whole duration of the project it is fixed in the contract.
For ST experts it may change
PER DIEMS is a maximum ceiling, the PL may decide to pay less
PER DIEMS are fixed by the UN
CFCU may also impose different ceilings for travel, for RTA assistant, etc.
6% as a compensation to the home administration of the RTA to cover cost of a replacement

## Slide 35
Travel
Travel: place of work place of duty
Removal/storage + annual trip home for RTA + spouse/children
OR:
monthly return trips home for RTA
Other RTA costs
Schooling fees (max. €12,000 per child and year)
RTA training in Brussels (3 per diems plus return flight to Brussels)
RTA Assistant
RTA-RELATED COSTS
Notes: PER DIEMS for the RTA are fixed for the entire duration of the RTA assignment in the country
PER DIEMS for short term expert can change during the project, the Twinning Team Brussels sends a Special Twinning Newsletter edition with the applicable PER DIEMS.
Monthly trips by RTA: Price quotation by a travel agency when drafting the contract, should be discussed with CA. Evidence is needed.
No need of evidence of travel, ask official travel agency to issue a price offer, will serve for the entire duration of the project. To be consulted with CFCU.

## Slide 36: PROJECT LEADER COSTS
The Project Leader is required to spend at least 3 days in beneficiary administration every quarter
Project leader fees and 150% management costs
when acting as STE
Airfares
Per diem
Translation of reports etc.
Interpretation
Final audit costs

## Slide 37: PER DIEMS
For RTA remains the same during the duration of project
For short term experts may vary during implementation of project
Per Diems for STEs (per night, no halves)
Per Diems are maximums, decided by the PL
Notes: Consult our website (last slide) to check the applicable per diem rate.
The PER Diem to serve as reference is the one in force on day of contract signature

## Slide 38: CONTRACT PREPARATION COSTS
Refundable upon endorsement of Contract for trips during the period up to 4 months (IPA)/5 months (ENI) following notification of selection
Projects ≤ 1 M€
Project Leader and RTA
6 flights
20 per diems
20 fees
Flat rate 150%
Projects > 1 M€
Project Leader and RTA
9 flights
30 per diems
30 fees
Flat rate 150%

## Slide 39: CONTRACT PREPARATION COSTS
Timeframe to prepare a final contract is 4 months under IPA, 5 months under ENI following the selection notification
6 weeks for submission of first draft.
Possibility to include summer/winter break (up to one additional month) is decided by the Contracting Authority
Notes: Without counting endorsment time.
meaning submission of the final draft Twinning Contract for Steering Committee consultation at Commission Headquarters,

## Slide 40: Limitation on procurement of goods and services in Twinning
Large scale equipment (in principle excluded)
VAT?

## Slide 41: Execution and Implementation period
execution period/legal duration starts with date on the letter of notification of signature of the contract, it will end 3 months after the implementation period of the Action as stipulated in art 2.2
Implementation period start on the date of the arrival of the Resident Twinning Adviser (RTA).
Notes: Execution and Implementation period of the Action (legal and work plan duration)
Article 2 – Execution and Implementation period of the Action (legal and work plan duration)
2.1 The execution period of the contract (legal duration) shall enter into force upon the date of notification by the Contracting Authority of the contract signed by all parties. The execution period of the contract will end 3 months after the implementation period of the Action as stipulated in art 2.2.
2.2 The implementation period of the Action will take .........months and shall start on the date of the arrival of the Resident Twinning Adviser (RTA). His/her arrival has to take place at the latest within one month following the notification of the Twinning contract.
Twinning Light:
The implementation period of the Action will take…..months and shall start on the date of the
notification of the Twinning Light contract.
Which means that for Full Twinning the implementation period starts once the RTA arrives and the execution period will end 3 months after. The RTA has one month for installing in the BC.

## Slide 42: Preparation of the contract (Annex A)
Activities not detailed, just headline and total budget
Article 6. Indicative schedule can be grouped by quarter
Detailed activities for first six months described outside the contract, in the Operative Side Letter (OSL)
IPA

## Slide 43: The Operative Side Letter (OSL) Annex C15, p.202: Template for OSL (IPA)
To be prepared with the contract
First OSL: Detailed activities for minimum 6 months period
  Tasks
  Resources (experts)
  Budget
Approved at Project Steering Committees
Following OSLs: Revision of 3 months + addition 3 months more
Must be signed by both PL, no delegation of signature
5 working days before becoming effective
Draft OSL circulated by RTA at least 10 WD before SC meeting
IPA
Notes: More flexibility more responsibility
Special role of the PL but also JPL and beneficiary PL in draftingthe OSL and reviewing it every quarter
If confident enough it is always possible to make a detailed budget table till end of project
First OSL for first six months then update every 3 months
Not part of the contract

## Slide 44
IPA

## Slide 45: VISIBILITY COSTS
Funds for the printing of posters, banners and other items promoting the activities and acknowledging the funding source (EU)
Projects > 1 M€
10 000 euro
Projects ≤ 1 M€
5 000 euro
The funding source (EU) must be acknowledged on all documents, products and at events within the project.
As a minimum, the EU logo should be displayed

## Slide 46: COSTS for Lead MS in brief
RTA remuneration
Fees of short-term experts
Management costs (150% of fees)
Per diems for STEs
Airfare (economy)
Local travel (max. €50)*
Translation (for instance €15 - €45 per page)
Interpretation (for instance max. €300/ day)
Interpretation away (for instance max. €400/day)
* Urban travel is excluded with the exception of taxi in case of flight arrivals or departures before 7 or after 22 hours.

## Slide 47: COSTS COVERED BY BENEFICIARY ADMINISTRATION (BA)
Office space for RTA and assistant
Telecommunications (phone, fax)
Computer, including e-mail access, printer
Office supplies
Secretarial assistance
Meeting and seminar venues
Small catering
International travel for BA staff (only under IPA I not IPA II nor ENI)
BA experts

## Slide 48: ELIGIBLE COSTS IN STUDY VISITS
Per diems for BA participants
Interpretation (for instance max. €300 per day)
Incidental fee 10€ for the host administration per BA participant
NB: Hiring a BC interpreter or to be accompanied by the RTA assistant/or interpreter/translator of the project (when applicable) is recommended if the cost, including travel and per diem, is lower than the cost of hiring an interpreter in the MS

## Slide 49: SHORT TERM EXPERTS FEES
PUBLIC ADMINISTRATION
Civil servants € 250
MANDATED BODY
Class 1 expert € 250
(Minimum 3 years of relevant experience)
Class 2 expert € 350
(Minimum 8 years of experience, work in non-EU countries)
Class 3 expert € 450
(Minimum 15 years of experience, high-level staff)
Notes: These are Maximum ceilings, the MS PL is entitled to pay less.

## Slide 50: Class 3 expert
"Personal experience in the implementation of institutional aspects targeted by the Twinning project: minimum 15 years.
In addition to the above and to the qualifications expected of senior experts, special counsellors will be past or present holders of a high-level post (junior minister, head of a government department or head or chairman of a public or private sector body with a record of government work, or equivalent).
This category is strictly reserved for individuals with exceptional experience, whose contribution to the Twinning project justifies the high rating and associated costs."

## Slide 51: PRIVATE SECTOR INPUTS
Supply of Goods: Limited to € 5000 for each TW project
Supply of Services: Limited to € 10000 per budget item (per activity)
In both cases a single tender procedure is managed by the MS PL
In special cases, the tender can be managed by the CA

## Slide 52: Twinning Community Tool (TCT)
As a preliminary step, you need to register in ECAS, the European Commission Authentication Service, via the link:
https://circabc.europa.eu
Once registered, please send back your confirmation to Christophe.CASILLAS-VACHER@ec.europa.eu
Registering in the TCT

## Slide 53: TAIEX latest developments
is the Technical Assistance and Information Exchange instrument
supports public administrations in the approximation, application and enforcement of EU legislation as well as facilitating the sharing of EU best practices
largely needs-driven to address issues at short notice in three ways:
Workshops
Expert missions
Study visits
Where to register as TAIEX expert?
http://ec.europa.eu/taiex/experts
Notes: The mission of the Service for Foreign Policy Instruments (FPI) is to support the attainment of the objectives of the EU foreign and security policy as defined in Article 21 of the Treaty on European Union, in particular as regards peace and conflict prevention, and to project the EU’s interests and image in the world.
The overall objective is to:
facilitate the implementation of EU bilateral Cooperation Agreements or similar policy agreements, with a focus on regulatory convergence in partner countries,
to share with them experience, know-how and information on EU policies and legislation in the widest sense
and to support the implementation of mutually agreed commitments
For that purpose FPI is responsible, under the authority of the High Representative of the Union for Foreign Affairs and Security Policy in his/her capacity as Vice-President of the Commission, for the operational and financial management of the budgets for Common Foreign and Security Policy (CFSP), Instrument contributing to Stability and Peace (IcSP), Partnership Instrument, Election Observation Missions (EOMs) and press and public diplomacy (PPD).
In addition, FPI is also responsible for the implementation of Foreign Policy Regulatory Instruments (such as "Sanctions", the Kimberley Process on conflict diamonds, and the "Anti-Torture" Regulation).
The Service is directly attached to the High Representative/Vice-President and works closely with the European External Action Service and with the Commission's Directorates-General, notably Development and Cooperation - EuropeAid, Enlargement, Trade and ECHO.

## Slide 54: Thanks for your attention
Functional mailbox: NEAR-Twinning@ec.europa.eu
NEAR Twinning webpage: http://ec.europa.eu/twinning/