## Slide 1: REPORTING REQUIREMENTS
Interim Quarterly Reports
Final Report

## Slide 2: REPORTING REQUIREMENTS
Reports shall consist of a content section and a financial section
The MS PL is responsible for submitting them to the concerned authority (Manual 6.4.1)
The BA Project Leader is fully involved in this process and should be given adequate time to put forward comments. S/he must also co-sign each report

## Slide 3: INTERIM QUARTERLY REPORTS
Executive summary
Describe progress in the implementation making direct reference to the timetables and benchmarks
Update on the general environment, assumption and risks
Make an overall evaluation of the progress achieved
document the actual expenditure in relation to budgeted expenditure
Provide recommendations

## Slide 4: FINAL REPORT
Executive summary of the project
Background information
Listing of objectives, purpose and mandatory results
Implementation process
Achievement of mandatory results

## Slide 5: FINAL REPORT
Analysis of the long-term impact of the project, its sustainable results and identification of potential relevant follow-up actions
Information on visibility of EU financing
Conclusions, recommendations, including lessons learned for future Twinning projects

## Slide 6: FINAL REPORT Financial part
Proof of transfers of ownership (if applicable) and a final statement of all eligible costs of the Twinning project plus a full summary statement of the Twinning project’s income and expenditure and payments received
Template to be used in ANNEX C5
Expenditure verification report from a recognized, independent auditor

## Slide 8: Basic principles
Changes can only be made within the execution period of the contract (legal duration)
Changes cannot be retroactive
There should be no changes to the mandatory results defined in the work plan; the means of achieving these (benchmarks) may be adapted to circumstances

## Slide 9: CHANGES TO TWINNING CONTRACTS
Addendum
Substantial changes to the Twinning Contract formalized in a formal written addendum to the contract signed by both MS administration and BC administration require prior approval
Side letter
Minor changes are notified to the CA through a side letter signed by both PLs. MS PL can delegate the RTA. Notification must be made by a secure means of communication, so that dispatch can be proven in the event of dispute

## Slide 10: ADDENDUM (1)
Union Acquis related to the project (Article 2 of the Work plan)
Definition of the mandatory results and the benchmarks to be achieved (Articles 3 and 4 of the Work plan)
MS administration involved in the Twinning project (Article 5 of the Contract)
The period of execution or implementation (Art 2 of the Contract)

## Slide 11: ADDENDUM (2)
Identity of the MS and BC Project Leaders, the RTA and the key MS experts (Article 6 of the Work plan)
Major reallocations beyond 25% of the total Budget
Template to be used in ANNEX C12
Notes: Budgetary Addendum required when cumulated changes are above 25% of the global budget. Then side letters can be used until the total reaches again 25%.

## Slide 12: Exception
No addendum needed for Interruption or termination of project before completion
6.7.2 Termination of the Twinning project
"Either party (BA or MS) may terminate the Twinning Contract at any time by giving three months notice in writing to the other party (as specified in article 7.2 of the Special Conditions), after having informed the Commission and the AO thereof. Failure of a party to fulfil any of its obligations under the Twinning Contract entitles the other party to terminate the Twinning Contract stating the grounds."

## Slide 13: SIDE LETTER
Changes not affecting basic purpose (means used for implementation, time schedule and dates, identity of non-key MS’ short term experts)
Reallocations below 25% of the total Twinning budget
Template to be used in ANNEX C13
Changes effective 48h (two working days) after notification.

## Slide 14: BUDGET CHANGES
The overall budget of a project cannot be increased
The unit costs (fees, daily allowances, etc.) must respect the rates set in the manual
Introduction of a new activity must be justified by showing that it will be of real use in achieving the mandatory results: mere availability of funds is not sufficient to justify the financing of new activities.
Costs generated by changes notified or approved after their implementation cannot be reimbursed
2,5% contingencies cannot be refilled

## Slide 15: PAYMENT PROCEDURE
Further pre-financing: when the Lead MS can demonstrate that more than 70% of the cumulated pre-financing has been consumed, a subsequent pre-financing payment may be requested
Payment should take place within 60 days of receipt of the request further to the endorsement by the Beneficiary of services rendered

## Slide 16: PAYMENT PROCEDURE
Prior to final payment/settlement, the accumulated payment of the initial prefinancing and the successive pre-financing payments may not exceed 90% of the total budget.
Final payment: Upon completion of the Twinning project, and subject to approval of the final project report demonstrating that the mandatory results have been achieved, the Lead MS may submit its request for final payment together with the final global financial report accompanied by the expenditure verification report

## Slide 17: EXPENDITURE VERIFICATION REPORT
An auditor must certify that all transactions invoiced by the Lead MS were duly justified in accordance with the established rules and arose solely as a result of the Twinning Contract. Veracity as well as eligibility of the transactions must be audited.
The expenditure verification report dispenses MS implementing bodies from submitting original documentary evidence to the contracting authority when requesting payment.

## Slide 18: DOCUMENTATION IN SUPPORT OF INVOICES
The MS is obliged to keep full accurate and systematic record and accounts of the activities implemented
Records must be kept for a 7-year period after the last payment made by the BA and the MS
These documents comprise any documentation concerning income and expenditure, inventory necessary for the checking of supporting documents, mission/timesheets, transport tickets, pay slips for experts and other invoices

## Slide 19: ARTICLE 9 Twinning Review Missions
Each project is in principle followed, 6 to 12 months after its finalisation, by a Twinning Review Mission
This mission aims at reporting whether sustainable impacts or spin offs have been observed after the Twinning project finalisation.

## Slide 20: Twinning Review Missions (Article 9 – Annex A1)
Triggered by EU Delegation
Final Report to be provided
2 experts (RTA + former RTA)
3-5 days
Obligation to provide report.
Twinning Review Missions are organized and financed by TAIEX
Notes: ALSO ENI, encourage EU Delegations and PAOs in ENI region to launch TRMs

## Slide 21
IMPLEMENTATION TIPS
Twinning Best Practices
Notes: First thing to say is that often a bad project during implementation is the result of a badly designed terms of reference.

## Slide 22: Preconditions for a successful Twinning:
A well designed Twinning fiche (Terms of reference)
Short gap between Twinning fiche approval and its circulation so that mandatory results, priorities, overall context and involved administrations remain unchanged.
High level of commitment of the beneficiary administration

## Slide 23
Absorption capacity of the beneficiary administration well apprehended within the Twinning fiche (a 20 staff unit cannot easily cope with a 2.5 million euros project assistance involving dozens of short term experts and carry out its daily work at the same time)
Project Leader counterpart must make himself available to participate in the management of the project
Notes: ideally not too high ranking position but not too low neither, in general PL are Heads of a department while RTA counterparts are heads of unit, this is the good combination

## Slide 24
(T)winning team: PL and RTAs from the MS(s) and the beneficiary administration should work as a team and remain in close contact, good understanding between MS PL and RTA, clear distribution of tasks
Open door policy, MS RTA and RTA counterpart should be sitting not too far away (offices at walking distance), they should always be available one for each other. If the counterpart PL is also available anytime for the MS RTA this can be key for success
Suggestion: RTA's Office is a meeting room

## Slide 25
If there is a junior partner, he should work closely and in good terms with the lead MS
If there is a consortium of MS', its better to make mix of experts of different nationalities instead of attributing one component of the project to each MS.
Very useful to set up a working group for each component
Very useful if the beneficiary administration officially appoints components leaders of its own (one for each component) and if they can actively participate in the steering committees, in a working group ideally the component leader from the beneficiary should be the leader.

## Slide 26
Develop synergies between Twinning projects, with other related projects, between beneficiary administrations working in the same area (Parliament?)
Inclusive process, civil society, private sector, professional associations, trade unions, Universities
The Twinning Newsletter on the Twinning webpage gives many hints and tips on best practices http://ec.europa.eu/twinning
Always remember Twinning is about sustainability!

## Slide 27: The Extra-mile, implementation tips
  Who is your target? (legislation, statistics, IT?)
  Widening the audience, regional, interinstitutional coverage?
  EU visibility: thematic events, project website (IT), visibity starts the first day!
  Appointing component leaders from BC, WG
  Synergies other projects (statistics, social protection)
  TAIEX, SIGMA no duplication
  SUSTAINABILITY
  Its not the end, just the beginning, open doors policy
Summary
Notes: Sustainability: Twinning is meant for long term assistance, essential aspect
Much to say: learning by doing, train the trainers, materials available online, project website, discussion forum for WG, preparation of missions beforehand
Signature of cooperation agreement between administrations at the end of the project? Assist the beneficiary, do not impose your legislation, your procedures, contract possibility to review activities, importance of implementation methods,
Invitation to events organised by EU administration, internships, exchanges of experts, the minimum answer phone calls
Names of countries
RTAs as Ambassadors
Minutes of meetings

## Slide 28
Notwithstanding
all this…

## Slide 29
…Twinning is
much easier
than it looks!

## Slide 30: Thank you for your attention
Twinning Coordination Team
Paolo Gozzi
Christophe Casillas
Lucia Santuccione
Birgit Persson
Raluca Haralambiade
NEAR Twinning Mail: NEAR-TWINNING@ec.europa.eu
Twinning website: http://ec.europa.eu/twinning/