## Slide 1: Feedback by a former Resident Twinning Adviser Lessons learned and recommendations Brussels, 15 October 2015
RTA SEMINAR
Dieter Goertz
Notes: <number>

## Slide 2
RTA SEMINAR
My experience
Twinning project manager
2000-2004
RTA Romania
2004-2008
Project Leader Romania
2008 - 2010
Mid-term expert Croatia
2010-2011
Since 2011 TAIEX Team leader

## Slide 3
RTA SEMINAR
What comes next?
Starting a twinning project
Implementing a twinning project
  communication
  tools
  managing the experts
  your special role

## Slide 4
RTA SEMINAR
The start
Your expectation?

## Slide 5
RTA SEMINAR
The reality?

## Slide 6
RTA SEMINAR
Assistants

## Slide 7
RTA SEMINAR
Assistants
Early selection
Cooperative behaviour is important
Be careful with recommendations
Translation vs. interpretation
Share of work between assistants

## Slide 8
RTA SEMINAR
Your environment

## Slide 9
RTA SEMINAR
Your environment
The country - history, culture
Government
Parliament
Justice
Media
Civil society
Economy, Trade
Social security

## Slide 10
RTA SEMINAR
Your environment
Relations
International
EU (SAA, Accession negotiations, benchmarks, progress reports, IPA program, Association agreements, country strategies, support programs)
EU Member States and your country
Neighbours

## Slide 11
RTA SEMINAR
Your environment
EU projects (previous, current, future)
Other projects (bilateral cooperation, world bank, UNDP etc.)
TAIEX
SIGMA
Resident experts
complementarity synergy
efficiency

## Slide 12
RTA SEMINAR
The institution to be built?
Current status?

## Slide 13
RTA SEMINAR
The institution to be built?

## Slide 14
RTA SEMINAR
Get familiar with the structure
Organisational chart
Budget, infrastructure
Regional, local structure
Competencies
Cooperation and competition with other institutions
The institution to be built?

## Slide 15
RTA SEMINAR
Get familiar with the structure
Who is who?
Salary level
Job security
Behaviour to hierarchy
The institution to be built?

## Slide 16
RTA SEMINAR
Implementing a project
Communication - use of a web based
intranet/sharepoint - web page of the project

## Slide 17
RTA SEMINAR
Implementing a project
Working groups - setting up of rules - regular meetings - BC official as leader - discussing the progress - based on an activity plan

## Slide 18
RTA SEMINAR
Implementing a project
Management meetings - directors, head of departments - BC project leader - regularly - discussing the progress - based on an activity plan

## Slide 19
RTA SEMINAR
Implementing a project
Activity plans - what needs to be done - by whom - until when - remarks - follow up of the benchmarks

## Slide 20
RTA SEMINAR
Implementing a project
Recommendation papers - results of discussions - recommendations - specific warnings - short notes (1-2 pages) - to be circulated to the beneficiaries - reminder for yourself - informal character

## Slide 21
RTA SEMINAR
Implementing a project
Managing the experts - input depends on availability - understanding the context - no need to separate by MS - RTA shall be the bridge - prepare objectives and agenda of missions - don’t waste expert days - allow the beneficiaries to evaluate the experts

## Slide 22
RTA SEMINAR
Implementing a project
Support the needs - output orientation - RTA shall provide additional input - help the partners to produce - develop plan B’s - lower your expectation - be realistic but optimistic

## Slide 23
RTA SEMINAR
Finalisation of the project
Final report
Focus on results/achievements
Preferably final quarterly report plus a final report
Recommendations
Thank your partners

## Slide 24
RTA SEMINAR
Finalisation of the project
Networking and follow up
Ensure that all contact details are available
Keep outputs of the project
Continue your support so far possible
Keep in touch

## Slide 25
RTA SEMINAR
TAIEX
TAIEX characteristics
TAIEX is the little brother of Twinning
Short term assistance by EU MS public officials
Workshops, expert missions and study visits
Centrally managed
Very flexible instrument driven by demand
Logistics supported by a service provider

## Slide 26
RTA SEMINAR
News on TAIEX
TAIEX between EU Member States
Peer to peer EU MS cooperation
Regional policy and transport
2)Partnership Instrument (PI)
Canada, India, Brazil, Korea first requests
Funded by the EU and requested by EU Delegations
https://myintracomm.ec.europa.eu/dg/fpi/whoweare/about_fpi/Pages/Index.aspx

## Slide 27
RTA SEMINAR
TAIEX EXPERT DATABASE
Encourage all experts to register as a TAIEX expert
Registration is simple using an online tool (renewed soon)
Registration does not mean any commitment

## Slide 28
RTA SEMINAR
TAIEX EXPERT DATABASE
Experts may be contacted by the TAIEX unit
Or have the possibility to show interest in a specific activity
Conditions (per diems, compensation) similar to Twinning
Logistics centrally managed

## Slide 29
RTA SEMINAR
THANK YOU FOR YOUR ATTENTION, GOOD LUCK IN YOUR NEW ENVIRONMENT AND MANY SUCCESS IN BUILDING YOUR INSTITUTION!!!
Dieter Goertz
TAIEX team leader agriculture Institution Building Unit, TAIEX DG NEAR
+32 29 63626 dieter.goertz@ec.europa.eu