## Slide 1
Practical advice on Twining working methods and management issues
DG Enlargement – Unit D2
November 2013
Practical advice on Twinning working methods and management issues
Christophe Casillas & Lucia Santuccione
DG NEAR – Unit C 3 – 15 and 16 October 2015
Notes: General comments
ask the participants during the meeting if somebody has something against the publication of the pictures in our next quarterly Twinning Newsletter or yearly activity report
Materials: Distribute Twinning Newsletter bring activity reports and manuals
Good morning, my name is

## Slide 2: Presentation content
The instrument and the actors
Twinning Contract
Implementation and Reporting
Addendums and Side letters
Payments
Notes: Today and tomorrow we will present you indetail rules and procedures in Twinning.
Today we will look more particularly the contract and get a general overview of the Twinning instrument while tomorrow we will see some relevant aspects more in detail.
Since the presentation is quite detailed, may I suggest you ask your questions at the end
Before going to the core of my presentation I will give you a brief refresher on what is Twinning, where it is implemented, since when and by whom

## Slide 3: WHERE?
EU MS 28 countries
Instrument for Pre-Accession Assistance (IPA)(in light blue)
9 partners
Albania
Bosnia and Herzegovina
Kosovo*
Montenegro
Serbia
Turkey
The former Yugoslav Republic of Macedonia
Croatia (MS but also still recipient of Twinning)
∗ This designation is without prejudice to positions on status, and is in line with UNSCR 1244 and the ICJ Opinion on the Kosovo Declaration of Independence
IPA
Notes: Croatia special case conferred management power without ex ante control, very active in circulating Twinning fiches mostly TWG lights and participating in calls most of the time as junior partner
Iceland

## Slide 4: WHERE ? ENI
 | ENI Countries (in orange) Morocco Algeria Tunisia Libya* Egypt Israel Palestine* Jordan Lebanon Syria* Armenia Georgia Azerbaijan Ukraine Moldova Belarus*

## Slide 5: Starting date of Twinning!
Launched in May 1998, aiming to help potential and candidate partners to EU accession in the development of modern public administrations, able to implement the UNION ACQUIS to the same standards as EU Member States (MS) through legal harmonisation.
Twinning is a cooperation tool between two Public Administrations one in a European Union (EU) Member State (MS) and its equivalent in the Instrument for pre-accession (IPA) region.
When? IPA

## Slide 6: When it started in the ENI region?
In 2004 The Twinning instrument was also made available to Neighbourhood countries
It aims at upgrading/modernising an administration though training, reorganisation as well as drafting of laws and regulations through legal approximation
...and to respond to agreements (cooperation or association).
When? ENI

## Slide 7
  Twinning provides the framework
  for public administrations
  and semi-public organisations
  to work with their counterpart in
  Member States.
...to achieve the "mandatory results" commonly agreed by the MS and the beneficiary partners in the contract...
For whom, what for?
Notes: Peer to peer cooperation instrument, best way to ensure a fruitful cooperation

## Slide 8: Peer to Peer
Notes: -Public bodies
-no supply contracts
-NOT TA
-Not for profit
-NO NGOs nor private consulting companies or experts

## Slide 9
It consists in sending to a beneficiary
administration a resident twinning
adviser (RTA) from 12 up to 36 months,
and a number of medium and short-
term experts coming from the EU MS administration(s) implementing the twinning...
The mobilisation of both administrations is ensured through the designation of their respective project leaders (high civil servants) the MS PL and beneficiary PL.
HOW?

## Slide 10: TWINNING CYCLE: KEY ACTORS
PAO-CFCU
Beneficiary Administration
MS NCP
EU Delegation
EC Headquarters
Project Leaders
Resident Twinning Advisers
Short Term Experts…

## Slide 11: MS Project Leader
The responsibility and involvement of the PL grows significantly:
"In particular, the Project Leader must ensure his/her presence at all meetings of each quarterly Project Steering Committee (PSC) during which the detailed description of activities is updated."
Roles in Twinning IPA

## Slide 12: Junior Project Leader
JPL has a role to play as facilitator for the project.
the JPL can attend Project Steering Committees at the cost of project
STAFF | TASKS | INPUTS
Junior Project Leader | Ensures the good coordination with Project Leader | Attendance to quarterly project steering committees is recommended.
Who?
Notes: The change of the Junior Partner Project Leader is not foreseen as a major change in Twinning and Junior Partner doesn't sign the contract. According to the point before, so the side letter should be enough for notifying this modification.
According to the Twinning Manual 2012, the attendance of the Junior PL to a PStC is not compulsory, but 'recommended' (section 4.3).
On the other hand, section 4.1 specifies that: "In the case of implementation by a Consortium, the MS Project leader and the RTA must ensure that the junior partner it fully involved in the preparation of the operative side letter and immediately informed of the details of activities, in particular with regard to its contribution to the project."

## Slide 13: Role of the RTA
No standard twinning can run without the RTA.
Reinforced importance of RTA’s presence (subsection 2.2.1 of TM 2012)
  …The RTA is the backbone of a Twinning project throughout the entire duration of the implementation period of the Action. He or she is supported in his or her MS administration for logistics, accounting and administrative tasks. This support should allow the RTA to concentrate on the essence of the project.
Addition in first paragraph Annex B1:
  …RTAs made available by MS… throughout the entire duration of the implementation period of the Action.
Who?

## Slide 14: Repeated assignments as RTA
No more than 36 months in one Beneficiary country
No more than 2 assignments in the same region (IPA, ENI South, ENI East)
Maximum 4 assignments in total
Uninterrupted period of 6 months back in MS Administration between the 2nd and the 3rd
3 years back in MS Administration if a 4th assignment is sought.
Who?

## Slide 15: Role of the Beneficiary PL and RTA
Master words:
Commitment
Mobilisation of the institution's staff
Ownership
Relation of equals
Best practices:
- BA component leaders
- Working groups
- Synergies with other stakeholders?
Who?
Notes: Not to forget most essential actor: the beneficiary without whom a project cannot be successful.
Very important message to convey today
Twinning is not TA: joint commitment, efforts
Open door policy
colleagues

## Slide 16: CONTRACTING AUTHORITY (CA)
Twinning partners should always refer to the Contracting Authority for financial and contractual issues
The CA can be:
1.the Commission (for Direct/centralised management programmes), with the EU Delegation
2.the CFCU (indirect/decentralised management mode after conferral of management power to the national authorities) in IPA region,
3.or the PAO for decentralised ENI region partners
How?
Notes: Tax payers money time of crisis
NO micro-management

## Slide 17: Management mode
Direct management
(EU Delegation)
Bosnia
Albania
Montenegro
Kosovo*
Indirect management
(CFCU/D/A)
Turkey
Former Yugoslav Republic of Macedonia
Serbia
How? IPA

## Slide 18: Management mode
Centralised /Direct management
(EU Delegation)
Israel
Armenia
Georgia
Azerbaijan
Ukraine
Moldova
Decentralised/Indirect management
(PAO)
Morocco
Algeria
Tunisia
Egypt
Jordan
Lebanon
How? ENI

## Slide 19: TWINNING CONTRACT
The formal commitment will be in the form of a ‘Twinning Contract’. Specifies the obligations of both administrations in the MS and its beneficiary counterpart
Drafting Twinning contract and work plan must be a joint MS/ Beneficiary administration exercise;
Twinning projects are not bilateral but european projects!
What is a Twinning contract?
EU funded project

## Slide 20: What is a Twinning contract?
Once the choice of the MS partner(s) has been made, it is entirely the duty and responsibility of both Twinning partner administrations (MS and BA) to draw up the Twinning work plan with a corresponding budget.
Together with the other annexes defined in the manual, these elements will form the Twinning Contract.
The structure of the standard Twinning Contract will correspond to the following model:

## Slide 21: Structure of the standard Twinning Contract
- Special Conditions (up-front document)
- Annex A1: Work Plan (Description of the action) ;
- Annex A2: General Conditions applicable to EU-financed grant contracts for external Actions;
- Annex A3: Budget for the Action (including co-financing part by the Final Recipient of the Action);
- Annex A4: Contract-award procedures;
- Annex A5: Standard request for payment and financial identification form;
- Annex A6: Expenditure Verification Report;
- Annex A7: Special Financial Annex;
- Annex A8: Mandates (if MS have formed a consortium)
- Annex A9: CVs
Notes: We invite you in particular to read the general conditions in Annex 2 when preparing the contract
Involvement of the beneficiary in drafting the contract, joint exercise

## Slide 22: MANDATORY RESULTS (OUTPUTS)
Concrete operational results
‘mandatory results’ should be limited, well-defined, measurable and precise institutional targets
Achievements of mandatory results should be maintained after the end of implementation, disseminated and consolidated
ANNEX A1 Description of the Action + WP
Notes: Sustainability
Not outputs but learning by doing, transfer of best practices, Network

## Slide 23: ANNEX A1 Description of the Action + WP
Work plan with clear benchmarks to allow for close monitoring of progress towards the final results;
A work plan consists of a sequence of activities which together constitute a strategy aimed at achieving the results.
The Twinning work plan details the relevant organisation and methods, including work and time schedule, a very precise division of tasks between the partners and a detailed breakdown of costs.
The Workplan, what level of details?

## Slide 24
The Workplan- under ENI
Twinning partners shall submit a draft Twinning Contract for assessment to the Contracting Authority within a maximum period of 2 months from the notification of the selection.
The Contracting Authority is committed to formulate a consolidated feedback within no more than six weeks. The overall target is to have the Twinning Contract signed within a maximum of 5 months from the selection notification date.
ENI

## Slide 25
The Workplan under IPA
Under IPA, information can be provided in an abridged version, i.e. listing only the denomination of components, results to be achieved and most relevant activities.
IPA
Notes: Twinning News 53
On 16 July 2014, Mr Schumann-Hitzler, Director at DG Enlargement, sent a note to the NIPACs in order to clarify some issues related to the preparation of Twinning fiches. The note included also the following considerations:
"The main purpose of the TF is to provide the Member States' administrations with the information necessary to develop a concrete and coherent proposal. Its essential components are therefore:
•a brief description of the situation with regard to the concerned acquis,
•a summary overview of the most relevant activities which are expected,
•the indication of the results to be achieved and
•the basic requirements for the key experts to be involved.
It is reminded that in the Twinning fiche (TF) any description of the suggested arrangements shall remain broad enough to offer Member States the possibility to elaborate proposals which put in due evidence the added value of their methodological approach and the comparative advantage of their offered input. Detailed lists of foreseen activities and disproportionate requirements for the key experts must therefore be avoided."
No need of detailed activities
OSL for first six months
we will see with more detail later

## Slide 26: Annex A3: Budget
Kick-off and closure meetings introduced as ‘Activity 0’ (small catering and venue can be charged – max 500 Euro per event)
No need to submit a request for the first pre-financing (article 4.3 of the Special Conditions)
Annex A5: Request for payment for Twinning Contract

## Slide 27: Annex A3: Budget
Under IPA, limited information required (budget for activities at level of activity heading).
IPA

## Slide 28: Annex A7: Special Financial Annex
Budgetary Addendum required when cumulated changes are above 25% of the global budget. Then side letters can be used until the total reaches again 25%.

## Slide 29: ELIGIBLE COSTS (1)
RTA salary, allowances (as per TM Section 5.3 and Annex B), training, Assistant
Project preparation (TM section 5.2.1)
Project Leader (fees, travel, visibility costs and audit certificate - TM section 5.4)
Experts per activity (fees, travel, per diem, local travel)

## Slide 30: ELIGIBLE COSTS (2)
“Management Costs”: 150% on all fees
Translation – Interpretation
Training in beneficiary administration – Study visit in MS? (different rules IPA/ENI)
Expenditure verification report costs (according to Annex 4)
Procurement of Supplies/Services (limitations)
Contingencies (2,5%)
Notes: For private experts no 150 managemet costs, the project only covers fees. Must remain exceptional 1 or 2 experts per project, if there is no public expertise available to perform an activity
Contingencies ex ashes cloud
For extension of project better take from savings or from non essential activities cannot be refiled.

## Slide 31: NON-ELIGIBLE COSTS
Costs of STE/PL working in the MS and backstopping costs (covered by project management costs)
Large scale equipment (in principle excluded)
VAT?

## Slide 32
Salary, benefits, allowance
Salary and non-wage labour costs
6% of salary and non-wage costs
Subsistence allowance (50% of per diem rate)
Health insurance RTA + spouse (max. €200 per person)
Accommodation
Full per diem for first 30 days (RTA) + ½ per diem for spouse/children)
Accommodation
Estate agent fees (max 2 months’ rent)
RTA COSTS
Notes: RTAs PER DIEM remains the same during the whole duration of the project it is fixed in the contract.
For ST experts it may change
PER DIEMS is a maximum ceiling, the PL may decide to pay less
PER DIEMS are fixed by the UN
CFCU may also impose different ceilings for travel, for RTA assistant, etc.

## Slide 33
Travel
Travel: place of work place of duty
Removal/storage + annual trip home for RTA + spouse/children
OR:
monthly return trips home for RTA
Other RTA costs
Schooling fees (max. €12,000 per child and year)
RTA training in Brussels (3 per diems plus return flight to Brussels)
RTA Assistant
RTA-RELATED COSTS
Notes: PER DIEMS for the RTA are fixed for the entire duration of the RTA assignment in the country
PER DIEMS for short term expert can change during the project, the Twinning Team Brussels sends a Special Twinning Newsletter edition with the applicable PER DIEMS.
Monthly trips by RTA: P
rice quotation by a travel agency when drafting the contract, should be discussed with CA.
No need of evidence of travel, ask official travel agency to issue a price offer, will serve for the entire duration of the project. To be consulted with CFCU.

## Slide 34: PROJECT LEADER COSTS
The Project Leader is required to spend at least 3 days in beneficiary administration every quarter
Project leader fees and 150% management costs
Airfares
Per diem
Translation of reports etc.
Interpretation
Final audit costs
Management of Logistics and Accounting are provided by the MS administration (and Partner MS) and covered out of the Management Costs (no additional cost to the contract)

## Slide 35: CONTRACT PREPARATION COSTS
Refundable upon endorsement of Contract for trips during the period up to 4 months (IPA)/5 months (ENI) following notification of selection
Projects ≤ 1 M€
Project Leader and RTA
6 flights
20 per diems
20 fees
Flat rate 150%
Projects > 1 M€
Project Leader and RTA
9 flights
30 per diems
30 fees
Flat rate 150%

## Slide 36: Preparation of the contract (Annex A)
Activities not detailed, just headline and total budget
Article 6. Indicative schedule can be grouped by quarter
Detailed activities for first six months described outside the contract, in the Operative Side Letter (OSL)
IPA

## Slide 37: The Operative Side Letter (OSL) Annex C15, p.202: Template for OSL (IPA)
To be prepared with the contract
First OSL: Detailed activities for minimum 6 months period
  Tasks
  Resources (experts)
  Budget
Approved at Project Steering Committees
Following OSLs: Revision of 3 months + addition 3 months more
Must be signed by both PL, no delegation of signature
5 working days before becoming effective
Draft OSL circulated by RTA at least 10 WD before SC meeting
IPA
Notes: More flexibility more responsibility
Special role of the PL but also JPL and beneficiary PL in draftingthe OSL and reviewing it every quarter
If confident enough it is always possible to make a detailed budget table till end of project

## Slide 38
IPA

## Slide 39: VISIBILITY COSTS
Funds for the printing of posters, banners and other items promoting the activities and acknowledging the funding source (EU)
Projects > 1 M€
10 000 euro
Projects ≤ 1 M€
5 000 euro
The funding source (EU) must be acknowledged on all documents, products and at events within the project.
As a minimum, the EU logo should be displayed

## Slide 40
    Thank you!