## Slide 1: Feedback by a former Resident Twinning Adviser
Lessons learned and recommendations
Brussels, 03 March 2016
Rudolf SPAN

## Slide 2: My Twinning-experience
2005 - 2007 Short-Term Expert - Romania
2007 - 2009 Resident Twinning Advisor - RO
2010 – 2011 Resident Twinning Advisor - RO
2011 - 2012 Short-Term Expert – Kosovo
<number>

## Slide 3: Let‘s start our excursion! What comes next?
<number>

## Slide 4: Content
The Resident Twinning Advisor (RTA)
Environment of the RTA
Implementation of the project
Conclusions
<number>

## Slide 5: The Resident Twinning Advisor
Tasks
Coordination of the implementation of the project
Achievement of the mandatory results
Professional support for the beneficiary institution – a real colleague!
<number>

## Slide 6: The Resident Twinning Advisor
Behaviour - Diplomatic skills
An 'ambassador' of your country of origine
An 'ambassador' of the European Union
Collaboration on very high level: -Ambassadors, Ministers, State Secretary, -EU-Delegation/Representation, EU-Commission,
-Executive board of different stakeholders -e.g. industry, associations, NGOs.
<number>

## Slide 7: The Resident Twinning Advisor
Skills
Management
Professional Expertise
Union legislation
EU - structure and functioning
Intercultural competences
Communication
<number>

## Slide 8: The start
Your expectation?
<number>

## Slide 9: The reality?
<number>

## Slide 10: First steps
Accommodation - Hotel => apartment for rent
Office
Contact - EU Delegation
Contact - own Embassy
Car registration
Health insurance
Doctors etc.
<number>

## Slide 11: First steps
Beneficiary institution
Hierarchy and counterparts in the beneficiary institution
Other relevant institutions
Assistants
Interpretation / Translation
Financial Unit
National experts
<number>

## Slide 12: Assistants
Early selection
Cooperative behavior is important
Be careful with recommendations
Translation vs. interpretation
Share of work between assistants
<number>

## Slide 13: Kick-off meeting
The first very official appearance of the RTA
High level guests
It has to be well organised
Start in due time
A crucial opportunity for visibility
Press release / press-conference
Presentation of the project
Presentation of the team (MS, BC, office)
<number>

## Slide 14: Kick-off meeting
It has to take place as soon as possible but not to early
already something to present, what can attract the press and the quests
Overview about the start of the project
Presentation of the work plan + implementation tools
Visibility material
Website!
<number>

## Slide 15: Your new environment
- The country - history, culture, - Language, Behaviour
- Political parties - Parliament
- Gouvernement
- Justice
- Media
- Economy, Trade
- Socialsecurity
<number>

## Slide 16: International context
International relations of the beneficiary country (BC)
European Union (Accession negotiations, benchmarks, progress reports, IPA program, Association agreements, country strategies, support programs)
EU Member States BC
Your country of origin  BC
Neighbours  BC
<number>

## Slide 17: Your professional environment
EU projects (previous, current, future)
Other projects (bilateral cooperation, world bank, etc.)
TAIEX
Resident experts
Stakeholders – international and national
<number>

## Slide 18: The institution to be supported
Get familiar with the structure
Organisational chart
Budget, infrastructure
Regional, local structure
Competencies
Cooperation and competition with other institutions
<number>

## Slide 19: Get familiar with the structure
Who is who?
Job security
Behaviour, habits
Workhours
Public holidays
Communication tools
<number>

## Slide 20: Current status?
<number>
'Current Situation Report'
Situation changed since the fiche was drafted
You need more details and additional special data.
Contact the leadership of the relevant institutions, units and stakeholders
Work together with the leaders of the working groups

## Slide 21: Reports
<number>
As specified in the Twinning contract!!!
RTA Office
Current Situation Report /Inception Report
Monthly Report / Technical Progress Report
Quarterly Report
Final Report
Short-term experts
Mission Report

## Slide 22: Management meetings Steering committee meetings
Directors, head of departments
BC project leader
regularly
discussing the progress
based on an activity plan
EU-Delegation
Central Financial and Contracting Unit
<number>

## Slide 23: EU Delegation
What do the EU Delegations do?
a key role in presenting, explaining and implementing EU’s foreign policies;
analyse and report on the policies and developments of their host countries;
conduct negotiations in accordance with given mandates.
How do the Delegations operate?
Maintaining political dialogue;
administering development aid;
supervision of EU trade issues and building cultural contacts.
<number>

## Slide 24: EU Delegation – support and monitoring
Close cooperation with the EU-Delegation is beneficial
General support in the implementation
Support in the collaboration with the BC-administration
Participation of the EU-Delegation at all important events
Kick-off, Steering Committee meetings, Final meeting etc.
<number>

## Slide 25: Implementing a project
Working groups
set up working groups
BC official as leader
set up up of rules
activity plan
regular meetings
discussing the progress
<number>

## Slide 26: Activity plans
follow up of the benchmarks
clear time schedule
what needs to be done
by whom
until when
calendars
expert-missions
study visits
<number>

## Slide 27: Additional useful documentation
results of discussions
minutes of the meetings
to be circulated to the beneficiaries
recommendations made
reminder for yourself
informal character
<number>

## Slide 28: Managing the experts
RTA shall be the bridge and the catalytic agent
overview and details
understanding the context
continuity
input – absorption capacity BC
no need to separate by MS
<number>

## Slide 29: Managing the experts
prepare objectives, terms of reference and agenda of the missions in due time
don’t waste expert days
allow the beneficiaries to evaluate the experts
mission reports of the experts in due time!
<number>

## Slide 30: Communication
Web based Intranet / share point
Access:
- Management of the project
Experts MS and BC
Working group members etc.
<number>

## Slide 31: Share point - Intranet
<number>

## Slide 32: Communication
Visibility – communication
Website – open for the public
Information for the stakeholders and for the citizens
It takes time but is essential during the implementation
added value after finalization of the project as well!
<number>

## Slide 33: Website
<number>

## Slide 34: Visibility – start without delay
<number>
Flyer
Brochures
Roll-up banners
Folders
USB-Sticks
Pencils
etc.

## Slide 35: During the implementation Support the needs of the BC
Benchmarks!
Output orientation
RTA shall provide additional input
Help the partners to contribute
Be realistic with your expectation
Remain optimistic and motivated
Develop plan B’s
<number>

## Slide 36: Challenges
Political instability
Continuity in the BC
Absorption capacity
Other working stiles, behaviours,
You need - patient, intercultural skills, enthusiasm, - target-oriented work, not forget the goals!
<number>

## Slide 37: Finalisation of the project
Final quarterly report
Final meeting
Final report
Focus on results/achievements
Recommendations
<number>

## Slide 38: Networking and follow up
Website!
Ensure that all contact details are available
Keep outputs of the project
Continue your support so far possible
Keep in touch
Lesssons learned?
Future cooperation?
<number>

## Slide 39: Added value for the RTA
A meaningful activity
Cooperation, collegiality,
Additional huge professional and life experience
Diplomatic and intercultural skills
International Management
EU Institutions
Visibility
But: it is hard work !!!
<number>

## Slide 40
THANK YOU FOR YOUR ATTENTION!
<number>
GOOD LUCK AND
SUCCESS!
Rudolf.Span@ec.europa.eu